## permit list
Permitting/compliance requirements for the Farallon Islands Restoration Project
Updated: 12/9/08
Permit | Purpose | Issuing agency | Responsible: | Duration of process | Target completion date | Post-implementation deliverables
NEPA analysis process (EA) | NEPA compliance (major Federal action) | FWS - CNO Region |  | Forever | 2009-06-26 | None
ESA Sec. 7 consultation (formal?) | Steller sea lion | NMFS - SW Region |  |  | 2009-04-21
ESA Sec. 7 consultation (informal?) | CA brown pelican | FWS-ES - CNO Region
IHA (MMPA) | Steller sea lion; CA sea lion; elephant seal; harbor seal; northern fur seal | NMFS - Nat'l |  |  | 2009-10-02
NOAA-Sanctuaries Manager's Permit | Activities in GFNMS | NOAA-GFNMS
CZMA consistency determination | Coastal zone actions | CA Coastal Commission
Wilderness Act Min. Requirements Analysis | Justification of actions w/in Designated Wilderness | FWS - CNO Region?
NHPA Sec. 106 consultation | Historical resources | FWS - CNO Region/SHPO
MBTA (specific reqs TBD) | Protection of migratory birds | FWS - CNO Region?
PUP | FWS approval of pesticide use | FWS - CNO Region
AMD (pilot/ops permits) | Fed. aviation regs | AMD - Regional?
Misc. Fed. safety regs | Boating; occupational safety; etc. | FWS
CA Pesticide Applicator permits | For personnel applying pesticide | CA (agency TBD)
CA State: pesticide use? | May need state concurrence | CA (agency TBD)
CA State: aerial pesticide application? | May need state concurrence | CA (agency TBD)
CA State: Collection permits? | May need state concurrence? | CA (agency TBD)

## Deliverables
DEC
product name
registration #
compnay product prucahse from
address
date purchased
amount purchased
date of use
location of use
rate of application
amount of product used
dilution rate of product used
target pests
site of use
name of person applying pesticide