## Full Budget 11%
LUCKENBACH - FARALLON ISLANDS HOUSE MOUSE ERADICATION PROJECT
UPDATED 15 NOVEMBER 2010
[5 empty] | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Phase 6
[5 empty] | Planning | Trial&NEPA | Implementation Planning | Implementation | Monitoring YR 1 | Monitoring YR 2
[5 empty] | Q3-2010 | Q4-2010 | FY2011 | FY2011 | FY 2012 | FY 2013
FUNDED IN FY2010
COOPERATIVE AGREEMENTS/CONTRACTS
ISLAND CONSERVATION (IC)
EXPENSES |  |  |  |  | TOTAL | TOTAL | TOTAL | TOTAL | TOTAL | TOTAL | TOTAL
6000 · Project Services
| Total 6000 · Project Services | [5 empty] | 10803.5775 | 750.5391 | 2498.9048 | 3075.1573
6090 · Field Work
|  | 6092 · Books,Periodicals,Subscriptions |  |  |  |  | 66.7901 | 15.174 | 20.1954 | 11.6282
|  |  | 6093.1 · Air Charter |  |  |  | 14000 | 18700 | 0 | 0
|  |  | 6093.2 · Sea Charter |  |  |  | 15000 | 0 | 5000 | 5000
|  | 6095 · Equipment |  |  |  |  | 5000 | 3000 | 0 | 0
|  | 6096 · Film,Photography |  |  |  |  | 140.3466 | 31.8853 | 42.4367 | 24.4345
|  | 6098 · Medical Evac Ins/Treatment |  |  |  |  | 1335.3751 | 303.3836 | 403.7782 | 232.4906
|  | 6099 · Supplies |  |  |  |  | 7084.7905 | 16360.0482 | 3979.1941 | 3025.9142
| Total 6090 · Field Work | [5 empty] | 42627.3023 | 38410.4911 | 9445.6044 | 8294.4676
6200 · Travel
|  | 6202 · Fees |  |  |  |  | 275.9086 | 62.6836 | 83.4266 | 48.0361
|  | 6203 · Hotel, Lodging |  |  |  |  | 8784.1033 | 496.206 | 2910.4087 | 2180.2553
|  | 6204 · Meals/Groceries |  |  |  |  | 2632.4738 | 4020.9179 | 2720.5691 | 2297.6113
|  | 6208 · Travel/Transportation |  |  |  |  | 18335.557 | 2120.9432 | 5822.7983 | 3125.3331
|  | 6200 · Travel - Other |  |  |  |  | 720 | 0 | 300 | 300
| Total 6200 · Travel | [5 empty] | 30748.0427 | 6700.7506 | 11837.2027 | 7951.2359
7000 · General Management
|  | 7030 · Depreciation expense |  |  |  |  | 0 | 1400 | 0 | 0
| Total 7000 · General Management | [5 empty] | 0 | 1400 | 0 | 0
7400 · Personnel Costs
|  | Employee benefits |  |  |  |  | 33778.5695 | 3400.9196 | 13511.1015 | 7283.862
7435 · 1099 Contractors
|  | Total 7435 · 1099 Contractors |  |  |  |  | 61162.7581 | 14835.8821 | 9040.5056 | 2326.4743
7436 · Payroll
|  |  |  | Executive Director |  |  | 7883.865 | 1791.1336 | 2383.8492 | 1372.5916
|  |  | Director | Directors |  |  | 24450.8113 | 3982.7801 | 5161.9983 | 753.1296
|  |  | Manager | Project Manager |  |  | 57123.2748 | 3029.6418 | 31954.909 | 16030.8781
|  |  | Specialist | Specialists |  |  | 36726.0012 | 6655.17 | 16705.3411 | 12347.8643
|  |  |  | NEPA specialist |  |  | 15625 | 0 | 0 | 0
|  |  |  | GIS specialist |  |  | 3917 | 0 | 0 | 0
|  |  |  | Communication |  |  | 7813 | 0 | 5208 | 2604
|  | Total 7436 Payroll |  |  |  |  | 153538.9523 | 15458.7255 | 61414.0977 | 33108.4636
|  | 7437 · Temp wages |  |  |  |  | 0 | 0 | 0 | 0
| Total 7400 · Personnel Costs | [5 empty] | 248480.2799 | 33695.5273 | 83965.7048 | 42718.7999
7600 · Professional Services
|  | 7100 · Science Program |  |  |  |  | 15388.2524 | 3496.0537 | 4652.9556 | 2679.1156
|  | 7610 · Consultants |  |  |  |  | 24429.4926 | 396.7853 | 528.0881 | 304.0667
| Total 7600 · Professional Services | [5 empty] | 39817.745 | 3892.839 | 5181.0437 | 2983.1823
7700 · Occupancy Expense
| Total 7700 · Occupancy Expense | [5 empty] | 10122.7711 | 2072.6004 | 2758.4581 | 1588.2868
SUBTOTAL IC PROGRAM EXPENSE | [6 empty] | 382599.7186 | 86922.7475 | 115686.9184 | 66611.1297
Project support allocation
ALLOCATED G & A | [6 empty] | 60326.216 | 13705.5 | 18240.876 | 10502.876
ISLAND CONSERVATION TOTAL |  |  |  |  | 55289 | 106954 | 442925.9346 | 100628.2475 | 133927.7944 | 77114.0057 | 916838.9822
PRBO CONSERVATION SCIENCE TOTAL |  |  |  |  | 0 | 12500 | 0 | 14500 | 9200 | 0 | 36200
NOAA - GULF OF THE FARALLONES NMS |  |  |  |  | 0 | 7500 | 0 | 7500 | 0 | 0 | 15000
U.S. FISH AND WILDLIFE SERVICE - FARALLON NWR
FWS Operating Costs
| Project Manager |  |  |  | 0 | 38945 | 0 | 39900 | 20300 | 20300 | 119445
| Administrative Assistance |  |  |  | 0 | 5000 | 0 | 5000 | 5000 | 2000 | 17000
| Supplies, Maintenance, other |  |  |  | 0 | 3000 | 0 | 2500 | 500 | 500 | 6500
| Final EA Printing |  |  |  | 1500 | 0 | 0 | 0 | 0 | 0 | 1500
| Introduction Prevention Plan |  |  |  | 0 | 0 | 0 | 5000 | 5000 | 0 | 10000
U.S. FISH AND WILDLIFE SERVICE - FARALLON NWR TOTAL |  |  |  |  | 1500 | 46945 | 0 | 52400 | 30800 | 22800 | 154445
NOAA INTERTIDAL FISH SAMPLING |  |  |  |  | 0 | 7500 | 0 | 7500 | 0 | 0 | 0
SUMMARY
TOTAL COOPERATIVE AGREEMENTS (PASS-THROUGH) |  |  |  |  | 55289 | 119454 | 442925.9346 | 115128.2475 | 143127.7944 | 77114.0057 | 953038.9822
TOTAL U.S. FISH AND WILDLIFE SERVICE (DIRECT ) |  |  |  |  | 1500 | 46945 | 0 | 52400 | 30800 | 22800 | 154445
FWS Direct Cost Recovery (11%) |  |  |  |  | 442.5 | 13848.775 | 0 | 5764 | 3388 | 2508 | 25951.275
FWS Pass-Through Recovery (6%) |  |  |  |  | 3317.34 | 7167.24 | 26575.5561 | 6907.6949 | 8587.6677 | 4626.8403 | 57182.3389
NOAA INTERTIDAL FISH SAMPLING |  |  |  |  | 0 | 7500 | 0 | 7500 | 0 | 0 | 15000
PROJECT TOTAL |  |  |  |  | 60548.84 | 194915.015 | 469501.4907 | 187699.9424 | 185903.462 | 107048.8461 | 1205617.5962
| Island Conservation | PRBO | USFWS | FWS Direct Cost Recovery | FWS Pass-through Recovery | NOAA | TOTAL
Original Budget | 674819.925 | 31000 | 176250 | 51993.75 | 43249.1955 | 15000 | 992312.8705
Current Budget | 916838.9822 | 36200 | 154445 | 25951.275 | 57182.3389 | 15000 | 1205617.5962
Difference | 242019.0572 | 5200 | -21805 | -26042.475 | 13933.1434 | 0 | 213304.7257
15% Contingency | [6 empty] | 148846.9306
Balance | FY2010 | FY2011 | FY2012 | FY2013
Island Conserv. | 512576.925 | -30977.2571 | -164905.0515 | -242019.0572
PRBO | 18500 | 4000 | -5200 | -5200
USFWS | 127805 | 75405 | 44605 | 21805
NOAA | 7500 | 0 | 0 | 0
Total | 736849.0155 | 79647.5824 | -106255.8796 | -213304.7257
Note on A1: PRBO Staff:

## 2011 Budget 11%
LUCKENBACH - FARALLON ISLANDS HOUSE MOUSE ERADICATION PROJECT
DRAFT FY2011 BUDGET (11/18/2010)
[5 empty] | Phase 3 | Phase 4
[5 empty] | Implementation Planning | Implementation
[5 empty] | FY2011 | FY2011 | TOTAL
COOPERATIVE AGREEMENTS/CONTRACTS
ISLAND CONSERVATION (IC)
EXPENSES
6000 · Project Services
| Total 6000 · Project Services |  |  |  | 10803.5775 | 750.5391 | 11554.1165
6090 · Field Work
|  | 6092 · Books,Periodicals,Subscriptions |  |  | 66.7901 | 15.174 | 81.9641
|  |  | 6093.1 · Air Charter |  | 14000 | 18700 | 32700
|  |  | 6093.2 · Sea Charter |  | 15000 | 0 | 15000
|  | 6095 · Equipment |  |  | 5000 | 3000 | 8000
|  | 6096 · Film,Photography |  |  | 140.3466 | 31.8853 | 172.232
|  | 6098 · Medical Evac Ins/Treatment |  |  | 1335.3751 | 303.3836 | 1638.7587
|  | 6099 · Supplies |  |  | 7084.7905 | 16360.0482 | 23444.8387
| Total 6090 · Field Work |  |  |  | 42627.3023 | 38410.4911 | 81037.7935
6200 · Travel
|  | 6202 · Fees |  |  | 275.9086 | 62.6836 | 338.5922
|  | 6203 · Hotel, Lodging |  |  | 8784.1033 | 496.206 | 9280.3093
|  | 6204 · Meals/Groceries |  |  | 2632.4738 | 4020.9179 | 6653.3917
|  | 6208 · Travel/Transportation |  |  | 18335.557 | 2120.9432 | 20456.5002
|  | 6200 · Travel - Other |  |  | 720 | 0 | 720
| Total 6200 · Travel |  |  |  | 30748.0427 | 6700.7506 | 37448.7934
7000 · General Management
|  | 7030 · Depreciation expense |  |  | 0 | 1400 | 1400
| Total 7000 · General Management |  |  |  | 0 | 1400 | 1400
7400 · Personnel Costs
|  | Employee benefits |  |  | 33778.5695 | 3400.9196 | 37179.4891
7435 · 1099 Contractors
|  | Total 7435 · 1099 Contractors |  |  | 61162.7581 | 14835.8821 | 75998.6403
7436 · Payroll
|  |  |  | Executive Director | 7883.865 | 1791.1336 | 9674.9986
|  |  | Director | Directors | 24450.8113 | 3982.7801 | 28433.5914
|  |  | Manager | Project Manager | 57123.2748 | 3029.6418 | 60152.9166
|  |  | Specialist | Specialists | 36726.0012 | 6655.17 | 43381.1712
|  |  |  | NEPA specialist | 15625 | 0 | 15625
|  |  |  | GIS specialist | 3917 | 0 | 3917
|  |  |  | Communication | 7813 | 0 | 7813
|  | Total 7436 Payroll |  |  | 153538.9523 | 15458.7255 | 168997.6778
|  | 7437 · Temp wages |  |  | 0 | 0 | 0
| Total 7400 · Personnel Costs |  |  |  | 248480.2799 | 33695.5273 | 282175.8072
7600 · Professional Services
|  | 7100 · Science Program |  |  | 15388.2524 | 3496.0537 | 18884.3062
|  | 7610 · Consultants |  |  | 24429.4926 | 396.7853 | 24826.2779
| Total 7600 · Professional Services |  |  |  | 39817.745 | 3892.839 | 43710.5841
7700 · Occupancy Expense
| Total 7700 · Occupancy Expense |  |  |  | 10122.7711 | 2072.6004 | 12195.3715
SUBTOTAL IC PROGRAM EXPENSE |  |  |  |  | 382599.7186 | 86922.7475 | 469522.4661
Project support allocation
ALLOCATED G & A |  |  |  |  | 60326.216 | 13705.5 | 74031.716
ISLAND CONSERVATION TOTAL |  |  |  |  | 442925.9346 | 100628.2475 | 543554.1821
PRBO CONSERVATION SCIENCE TOTAL |  |  |  |  | 0 | 14500 | 14500
U.S. FISH AND WILDLIFE SERVICE - FARALLON NWR
FWS Operating Costs
| Project Manager |  |  |  | 0 | 39900 | 39900
| Administrative Assistance |  |  |  | 0 | 5000 | 5000
| Supplies, Maintenance, other |  |  |  | 0 | 2500 | 2500
| Final EA Printing |  |  |  | 0 | 0 | 0
| Introduction Prevention Plan |  |  |  | 0 | 5000 | 5000
U.S. FISH AND WILDLIFE SERVICE - FARALLON NWR TOTAL |  |  |  |  | 0 | 52400 | 52400
SUMMARY
TOTAL COOPERATIVE AGREEMENTS (PASS-THROUGH) |  |  |  |  | 442925.9346 | 115128.2475 | 558054.1821
TOTAL U.S. FISH AND WILDLIFE SERVICE (DIRECT ) |  |  |  |  | 0 | 52400 | 52400
FWS Direct Cost Recovery (11%) |  |  |  |  | 0 | 5764 | 5764
FWS Pass-hrough Recovery (6%) |  |  |  |  | 26575.5561 | 6907.6949 | 33483.2509
NOAA (Intertidal fish sampling) |  |  |  |  | 0 | 7500 | 7500
PROJECT TOTAL |  |  |  |  | 469501.4907 | 187699.9424 | 657201.4331
Note on A1: PRBO Staff:

## Full Budget 29.5%
LUCKENBACH - FARALLON ISLANDS HOUSE MOUSE ERADICATION PROJECT
UPDATED 15 NOVEMBER 2010
[5 empty] | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Phase 6
[5 empty] | Planning | Trial&NEPA | Implementation Planning | Implementation | Monitoring YR 1 | Monitoring YR 2
[5 empty] | Q3-2010 | Q4-2010 | FY2011 | FY2011 | FY 2012 | FY 2013
FUNDED IN FY2010
COOPERATIVE AGREEMENTS/CONTRACTS
ISLAND CONSERVATION (IC)
EXPENSES |  |  |  |  | TOTAL | TOTAL | TOTAL | TOTAL | TOTAL | TOTAL | TOTAL
6000 · Project Services
| Total 6000 · Project Services | [5 empty] | 10803.5775 | 750.5391 | 2498.9048 | 3075.1573
6090 · Field Work
|  | 6092 · Books,Periodicals,Subscriptions |  |  |  |  | 66.7901 | 15.174 | 20.1954 | 11.6282
|  |  | 6093.1 · Air Charter |  |  |  | 14000 | 18700 | 0 | 0
|  |  | 6093.2 · Sea Charter |  |  |  | 15000 | 0 | 5000 | 5000
|  | 6095 · Equipment |  |  |  |  | 5000 | 3000 | 0 | 0
|  | 6096 · Film,Photography |  |  |  |  | 140.3466 | 31.8853 | 42.4367 | 24.4345
|  | 6098 · Medical Evac Ins/Treatment |  |  |  |  | 1335.3751 | 303.3836 | 403.7782 | 232.4906
|  | 6099 · Supplies |  |  |  |  | 7084.7905 | 16360.0482 | 3979.1941 | 3025.9142
| Total 6090 · Field Work | [5 empty] | 42627.3023 | 38410.4911 | 9445.6044 | 8294.4676
6200 · Travel
|  | 6202 · Fees |  |  |  |  | 275.9086 | 62.6836 | 83.4266 | 48.0361
|  | 6203 · Hotel, Lodging |  |  |  |  | 8784.1033 | 496.206 | 2910.4087 | 2180.2553
|  | 6204 · Meals/Groceries |  |  |  |  | 2632.4738 | 4020.9179 | 2720.5691 | 2297.6113
|  | 6208 · Travel/Transportation |  |  |  |  | 18335.557 | 2120.9432 | 5822.7983 | 3125.3331
|  | 6200 · Travel - Other |  |  |  |  | 720 | 0 | 300 | 300
| Total 6200 · Travel | [5 empty] | 30748.0427 | 6700.7506 | 11837.2027 | 7951.2359
7000 · General Management
|  | 7030 · Depreciation expense |  |  |  |  | 0 | 1400 | 0 | 0
| Total 7000 · General Management | [5 empty] | 0 | 1400 | 0 | 0
7400 · Personnel Costs
|  | Employee benefits |  |  |  |  | 33778.5695 | 3400.9196 | 13511.1015 | 7283.862
7435 · 1099 Contractors
|  | Total 7435 · 1099 Contractors |  |  |  |  | 61162.7581 | 14835.8821 | 9040.5056 | 2326.4743
7436 · Payroll
|  |  |  | Executive Director |  |  | 7883.865 | 1791.1336 | 2383.8492 | 1372.5916
|  |  | Director | Directors |  |  | 24450.8113 | 3982.7801 | 5161.9983 | 753.1296
|  |  | Manager | Project Manager |  |  | 57123.2748 | 3029.6418 | 31954.909 | 16030.8781
|  |  | Specialist | Specialists |  |  | 36726.0012 | 6655.17 | 16705.3411 | 12347.8643
|  |  |  | NEPA specialist |  |  | 15625 | 0 | 0 | 0
|  |  |  | GIS specialist |  |  | 3917 | 0 | 0 | 0
|  |  |  | Communication |  |  | 7813 | 0 | 5208 | 2604
|  | Total 7436 Payroll |  |  |  |  | 153538.9523 | 15458.7255 | 61414.0977 | 33108.4636
|  | 7437 · Temp wages |  |  |  |  | 0 | 0 | 0 | 0
| Total 7400 · Personnel Costs | [5 empty] | 248480.2799 | 33695.5273 | 83965.7048 | 42718.7999
7600 · Professional Services
|  | 7100 · Science Program |  |  |  |  | 15388.2524 | 3496.0537 | 4652.9556 | 2679.1156
|  | 7610 · Consultants |  |  |  |  | 24429.4926 | 396.7853 | 528.0881 | 304.0667
| Total 7600 · Professional Services | [5 empty] | 39817.745 | 3892.839 | 5181.0437 | 2983.1823
7700 · Occupancy Expense
| Total 7700 · Occupancy Expense | [5 empty] | 10122.7711 | 2072.6004 | 2758.4581 | 1588.2868
SUBTOTAL IC PROGRAM EXPENSE | [6 empty] | 382599.7186 | 86922.7475 | 115686.9184 | 66611.1297
Project support allocation
ALLOCATED G & A | [6 empty] | 60326.216 | 13705.5 | 18240.876 | 10502.876
ISLAND CONSERVATION TOTAL |  |  |  |  | 55289 | 106954 | 442925.9346 | 100628.2475 | 133927.7944 | 77114.0057 | 916838.9822
PRBO CONSERVATION SCIENCE TOTAL |  |  |  |  | 0 | 12500 | 0 | 14500 | 9200 | 0 | 36200
NOAA - GULF OF THE FARALLONES NMS |  |  |  |  | 0 | 7500 | 0 | 7500 | 0 | 0 | 15000
U.S. FISH AND WILDLIFE SERVICE - FARALLON NWR
FWS Operating Costs
| Project Manager |  |  |  | 0 | 38945 | 0 | 39900 | 20300 | 20300 | 119445
| Administrative Assistance |  |  |  | 0 | 5000 | 0 | 5000 | 5000 | 2000 | 17000
| Supplies, Maintenance, other |  |  |  | 0 | 3000 | 0 | 2500 | 500 | 500 | 6500
| Final EA Printing |  |  |  | 1500 | 0 | 0 | 0 | 0 | 0 | 1500
| Introduction Prevention Plan |  |  |  | 0 | 0 | 0 | 5000 | 5000 | 0 | 10000
U.S. FISH AND WILDLIFE SERVICE - FARALLON NWR TOTAL |  |  |  |  | 1500 | 46945 | 0 | 52400 | 30800 | 22800 | 154445
NOAA INTERTIDAL FISH SAMPLING |  |  |  |  | 0 | 7500 | 0 | 7500 | 0 | 0 | 0
SUMMARY
TOTAL COOPERATIVE AGREEMENTS (PASS-THROUGH) |  |  |  |  | 55289 | 119454 | 442925.9346 | 115128.2475 | 143127.7944 | 77114.0057 | 953038.9822
TOTAL U.S. FISH AND WILDLIFE SERVICE (DIRECT ) |  |  |  |  | 1500 | 46945 | 0 | 52400 | 30800 | 22800 | 154445
FWS Direct Cost Recovery (29.5%) |  |  |  |  | 442.5 | 13848.775 | 0 | 15458 | 9086 | 6726 | 45561.275
FWS Pass-hrough Recovery (6%) |  |  |  |  | 3317.34 | 7167.24 | 26575.5561 | 6907.6949 | 8587.6677 | 4626.8403 | 57182.3389
NOAA INTERTIDAL FISH SAMPLING |  |  |  |  | 0 | 7500 | 0 | 7500 | 0 | 0 | 15000
PROJECT TOTAL |  |  |  |  | 60548.84 | 194915.015 | 469501.4907 | 197393.9424 | 191601.462 | 111266.8461 | 1225227.5962
| Island Conservation | PRBO | USFWS | FWS Direct Cost Recovery (29.5%) | FWS Pass-through Recovery (6%) | NOAA | TOTAL
Original Budget | 674819.925 | 31000 | 176250 | 51993.75 | 43249.1955 | 15000 | 992312.8705
Current Budget | 916838.9822 | 36200 | 154445 | 45561.275 | 57182.3389 | 15000 | 1225227.5962
Difference | -242019.0572 | -5200 | 21805 | 6432.475 | -13933.1434 | 0 | -232914.7257
15% Contigency | [6 empty] | 148846.9306
difference-15% contingency | [6 empty] | -84067.7951
Coastal Conservancy funds | 150000 | [5 empty] | 150000
Difference-Coastal Conservancy | -92019.0572 | [5 empty] | -82914.7257
Balance | FY2010 | FY2011 | FY2012 | FY2013
Island Conserv. | 512576.925 | -30977.2571 | -164905.0515 | -242019.0572
PRBO | 18500 | 4000 | -5200 | -5200
USFWS | 127805 | 75405 | 44605 | 21805
NOAA | 7500 | 0 | 0 | 0
Total | 736849.0155 | 69953.5824 | -121647.8796 | -232914.7257
with Coastal Conservancy funds
Island Conserv. | 512576.925 | 119022.7429 | -14905.0515 | -92019.0572
Note on A1: PRBO Staff:

## 2011 Budget 29.5%
LUCKENBACH - FARALLON ISLANDS HOUSE MOUSE ERADICATION PROJECT
DRAFT FY2011 BUDGET (11/15/2010)
[5 empty] | Phase 3 | Phase 4
[5 empty] | Implementation Planning | Implementation
[5 empty] | FY2011 | FY2011
COOPERATIVE AGREEMENTS/CONTRACTS
ISLAND CONSERVATION (IC)
EXPENSES |  |  |  |  | TOTAL | TOTAL | TOTAL
6000 · Project Services
| Total 6000 · Project Services |  |  |  | 10803.5775 | 750.5391 | 11554.1165
6090 · Field Work
|  | 6092 · Books,Periodicals,Subscriptions |  |  | 66.7901 | 15.174 | 81.9641
|  |  | 6093.1 · Air Charter |  | 14000 | 18700 | 32700
|  |  | 6093.2 · Sea Charter |  | 15000 | 0 | 15000
|  | 6095 · Equipment |  |  | 5000 | 3000 | 8000
|  | 6096 · Film,Photography |  |  | 140.3466 | 31.8853 | 172.232
|  | 6098 · Medical Evac Ins/Treatment |  |  | 1335.3751 | 303.3836 | 1638.7587
|  | 6099 · Supplies |  |  | 7084.7905 | 16360.0482 | 23444.8387
| Total 6090 · Field Work |  |  |  | 42627.3023 | 38410.4911 | 81037.7935
6200 · Travel
|  | 6202 · Fees |  |  | 275.9086 | 62.6836 | 338.5922
|  | 6203 · Hotel, Lodging |  |  | 8784.1033 | 496.206 | 9280.3093
|  | 6204 · Meals/Groceries |  |  | 2632.4738 | 4020.9179 | 6653.3917
|  | 6208 · Travel/Transportation |  |  | 18335.557 | 2120.9432 | 20456.5002
|  | 6200 · Travel - Other |  |  | 720 | 0 | 720
| Total 6200 · Travel |  |  |  | 30748.0427 | 6700.7506 | 37448.7934
7000 · General Management
|  | 7030 · Depreciation expense |  |  | 0 | 1400 | 1400
| Total 7000 · General Management |  |  |  | 0 | 1400 | 1400
7400 · Personnel Costs
|  | Employee benefits |  |  | 33778.5695 | 3400.9196 | 37179.4891
7435 · 1099 Contractors
|  | Total 7435 · 1099 Contractors |  |  | 61162.7581 | 14835.8821 | 75998.6403
7436 · Payroll
|  |  |  | Executive Director | 7883.865 | 1791.1336 | 9674.9986
|  |  | Director | Directors | 24450.8113 | 3982.7801 | 28433.5914
|  |  | Manager | Project Manager | 57123.2748 | 3029.6418 | 60152.9166
|  |  | Specialist | Specialists | 36726.0012 | 6655.17 | 43381.1712
|  |  |  | NEPA specialist | 15625 | 0 | 15625
|  |  |  | GIS specialist | 3917 | 0 | 3917
|  |  |  | Communication | 7813 | 0 | 7813
|  | Total 7436 Payroll |  |  | 153538.9523 | 15458.7255 | 168997.6778
|  | 7437 · Temp wages |  |  | 0 | 0 | 0
| Total 7400 · Personnel Costs |  |  |  | 248480.2799 | 33695.5273 | 282175.8072
7600 · Professional Services
|  | 7100 · Science Program |  |  | 15388.2524 | 3496.0537 | 18884.3062
|  | 7610 · Consultants |  |  | 24429.4926 | 396.7853 | 24826.2779
| Total 7600 · Professional Services |  |  |  | 39817.745 | 3892.839 | 43710.5841
7700 · Occupancy Expense
| Total 7700 · Occupancy Expense |  |  |  | 10122.7711 | 2072.6004 | 12195.3715
SUBTOTAL IC PROGRAM EXPENSE |  |  |  |  | 382599.7186 | 86922.7475 | 469522.4661
Project support allocation
ALLOCATED G & A |  |  |  |  | 60326.216 | 13705.5 | 74031.716
ISLAND CONSERVATION TOTAL |  |  |  |  | 442925.9346 | 100628.2475 | 543554.1821
PRBO CONSERVATION SCIENCE TOTAL |  |  |  |  | 0 | 14500 | 14500
U.S. FISH AND WILDLIFE SERVICE - FARALLON NWR
FWS Operating Costs
| Project Manager |  |  |  | 0 | 39900 | 39900
| Administrative Assistance |  |  |  | 0 | 5000 | 5000
| Supplies, Maintenance, other |  |  |  | 0 | 2500 | 2500
| Final EA Printing |  |  |  | 0 | 0 | 0
| Introduction Prevention Plan |  |  |  | 0 | 5000 | 5000
U.S. FISH AND WILDLIFE SERVICE - FARALLON NWR TOTAL |  |  |  |  | 0 | 52400 | 52400
TOTAL COOPERATIVE AGREEMENTS (PASS-THROUGH) |  |  |  |  | 442925.9346 | 115128.2475 | 558054.1821
TOTAL U.S. FISH AND WILDLIFE SERVICE (DIRECT ) |  |  |  |  | 0 | 52400 | 52400
FWS Direct Cost Recovery (29.5%) |  |  |  |  | 0 | 15458 | 15458
FWS Pass-hrough Recovery (6%) |  |  |  |  | 26575.5561 | 6907.6949 | 33483.2509
NOAA (Intertidal fish sampling) |  |  |  |  | 0 | 7500 | 7500
PROJECT TOTAL |  |  |  |  | 469501.4907 | 197393.9424 | 666895.4331
Note on A1: PRBO Staff:

## Summary
| Island Conservation | PRBO | USFWS | FWS Direct Cost Recovery | FWS Pass-through Recovery | NOAA | TOTAL
Original Budget | 674819.925 | 31000 | 176250 | 51993.75 | 43249.1955 | 15000 | 992312.8705
Current Budget | 916838.9822 | 36200 | 154445 | 25951.275 | 57182.3389 | 15000 | 1205617.5962
Difference | 242019.0572 | 5200 | -21805 | -26042.475 | 13933.1434 | 0 | 213304.7257
15% Contingency | [6 empty] | 148846.9306
Balance | FY2010 | FY2011 | FY2012 | FY2013
Island Conserv. | 512576.925 | -30977.2571 | -164905.0515 | -242019.0572
PRBO | 18500 | 4000 | -5200 | -5200
USFWS | 127805 | 75405 | 44605 | 21805
NOAA | 7500 | 0 | 0 | 0
Total | 736849.0155 | 79647.5824 | -106255.8796 | -213304.7257