## Farallon Mouse Eradication
FARALLON MOUSE ERADICATION
Task - we need to submit a schedule as an attachment, it can be an excel spreadsheet of Gant Chart | Date | Federal Register |  |  | Database Milestones | Comment (internal)
Issue NOI for EIS | 2011-04-13 | 76 FR 20706 |  |  | Required Target Completion Date
End of Public Scoping
Issue NOA for Draft EIS | 2013-08-16 | 78 FR 52524 |  |  | Required Target Completion Date
Issue NOA for Revised Draft EIS | 2013-10-25 | 78 FR 63977 |  |  | Required Target Completion Date
Prepare Administrative draft Final EIS (including a draft of the ROD) | 2018-09-06
Internal Review of Administrative draft Final EIS | 2018-10-25
Final EIS ready for public distribution | 2018-12-06 |  |  |  |  | 30 business days following end of Admin draft review.
Final EIS package ready for Review Team. Package includes: Final EIS and Appendices; a draft of the Record of Decision; a draft of the Notice of Availability. Schedule briefing for the Review Team. | 2018-12-06
Prepare briefing materials for Review Team: Powerpoint overview of preferred alternative, purpose and need, alternatives, salient environmental impacts and resource conflicts, the significant opportunities and hurdles that exist in completing the project. Briefing materials should address (as appropriate) the Secretary's priorities, resolution of resource conflicts, land-use restrictions, transportation or access limitations, elected official views, and inter-jurisdictional considerations. | 2018-12-20
Provide briefing materials to Review Team 1 week prior to briefing. | 2019-01-02
Project Briefing to the Review Team | 2019-01-09
Review Team provides comments to Project Team (day of the briefing and up to 5 business days following) | 2019-01-16
Review Team approval | 2019-01-16
Delegated SES (Regional Director) signs and approves FEIS and NOA | 2019-01-17
File FEIS with EPA | 2019-01-18
Federal Register Notices Published - (Friday of the week following filing with EPA) | 2019-01-25 |  |  |  | Required Target Completion Date
Final EIS wait period - 30 days | 2019-02-25 |  |  |  |  | Need to check with Paul Souza, who requested 60 day wait period.
Submit Consistency Determination to the Coastal Commission (90 days in advance of the ROD) | 2019-01-25
EIS Project Team sends a one-page notice to the Review Team seeking objections to Final ROD approval. Notice includes: 1) a brief discussion on any substantive issues that arose during the Final EIS notice period, 2) the Final ROD text, and 3) confirmation that it did not change from what was initially reviewed, or advise of any outstanding issues that need to be addressed, such as protest resolutions or Governor's Consistency Review objections. | 2019-04-19
Review Team has 3 days to request an oral briefing or object to the ROD. | 2019-04-24
Regional Director signs ROD and NOA | 2019-04-27 |  |  |  | Required Target Completion Date
NOA sent to Federal Register for publication
PERMITS | ACTION | BUREAU POC: NAME, EMAIL, PHONE | TARGET COMPLETION DATE_1 | TARGET COMPLETION DATE_2 | TARGET COMPLETION DATE GUIDANCE | Comments
DOI Actions
Migratory Bird Treaty Act Special Purpose permit |  | Jennifer Brown, jennifer_c_brown@fws.gov, 916-978-6193 | 2019-07-27 |  | Required Target Completion Date - target date needed for Issuance of decision for permit/approval | 60 day approval period
NHPA Sec. 106 consultation |  | Julianne Polanco, calshpo.ohp@parks.ca.gov, (916) 445-7000 | 2019-07-27 |  |  | Issuance of decision for permit/approval
NON-DOI Actions
ESA Consultation - NOAA-NMFS |  | Susan Wang, susan.wang@noaa.gov, 562-980-4199 | 2018-10-05 | 2019-04-24 | Required Target Completion Date - 2 dates needed: Consultation Initiation Date and Final BO Issued | 6 month review period
Magnuson-Stevens Act |  | Amanda Morrison, amanda.morrison@noaa.gov, 707-575-6084 | 2018-10-05 | 2019-04-24 | Required Target Completion Date - 2 dates needed: Issuance of decision for permit/approval andNotice to proceed | Essential Fish Habitat consultation
Marine Mammal Protection Act Incidental Harassment Authorization |  | Rob Pauline, robert.pauline@noaa.gov, 301-427-8408 | 2020-04-27 | 2020-04-27 | Required Target Completion Date - 2 dates needed: Issuance of decision for permit/approval and Notice to proceed | 30 day comment period. 6 month review period
Consultation to Protect National Marine Sanctuaries |  | Maria Brown, maria.brown@noaa.gov, 415-561-6622 | 2019-04-24 | 2019-04-24 | Required Target Completion Date - 2 dates needed: Issuance of decision for permit/approval and Notice to proceed
State and other permits (not included in NEPA database)
CZMA - Coastal Consistency Determination (this is not currently in the list of Non-DOI Actions and the Department would need to develop a list of agreed upon milestones so we do not need to identify a completion date for Coastal Consistency at this point) |  |  | TBD |  |  | Prior to project implementation
CWA - NPDES (Regional Water Quality Board) |  |  | TBD |  |  | Prior to project implementation
CA State: Collection permit (CDFW) |  |  | TBD |  |  | Prior to project implementation
CA State: pesticide use (unlikely to be needed) |  |  | TBD |  |  | Prior to project implementation
CA Special closure permits (CDFW) |  |  | TBD |  |  | Prior to project implementation
Marine Life Protection Act - Marine Take permits (CDFW) |  |  | TBD |  |  | Prior to project implementation
Permit to store and use pyrotechniques |  |  | TBD |  |  | Prior to project implementation
BRIEF PROJECT DESCRIPTION
The U.S. Fish and Wildife Service proposes the eradication of the invasive house mouse on the South Farallon Islands. The preferred alternative is the aerial application of the rodenticide Brodifacoum-25D Conservation. The Farallon Islands comprise four groups of small islands located about 30 miles west of San Francisco. Together, they constitute the Farallon Islands Natonal Wildlife Refuge, administered by the USFWS. The islands host the largest seabird breeding colony in the lower 48 United States. Twenty-five percent of Califonia's breeding seabirds - an estimated 350,000 individuals of 13 species, breed on the South Farallon Islands. About 50% of the world population of the rare ashy storm-petrel (listed as a Species of Management Concern by the USFWS and a Bird Species of Special Concern by the California Department of Fish and Wildlife) breed on the islands. Other rare and endemic wildlife and plants make the Farallones a unique ecosystem. The invasive house mice pose a pervasive threat to these important natural resources. We anticipate that the complete removal of mice would allow many of the island's natural ecosytem processes to be restored.
KEY WORDS
Habitat Restoration; Invasive Species; Wildlife; Conservation and Preservation; Island Restoration; Rodent eradication
PROJECT MANAGER POC - Responsible for the overall project and must be able to take direct calls from DOI. | Anne Morkill
NEPA TEAM | NAME
NEPA Lead POC | Gerry McChesney; 510-792-0222; gerry_mcchesney@fws.gov
Solicitor POC | Veronica Rowan
1st line SES | Paul Souza
WAIVER
The FEIS will be greater than 150 pages. No waiver was obtained because there is a published Draft EIS - per Memorandum issued on April 27, 2018; Additional Direction for Implementing Secretary's Order 3355. The Service will meet the schedule requirements.
CO-LEAD Agency | None
COOPERATING AGENCY | None
CONTRACTOR USED | Environmental Policy Solutions
Formulas:
Date = [Date, row below]-3

## Farallones Schedule only
FARALLON MOUSE ERADICATION
| Start Date | End Date
Issue NOI for EIS |  | 2011-04-13
End of Public Scoping | 2011-04-13 | 2011-05-27
Issue NOA for Draft EIS |  | 2013-08-16
Issue NOA for Revised Draft EIS |  | 2013-10-25
Prepare Administrative draft Final EIS (including a draft of the ROD) |  | 2018-09-06
Internal Review of Administrative draft Final EIS | 2018-09-06 | 2018-10-25
Final EIS ready for public distribution and EIS Clearance Process | 2018-10-25 | 2018-12-06
Final EIS package ready for Review Team. Package includes: Final EIS and Appendices; a draft of the Record of Decision; a draft of the Notice of Availability. Schedule briefing for the Review Team. |  | 2018-12-06
Prepare briefing materials for Review Team: Powerpoint overview of preferred alternative, purpose and need, alternatives, salient environmental impacts and resource conflicts, the significant opportunities and hurdles that exist in completing the project. Briefing materials should address (as appropriate) the Secretary's priorities, resolution of resource conflicts, land-use restrictions, transportation or access limitations, elected official views, and inter-jurisdictional considerations. | 2018-12-06 | 2018-12-20
Provide briefing materials to Review Team 1 week prior to briefing. |  | 2019-01-02
Project Briefing to the Review Team |  | 2019-01-09
Review Team provides comments to Project Team (day of the briefing and up to 5 business days following) |  | 2019-01-16
Review Team approval |  | 2019-01-16
Delegated SES (Regional Director) signs and approves FEIS and NOA |  | 2019-01-17
File FEIS with EPA |  | 2019-01-18
Federal Register Notices Published - (Friday of the week following filing with EPA) |  | 2019-01-25
Final EIS wait period - 30 days | 2019-01-25 | 2019-02-25
Submit Consistency Determination to the Coastal Commission (90 days in advance of the ROD) |  | 2019-01-25
ROD Clearance Process - EIS Project Team sends a one-page notice to the Review Team seeking objections to Final ROD approval. Notice includes: 1) a brief discussion on any substantive issues that arose during the Final EIS notice period, 2) the Final ROD text, and 3) confirmation that it did not change from what was initially reviewed, or advise of any outstanding issues that need to be addressed, such as protest resolutions or Governor's Consistency Review objections. |  | 2019-04-19
Review Team has 3 days to request an oral briefing or object to the ROD. | 2019-04-19 | 2019-04-23
Regional Director signs ROD and NOA |  | 2019-04-26
NOA sent to Federal Register for publication |  | 2019-04-26
PERMITS
DOI Actions
Migratory Bird Treaty Act Special Purpose permit | 2019-01-25 | 2019-07-27
NHPA Sec. 106 consultation | 2019-01-25 | 2019-07-27
NON-DOI Actions
ESA Consultation - NOAA-NMFS | 2018-10-05 | 2019-04-24
Magnuson-Stevens Act | 2018-10-05 | 2019-04-24
Marine Mammal Protection Act Incidental Harassment Authorization | 2019-01-25 | 2020-04-27
Consultation to Protect National Marine Sanctuaries | 2019-01-25 | 2019-04-24
State and other permits (not included in NEPA and Permit Tracking Database)
CZMA - Coastal Consistency Determination | 2019-01-25 | 2019-04-26
CWA - NPDES (Regional Water Quality Board) |  | TBD | Prior to project implementation
CA State: Collection permit (CDFW) |  | TBD | Prior to project implementation
CA State: pesticide use (unlikely to be needed) |  | TBD | Prior to project implementation
CA Special closure permits (CDFW) |  | TBD | Prior to project implementation
Marine Life Protection Act - Marine Take permits (CDFW) |  | TBD | Prior to project implementation
Permit to store and use pyrotechniques |  | TBD | Prior to project implementation
RICRA (disposal of carcasses, unused bait) |  |  | Possibly make part of the project.
Rodenticide supplemental label |  |  | 6-9 mos from application