## Farallon Mouse Eradication
FARALLON MOUSE ERADICATION
Task - we need to submit a schedule as an attachment, it can be an excel spreadsheet of Gant Chart | Date | Federal Register |  |  | Database Milestones | Comment (internal)
Issue NOI for EIS | 2011-04-13 | 76 FR 20706 |  |  | Required Target Completion Date
End of Public Scoping
Issue NOA for Draft EIS | 2013-08-16 | 78 FR 52524 |  |  | Required Target Completion Date
Issue NOA for Revised Draft EIS | 2013-10-25 | 78 FR 63977 |  |  | Required Target Completion Date
Prepare Administrative draft Final EIS (including a draft of the ROD) | 2018-09-06
Internal Review of Administrative draft Final EIS | 2018-10-25
Final EIS ready for public distribution | 2018-12-06 |  |  |  |  | 30 business days following end of Admin draft review.
Final EIS package ready for Review Team. Package includes: Final EIS and Appendices; a draft of the Record of Decision; a draft of the Notice of Availability. Schedule briefing for the Review Team. | 2018-12-06
Prepare briefing materials for Review Team: Powerpoint overview of preferred alternative, purpose and need, alternatives, salient environmental impacts and resource conflicts, the significant opportunities and hurdles that exist in completing the project. Briefing materials should address (as appropriate) the Secretary's priorities, resolution of resource conflicts, land-use restrictions, transportation or access limitations, elected official views, and inter-jurisdictional considerations. | 2018-12-20
Provide briefing materials to Review Team 1 week prior to briefing. | 2019-01-02
Project Briefing to the Review Team | 2019-01-09
Review Team provides comments to Project Team (day of the briefing and up to 5 business days following) | 2019-01-16
Review Team approval | 2019-01-16
Delegated SES (Regional Director) signs and approves FEIS and NOA | 2019-01-17
File FEIS with EPA | 2019-01-18
Federal Register Notices Published - (Friday of the week following filing with EPA) | 2019-01-25 |  |  |  | Required Target Completion Date
Final EIS wait period - 30 days | 2019-02-25 |  |  |  |  | Need to check with Paul Souza, who requested 60 day wait period.
Submit Consistency Determination to the Coastal Commission (90 days in advance of the ROD) | 2019-01-25
EIS Project Team sends a one-page notice to the Review Team seeking objections to Final ROD approval. Notice includes: 1) a brief discussion on any substantive issues that arose during the Final EIS notice period, 2) the Final ROD text, and 3) confirmation that it did not change from what was initially reviewed, or advise of any outstanding issues that need to be addressed, such as protest resolutions or Governor's Consistency Review objections. | 2019-04-19
Review Team has 3 days to request an oral briefing or object to the ROD. | 2019-04-24
Regional Director signs ROD and NOA | 2019-04-27 |  |  |  | Required Target Completion Date
NOA sent to Federal Register for publication
PERMITS | ACTION | BUREAU POC: NAME, EMAIL, PHONE | TARGET COMPLETION DATE_1 | TARGET COMPLETION DATE_2 | TARGET COMPLETION DATE GUIDANCE | Comments
DOI Actions
Migratory Bird Treaty Act Special Purpose permit |  | Jennifer Brown, jennifer_c_brown@fws.gov, 916-978-6193 | 2019-07-27 |  | Required Target Completion Date - target date needed for Issuance of decision for permit/approval | 60 day approval period
NHPA Sec. 106 consultation |  | Julianne Polanco, calshpo.ohp@parks.ca.gov, (916) 445-7000 | 2019-07-27 |  |  | Issuance of decision for permit/approval
NON-DOI Actions
ESA Consultation - NOAA-NMFS |  | Susan Wang, susan.wang@noaa.gov, 562-980-4199 | 2018-10-05 | 2019-04-24 | Required Target Completion Date - 2 dates needed: Consultation Initiation Date and Final BO Issued | 6 month review period
Magnuson-Stevens Act |  | Amanda Morrison, amanda.morrison@noaa.gov, 707-575-6084 | 2018-10-05 | 2019-04-24 | Required Target Completion Date - 2 dates needed: Issuance of decision for permit/approval andNotice to proceed | Essential Fish Habitat consultation
Marine Mammal Protection Act Incidental Harassment Authorization |  | Michelle Magliocca, michelle.magliocca@noaa.gov, 301-427-8426 | 2020-04-27 | 2020-04-27 | Required Target Completion Date - 2 dates needed: Issuance of decision for permit/approval and Notice to proceed | 30 day comment period. 6 month review period
Consultation to Protect National Marine Sanctuaries |  | Maria Brown, maria.brown@noaa.gov, 415-561-6622 | 2019-04-24 | 2019-04-24 | Required Target Completion Date - 2 dates needed: Issuance of decision for permit/approval and Notice to proceed
State and other permits (not included in NEPA database)
CZMA - Coastal Consistency Determination (this is not currently in the list of Non-DOI Actions and the Department would need to develop a list of agreed upon milestones so we do not need to identify a completion date for Coastal Consistency at this point) |  |  | TBD |  |  | Prior to project implementation
CWA - NPDES (Regional Water Quality Board) |  |  | TBD |  |  | Prior to project implementation
CA State: Collection permit (CDFW) |  |  | TBD |  |  | Prior to project implementation
CA State: pesticide use (unlikely to be needed) |  |  | TBD |  |  | Prior to project implementation
CA Special closure permits (CDFW) |  |  | TBD |  |  | Prior to project implementation
Marine Life Protection Act - Marine Take permits (CDFW) |  |  | TBD |  |  | Prior to project implementation
Permit to store and use pyrotechniques |  |  | TBD |  |  | Prior to project implementation
BRIEF PROJECT DESCRIPTION
The U.S. Fish and Wildife Service proposes the eradication of the invasive house mouse on the South Farallon Islands. The preferred alternative is the aerial application of the rodenticide Brodifacoum-25D Conservation. The Farallon Islands comprise four groups of small islands located about 30 miles west of San Francisco. Together, they constitute the Farallon Islands Natonal Wildlife Refuge, administered by the USFWS. The islands host the largest seabird breeding colony in the lower 48 United States. Twenty-five percent of Califonia's breeding seabirds - an estimated 350,000 individuals of 13 species, breed on the South Farallon Islands. About 50% of the world population of the rare ashy storm-petrel (listed as a Species of Management Concern by the USFWS and a Bird Species of Special Concern by the California Department of Fish and Wildlife) breed on the islands. Other rare and endemic wildlife and plants make the Farallones a unique ecosystem. The invasive house mice pose a pervasive threat to these important natural resources. We anticipate that the complete removal of mice would allow many of the island's natural ecosytem processes to be restored.
KEY WORDS
Habitat Restoration; Invasive Species; Wildlife; Conservation and Preservation; Island Restoration; Rodent eradication
PROJECT MANAGER POC - Responsible for the overall project and must be able to take direct calls from DOI. | Anne Morkill
NEPA TEAM | NAME
NEPA Lead POC | Gerry McChesney; 510-792-0222; gerry_mcchesney@fws.gov
Solicitor POC | Veronica Rowan
1st line SES | Paul Souza
WAIVER
The FEIS will be greater than 150 pages. No waiver was obtained because there is a published Draft EIS - per Memorandum issued on April 27, 2018; Additional Direction for Implementing Secretary's Order 3355. The Service will meet the schedule requirements.
CO-LEAD Agency | None
COOPERATING AGENCY | None
CONTRACTOR USED | Environmental Policy Solutions
Formulas:
Date = [Date, row below]-3

## SBSP Eden Landing
SBSP RESTORATION, PHASE 2 AT EDEN LANDING
Task - we need to submit a schedule, can be an excel spreadsheet or Gant Chart | Date | Federal Register
Issue NOI for EIS | 2016-06-20 | 81 FR 39949 | completed
End of Public Scoping | 2016-07-20 |  | completed
Issue NOA for Draft EIS | 2018-04-06 | 83 FR 14852 | completed
Complete Administrative draft Final EIS | 2018-11-09 |  | Target completion date
Complete Internal Review of Administrative draft Final EIS | 2019-01-11 |  | Target completion date
Final EIS package ready for Review Team. Package includes: Final EIS and Appendices; a draft of the Record of Decision; a draft of the Notice of Availability. | 2019-01-14 |  | Target completion date
Prepare briefing materials for Review Team: Powerpoint overview of preferred alternative, purpose and need, alternatives, salient environmental impacts and resource conflicts, the significant opportunities and hurdles that exist in completing the project. Briefing materials should address (as appropriate) the Secretary's priorities, resolution of resource conflicts, land-use restrictions, transportation or access limitations, elected official views, and inter-jurisdictional considerations.
Schedule an oral briefing for the Review Team. | tbd
Provide briefing materials to Review Team 1 week prior to briefing. | tbd
Project Briefing to the Review Team | tbd
Review Team provides comments to Project Team (day of the briefing and up to 5 business days following) | tbd
Review Team/EIS Clearance Process completed | 2019-02-08
Delegated SES (Regional Director) signs and approves FEIS and NOA | 2019-02-08
File FEIS with EPA | 2019-02-15
Federal Register Notices Published - (Friday of the week following filing with EPA) | 2019-02-22 |  | Required Target Completion Date
Final EIS wait period - 30 days | 2019-03-25
EIS Project Team sends a one-page notice to the Review Team seeking objections to Final ROD approval. Notice includes: 1) a brief discussion on any substantive issues that arose during the Final EIS notice period, 2) the Final ROD text, and 3) confirmation that it did not change from what was initially reviewed, or advise of any outstanding issues that need to be addressed, such as protest resolutions or Governor's Consistency Review objections. | 2019-04-12
Review Team has 3 days to request an oral briefing or object to the ROD.
Regional Director signs ROD and NOA | 2019-04-26 |  | These oral briefings kill the timeline
NOA sent to Federal Register for publication | 2019-04-26
PERMITS | ACTION | BUREAU POC: NAME, EMAIL, PHONE | TARGET COMPLETION DATE | NOTES
DOI Actions
DOI Actions | 1/24/2019- 7/26/2019 |  | Required Target Completion Date - 2 dates needed: Consultation Initiation Date and Final BO Issued | average 1 year
ESA Consultation - FWS | 1/24/2019- 7/26/2019 |  | Required Target Completion Date
Required Target Completion Date - target date needed for Issuance of decision for permit/approval
NON-DOI Actions |  |  |  | NMFS and BCDC permits are over 1 year to secure dates and some agencies will not start review until they receive a copy of the other agencies permits (BCDC requires RWQCB and NMFS permits prior to issuance of scheduling board hearing for the CD).
ESA Consultation - NOAA-NMFS | 1/24/2019- 7/26/2019 |  | Required Target Completion Date - 2 dates needed: Consultation Initiation Date and Final BO Issued
Magnuson-Stevens Act | N/A |  | Required Target Completion Date - 2 dates needed: Issuance of decision for permit/approval andNotice to proceed
BCDC-San Francisco Bay Conservation and Devlopment Commission (authority McAteer-Petris Act) | 1/24/2019- 7/26/2019
Clean Water Act, Section 404 |  |  | Required Target Completion Date - 3 milestone dates needed: Pre-Construction Notification (PCN)/Application Deemed Complete; Publication of Public Notice; Final Verification/Permit Decision Rendered
RWQCB | 1/24/2019- 7/26/2019
BRIEF PROJECT DESCRIPTION
The U.S. Fish and Wildife Service and the California Department of Fish and Wildife are preparing a joint EIS/EIR focused on Phase 2 of salt pond restoration at the Eden Landing Ecological Reserve. The joint EIS/EIR is a project-level environmental document that tiers from the Programmatic actions described in the 2007 South Bay Salt Pond Restoration Project EIS/EIR.
KEY WORDS
Habitat Restoration; Wildlife; Conservation and Preservation; Other - we can add other key words, let me know.
PROJECT MANAGER POC - Responsible for the overall project and must be able to take direct calls from DOI. | Anne Morkill
NEPA TEAM | NAME
NEPA Lead POC | Patricia Roberson
Solicitor POC | Greg Lind
1st line SES | Paul Souza
WAIVER
The FEIS will be greater than 150 pages and will not be completed by April 27, 2019. This is a joint NEPA/CEQA project and will be covered by the blanket waiver for projects constrained by State Environmental laws.
CO-LEAD Agency
California State Coastal Conservancy | Matt Gerhart,Matt.Gerhart@scc.ca.gov, 510-286-0317
USFWS- San Francisco Bay NWR Complex
COOPERATING AGENCY
United States Army Corp of Engineers
Alameda County Flood Control and Water Conservation District
East Bay Regional Parks District
CONTRACTOR USED
John Bourgeois, Executive Project Manager to the State California Coastal Conservancy | John Bourgeois, john.bourgeois@scc.ca.gov, 408-314-8859
AECOM | Dillion Lennebacker, Dillon.Lennebacker@aecom.com, 1-510-874-3035

## M&T Long Term
M&T/Llano Seco Fish Screen Facility Long-Term Protection Project
Task - we need to submit a schedule as an attachment, it can be an excel spreadsheet of Gant Chart | Date | Federal Register | Database Milestones
Issue NOI for EIS | 2016-07-13 | 81 FR 45296 | Required Target Completion Date
End of Public Scoping | 2016-08-12
Prepare Administrative Draft EIS/EIR
Internal Review of Administrative Draft EIS/EIR
Draft EIS/EIR ready for Project Review Team
Final EIS package ready for Review Team. Package includes: Final EIS and Appendices; a draft of the Record of Decision; a draft of the Notice of Availability.
Prepare briefing materials for Review Team: Powerpoint overview of preferred alternative, purpose and need, alternatives, salient environmental impacts and resource conflicts, the significant opportunities and hurdles that exist in completing the project. Briefing materials should address (as appropriate) the Secretary's priorities, resolution of resource conflicts, land-use restrictions, transportation or access limitations, elected official views, and inter-jurisdictional considerations.
Schedule an oral briefing for the Review Team.
Provide briefing materials to Review Team 1 week prior to briefing.
Project Briefing to the Review Team
Review Team provides comments to Project Team (day of the briefing and up to 10 business days following)
Review Team approval
Delegated SES (Regional Director) signs NOA and approves release of DEIS/EIR
File Draft EIS/EIR with EPA | 2019-01-18
Federal Register Notices Published - (Friday of the week following filing with EPA) | 2019-01-25 |  | Required Target Completion Date
Prepare Administrative draft Final EIS (including a draft of the ROD)
Internal Review of Administrative draft Final EIS/EIR
Final EIS/EIR ready for public distribution
Final EIS/EIR package ready for Review Team. Package includes: Final EIS/EIR and Appendices; a draft of the Record of Decision; a draft of the Notice of Availability.
Prepare briefing materials for Review Team: Powerpoint overview of preferred alternative, purpose and need, alternatives, salient environmental impacts and resource conflicts, the significant opportunities and hurdles that exist in completing the project. Briefing materials should address (as appropriate) the Secretary's priorities, resolution of resource conflicts, land-use restrictions, transportation or access limitations, elected official views, and inter-jurisdictional considerations.
Schedule an oral briefing for the Review Team.
Provide briefing materials to Review Team 1 week prior to briefing.
Project Briefing to the Review Team
Review Team provides comments to Project Team (day of the briefing and up to 5 business days following)
Review Team approval
Delegated SES (Regional Director) signs and approves FEIS and NOA
File FEIS/EIR with EPA | 2019-10-11
Federal Register Notices Published - (Friday of the week following filing with EPA) | 2019-10-18 |  | Required Target Completion Date
Final EIS wait period - 30 days | 2019-11-18
EIS Project Team sends a one-page notice to the Review Team seeking objections to Final ROD approval. Notice includes: 1) a brief discussion on any substantive issues that arose during the Final EIS notice period, 2) the Final ROD text, and 3) confirmation that it did not change from what was initially reviewed, or advise of any outstanding issues that need to be addressed, such as protest resolutions or Governor's Consistency Review objections.
Review Team has 3 days to request an oral briefing or object to the ROD.
Regional Director signs ROD and NOA | 2019-11-29 |  | Required Target Completion Date
NOA for the ROD sent to Federal Register for publication
PERMITS |  | BUREAU POC: NAME, EMAIL, PHONE | TARGET COMPLETION DATE
DOI Actions
ESA Section 7 consultation - FWS | 2019-01-02 | 2019-05-15 | Required Target Completion Date - 2 dates needed: Consultation Initiation Date and Final BO Issued
Section 106/SHPO | 2018-06-01 | 2018-07-01 | Required Target Completion Date - 4 milestone dates: Initial application received; Completed application received; Issuance of decision for permit/approval; Notice to proceed
NON-DOI Actions
ESA Consultation - NOAA-NMFS | 2019-01-02 | 2019-05-15 | Required Target Completion Date - 2 dates needed: Consultation Initiation Date and Final BO Issued
Magnuson-Stevens Act | 2019-01-02 | 2019-05-15 | Required Target Completion Date - 2 dates needed: Issuance of decision for permit/approval andNotice to proceed
USACE - Section 404 | 2019-04-01 | 2019-11-01 | Required Target Completion Date - 3 milestone dates needed: Pre-Construction Notification (PCN)/Application Deemed Complete; Publication of Public Notice; Final Verification/Permit Decision Rendered
USACE - Section 10 | 2019-04-01 | 2019-11-01 | Required Target Completion Date - 3 milestone dates needed: Pre-Construction Notification (PCN)/Application Deemed Complete; Publication of Public Notice; Final Verification/Permit Decision Rendered
BRIEF PROJECT DESCRIPTION
The U.S. Fish and Wildife Service and the California Department of Fish and Wildlife are preparing a joint environmental impact statement/environmental impact report (EIS/EIR) for the proposed M&T/Llano Seco Fish Screen Facility Long-Term Protection Project. The EIS/EIR will present and analyze a range of alternatives that would provide a reliable long-term water supply for agricultural lands and the wildlife refuges while protecting endangered species and their habitats in the Sacramento River.
KEY WORDS
Habitat Restoration; Water Resources; Wildlife; Infrastructure; Conservation and Preservation; Right-of-Way; Other - we can add other key words, let me know.
PROJECT MANAGER POC - Responsible for the overall project and must be able to take direct calls from DOI. | Curt McCasland
NEPA TEAM | NAME
NEPA Lead POC
Solicitor POC | Veronica Rowan
1st line SES | Paul Souza
WAIVER
The FEIS will be greater than 150 pages and will not be completed by April 27, 2019. This is a joint NEPA/CEQA project and will be covered by the blanket waiver for projects constrained by State Environmental laws.
CO-LEAD Agency | None | This refers to another federal agency, so I indicated none.
COOPERATING AGENCY | None | I thought the Corps was going to be a cooperating agency but I don't see them listed in the NOI.
CONTRACTOR USED | Yes - ICF - Mike Rushton is still the contact?

## OREP
OREP
Task - we need to submit a schedule as an attachment, it can be an excel spreadsheet of Gantt Chart | Date | Federal Register | Database Milestones
NOI | 2011-11-14 | 76 FR 70480 | Required Target Completion Date
NOA for Draft EIS/EIR | 2016-10-21 | 81 FR 72817 | Required Target Completion Date
NOA for Final EIS/EIR | 2018-05-18 | 83 FR 23289 | Required Target Completion Date
Final EIS wait period - 30 days | 2018-06-21
EIS Project Team sends a one-page notice to the Review Team seeking objections to Final ROD approval. Notice includes: 1) a brief discussion on any substantive issues that arose during the Final EIS notice period, 2) the Final ROD text, and 3) confirmation that it did not change from what was initially reviewed, or advise of any outstanding issues that need to be addressed, such as protest resolutions or Governor's Consistency Review objections.
Review Team has 3 days to request an oral briefing or object to the ROD.
Regional Director signs ROD and NOA | 2018-10-22 |  | Required Target Completion Date
NOA sent to Federal Register for publication
PERMITS | ACTION | BUREAU POC: NAME, EMAIL, PHONE | TARGET COMPLETION DATE
DOI Actions
None | N/A |  | Required Target Completion Date
NON-DOI Actions
ESA Consultation - NOAA-NMFS | 6/18/2018 Consultation Initiation Date 08/18/2018 Final BO Issued | Brian Collins; brian_collins@fws.gov; 619-575-2704 ext. 302 | Required Target Completion Date - 2 dates needed: Consultation Initiation Date and Final BO Issued
Magnuson-Stevens Act | 6/18/2018 EFH Consultation Initiation Date 08/18/2018 Final EFH Consultation Issued | Brian Collins; brian_collins@fws.gov; 619-575-2704 ext. 302 | Required Target Completion Date - 2 dates needed: Issuance of decision for permit/approval and Notice to proceed
USACE - 404 Permit (Nationwide Permit 27) | 12/18/2018 Nationwide permit application; 03/18/2019 NW27 permit issued (note: Dudek preparing NW27 permit application) | Brian Collins; brian_collins@fws.gov; 619-575-2704 ext. 302 | Required Target Completion Date - 3 milestone dates needed: Pre-Construction Notification (PCN)/Application Deemed Complete; Publication of Public Notice; Final Verification/Permit Decision Rendered
BRIEF PROJECT DESCRIPTION
The U.S. Fish and Wildlife Service proposes to restore approximately 125 acres of coastal wetlands and associated uplands at two locations on the San Diego Bay National Wildlife Refuge, San Diego County, California. The proposed action, which would implement restoration proposals included in the San Diego Bay National Wildlife Refuge Comprehensive Conservation Plan would involve restoring tidal influence to a 33.5-acre portion of the Otay River floodplain and a 91-acre active solar salt pond.
KEY WORDS
Habitat Restoration; Wildlife; Conservation and Preservation; salt marsh restoration Other - we can add other key words, let me know.
PROJECT MANAGER POC- Responsible for overall project and must be able to take direct calls from DOI. | Andy Yuen | andy_yuen@fws.gov; 619-476-9150 ext. 100
NEPA TEAM | NAME
NEPA Lead POC | Vicki Touchstone | victoria_touchstone@fws.gov; 619-476-9150 ext. 103
Solicitor POC | Greg Lind
1st line SES | Paul Souza
WAIVER
The FEIS will be greater than 150 pages. No waiver was obtained because there is already a published Final EIS - The Service will meet the schedule requirements.
CO-LEAD Agency | None
COOPERATING AGENCY | U.S. Army Corps of Engineers; Robert Revo Smith Jr., P.E., M. ASCE; Senior Project Manager, Regulatory Division U.S. Army Corps of Engineers; 5900 La Place Ct. Suite 100; Carlsbad, CA 92008; Email: Robert.r.smith@usace.army.mil
CONTRACTOR USED | DUDEK; Brian Grover; bgrover@dudek.com; 605 Third Street; Encinitas, CA 92024; (760) 479-4248; www.dudek.com

## Farallones Schedule only
FARALLON MOUSE ERADICATION
| Start Date | End Date
Issue NOI for EIS |  | 2011-04-13
End of Public Scoping | 2011-04-13 | 2011-05-27
Issue NOA for Draft EIS |  | 2013-08-16
Issue NOA for Revised Draft EIS |  | 2013-10-25
Prepare Administrative draft Final EIS (including a draft of the ROD) |  | 2018-09-06
Internal Review of Administrative draft Final EIS | 2018-09-06 | 2018-10-25
Final EIS ready for public distribution and EIS Clearance Process | 2018-10-25 | 2018-12-06
Final EIS package ready for Review Team. Package includes: Final EIS and Appendices; a draft of the Record of Decision; a draft of the Notice of Availability. Schedule briefing for the Review Team. |  | 2018-12-06
Prepare briefing materials for Review Team: Powerpoint overview of preferred alternative, purpose and need, alternatives, salient environmental impacts and resource conflicts, the significant opportunities and hurdles that exist in completing the project. Briefing materials should address (as appropriate) the Secretary's priorities, resolution of resource conflicts, land-use restrictions, transportation or access limitations, elected official views, and inter-jurisdictional considerations. | 2018-12-06 | 2018-12-20
Provide briefing materials to Review Team 1 week prior to briefing. |  | 2019-01-02
Project Briefing to the Review Team |  | 2019-01-09
Review Team provides comments to Project Team (day of the briefing and up to 5 business days following) |  | 2019-01-16
Review Team approval |  | 2019-01-16
Delegated SES (Regional Director) signs and approves FEIS and NOA |  | 2019-01-17
File FEIS with EPA |  | 2019-01-18
Federal Register Notices Published - (Friday of the week following filing with EPA) |  | 2019-01-25
Final EIS wait period - 30 days | 2019-01-25 | 2019-02-25
Submit Consistency Determination to the Coastal Commission (90 days in advance of the ROD) |  | 2019-01-25
ROD Clearance Process - EIS Project Team sends a one-page notice to the Review Team seeking objections to Final ROD approval. Notice includes: 1) a brief discussion on any substantive issues that arose during the Final EIS notice period, 2) the Final ROD text, and 3) confirmation that it did not change from what was initially reviewed, or advise of any outstanding issues that need to be addressed, such as protest resolutions or Governor's Consistency Review objections. |  | 2019-04-19
Review Team has 3 days to request an oral briefing or object to the ROD. | 2019-04-19 | 2019-04-23
Regional Director signs ROD and NOA |  | 2019-04-26
NOA sent to Federal Register for publication |  | 2019-04-26
PERMITS
DOI Actions
Migratory Bird Treaty Act Special Purpose permit | 2019-01-25 | 2019-07-27
NHPA Sec. 106 consultation | 2019-01-25 | 2019-07-27
NON-DOI Actions
ESA Consultation - NOAA-NMFS | 2018-10-05 | 2019-04-24
Magnuson-Stevens Act | 2018-10-05 | 2019-04-24
Marine Mammal Protection Act Incidental Harassment Authorization | 2019-01-25 | 2020-04-27
Consultation to Protect National Marine Sanctuaries | 2019-01-25 | 2019-04-24
State and other permits (not included in NEPA and Permit Tracking Database)
CZMA - Coastal Consistency Determination | 2019-01-25 | 2019-04-26
CWA - NPDES (Regional Water Quality Board) |  | TBD | Prior to project implementation
CA State: Collection permit (CDFW) |  | TBD | Prior to project implementation
CA State: pesticide use (unlikely to be needed) |  | TBD | Prior to project implementation
CA Special closure permits (CDFW) |  | TBD | Prior to project implementation
Marine Life Protection Act - Marine Take permits (CDFW) |  | TBD | Prior to project implementation
Permit to store and use pyrotechniques |  | TBD | Prior to project implementation

## Phase 2 DonEdwards
SBSP Phase 2 at Don Edwards NWR
Task - we need to submit a schedule as an attachment, it can be an excel spreadsheet of Gantt Chart | Date | Federal Register | Database Milestones
NOI | 2013-09-16 | 78 FR 56921 | completed
NOA for Draft EIS/EIR | 2015-07-22 | 80 FR 43456 | completed
NOA for Final EIS/EIR | 2016-06-03 | 81 FR 35790 | completed
Final EIS wait period - 30 days | 2016-07-03 |  | completed
EIS Project Team sends a one-page notice to the Review Team seeking objections to Final ROD approval. Notice includes: 1) a brief discussion on any substantive issues that arose during the Final EIS notice period, 2) the Final ROD text, and 3) confirmation that it did not change from what was initially reviewed, or advise of any outstanding issues that need to be addressed, such as protest resolutions or Governor's Consistency Review objections. | tbd
Review Team has 3 days to request an oral briefing or object to the ROD. | tbd
Regional Director signs ROD and NOA | 2018-09-27 |  | 2018-06-15
NOA sent to Federal Register for publication | 2018-09-28 |  | 2018-07-31
PERMITS | ACTION | BUREAU POC: NAME, EMAIL, PHONE | TARGET COMPLETION DATE
DOI Actions
ESA Consultation - FWS | 2017-11-21 | Kaylee Allen, kaylee_allen@fws.gov,916-930-5632 | completed
Section 106-National Historic Preservation Act | 2015-09-15 | Lou-Anne Speulda-Drews,louann_speulda-drews@fws.gov ,775-861-6335 | completed | amendmendment to programtic Sec 106 completed
NON-DOI Actions
ESA Consultation - NOAA-NMFS | 2017-05-23 | Gary Stern, gary.stern@noaa.gov, 707-575-6060 | Expected completion date
Magnuson-Stevens Act | N/A |  | Required Target Completion Date
USACE - 404 Permit |  | 2018-07-27 | Corps wants BCDC to weigh in before permitting
RWQCB | 2018-05-09 | Brian Wines, Brian.Wines@waterboards.ca.gov,510-622-5680 | completed
BCDC-San Francisco Bay Conservation and Devlopment Commission (authority McAteer-Petris Act) | 2018-06-29 | Brenda Goeden, brenda.goeden@bcdc.ca.gov, 415.352.3623 | Expected completion date
BRIEF PROJECT DESCRIPTION
The U.S. Fish and Wildlife Service and the California State Coastal Conservancy propose restoration or enhancement of over 2,000 acres of former salt ponds in the second phase of the South Bay Salt Pond Restoration Project. The action agencies would continue habitat restoration activities on USFWS salt pond complexes, while also providing recreation and public access opportunities at two sets of ponds and maintaining or improving current levels of flood protection in the surrounding communities. The remaining action for the USFWS is the signature of a Record of Decision. The Don Edwards EIS and Eden EIS are both projects under the programmatic EIR for the South Bay Salt Pond Restoration Project. Under Phase 1 projects they were in a combined EIS and for Phase 2 the EIS's were separated but are still related to the programmatic approach for restoring former salt ponds under this landscape level project.
KEY WORDS
Habitat Restoration; Wildlife; Conservation and Preservation; Other - we can add other key words, let me know.
PROJECT MANAGER POC- Responsible for overall project and must be able to take direct calls from DOI. | Anne Morkill
NEPA TEAM | NAME
NEPA Lead POC | Chris Barr, chris_barr@fws.gov, 510-792-0222 x127
Solicitor POC | Greg Lind
1st line SES | Paul Souza
WAIVER
The FEIS will be greater than 150 pages. No waiver was obtained because there is already a published Final EIS - The Service will meet the schedule requirements.
CO-LEAD Agency
California State Coastal Conservancy | Matt Gerhart
COOPERATING AGENCY |  |  | Mentioned in the EIS
California Department of Fish & Wildlife
United States Army Corp of Engineers
Santa Clara Valley Water District
City of Mounatin View
City of redwood City
CONTRACTOR USED
John Bourgeois, Executive Project Manager to the State California Coastal Conservancy | John Bourgeois, john.bourgeois@scc.ca.gov, 408-314-8859
AECOM | Dillion Lennebacker, Dillon.Lennebacker@aecom.com, 1-510-874-3035

## NWRS EIS Summary Sheet
Proposed R8 NWRS EIS Schedules
Project
Task | South Bay Salt Ponds Phase 2 at Don Edwards NWR | Otay River Estuary Restoration Project, (San Diego Bay NWR) | South Bay Salt Ponds Phase 2 at Eden Landing | Farallon NWR Mouse Eradication | M&T/Llano Seco Fish Screen Facility Long-Term Protection Project
NOI for EIS Published in Federal Register | 2013-09-16 | 2011-11-14 | 2016-06-20 | 2011-04-13 | 2016-07-13
NOA for Draft EIS Published in Federal Register | 2015-07-22 | 2016-10-21 | 2018-04-06 | 2013-08-16 | 2019-01-25
Prepare Administrative draft Final EIS (including a draft of the ROD) |  |  | 2018-11-09 | 2018-09-06
Internal Review of Admin draft Final EIS Completed |  |  | 2019-01-11 | 2018-10-25
Final EIS package ready for Review Team (Final EIS; draft ROD; NOA) | n/a | n/a |  | 2018-12-06
Project Briefing to the Review Team | n/a | n/a | tbd | 2019-01-09
Review Team approval | n/a | n/a |  | 2019-01-16
Delegated SES (Regional Director) signs and approves FEIS and NOA | n/a | n/a | 2019-02-08 | 2019-01-17
File FEIS with EPA | 2016-05-27 | 2018-05-11 | 2019-02-15 | 2019-01-18 | 2019-10-11
NOA of Final EIS Published in Federal Register | 2016-06-03 | 2018-05-18 | 2019-02-22 | 2019-01-25 | 2019-10-18
Final EIS wait period ends- 30 days | 2016-07-03 | 2018-06-21 | 2019-03-25 | 2019-02-25 | 2019-11-18
EIS Project Team sends a one-page notice to the Review Team seeking objections to Final ROD approval. | tbd |  | 2019-04-12 | 2019-04-19
Regional Director signs ROD and NOA | 2018-09-27 | 2018-10-22 | 2019-04-26 | 2019-04-26 | 2019-11-29
NEPA Project Team Members
Senior Executive Service Member | Paul Souza | Paul Souza | Paul Souza | Paul Souza | Paul Souza
Project Manager | Anne Morkill | Andy Yuen | Anne Morkill | Anne Morkill | Curt McCasland
Subject Matter Expert / NEPA POC | Chris Barr | Brian Collins | Chris Barr | Gerry McChesney | Joe Silveira
Solicitor | Greg Lind | Greg Lind | Greg Lind | Veronica Rowan | Veronica Rowan
Contractor | AECOM | DUDEK | AECOM | Environmental Policy Solutions | ICF