## Farallon Mouse Eradication
FARALLON MOUSE ERADICATION
Task - we need to submit a schedule as an attachment, it can be an excel spreadsheet of Gant Chart | Date | Federal Register | Database Milestones | Comment (internal)
Issue NOI for EIS | 2011-04-13 | 76 FR 20706 | Required Target Completion Date
End of Public Scoping
Issue NOA for Draft EIS | 2013-08-16 | 78 FR 52524 | Required Target Completion Date
Issue NOA for Revised Draft EIS | 2013-10-25 | 78 FR 63977 | Required Target Completion Date
Prepare Administrative draft Final EIS (including a draft of the ROD) | 2018-11-12
Internal Review of Administrative draft Final EIS | 2018-12-24
Final EIS ready for public distribution | 2019-02-04 |  |  | 30 business days following end of Admin draft review.
Final EIS package ready for Review Team. Package includes: Final EIS and Appendices; a draft of the Record of Decision; a draft of the Notice of Availability. | 2019-02-04
Prepare briefing materials for Review Team: Powerpoint overview of preferred alternative, purpose and need, alternatives, salient environmental impacts and resource conflicts, the significant opportunities and hurdles that exist in completing the project. Briefing materials should address (as appropriate) the Secretary's priorities, resolution of resource conflicts, land-use restrictions, transportation or access limitations, elected official views, and inter-jurisdictional considerations. | 2019-02-15
Schedule an oral briefing for the Review Team. | 2019-02-04
Provide briefing materials to Review Team 1 week prior to briefing. | 2019-02-18
Project Briefing to the Review Team | 2019-02-25
Review Team provides comments to Project Team (day of the briefing and up to 5 business days following) | 2019-03-04 |  |  | Can approval be expected on the last day of the comment period? YES - we will assume approval on the 5th day and no revisions.
Review Team approval | 2019-03-04
Delegated SES (Regional Director) signs and approves FEIS and NOA | 2019-03-07
File FEIS with EPA | 2019-03-08 |  |  | Is filing the Friday before publication enough time? YES - if we file by Friday, EPA will publish the NOA on the following Friday.
Federal Register Notices Published - (Friday of the week following filing with EPA) | 2019-03-15 |  | Required Target Completion Date
Final EIS wait period - 30 days | 2019-04-14 |  |  | Need to check with Paul Souza, who requested 60 day wait period.
EIS Project Team sends a one-page notice to the Review Team seeking objections to Final ROD approval. Notice includes: 1) a brief discussion on any substantive issues that arose during the Final EIS notice period, 2) the Final ROD text, and 3) confirmation that it did not change from what was initially reviewed, or advise of any outstanding issues that need to be addressed, such as protest resolutions or Governor's Consistency Review objections. | 2019-04-19
Review Team has 3 days to request an oral briefing or object to the ROD. | 2019-04-24
Regional Director signs ROD and NOA | 2019-04-27 |  | Required Target Completion Date
NOA sent to Federal Register for publication
PERMITS | ACTION | BUREAU POC: NAME, EMAIL, PHONE | TARGET COMPLETION DATE
DOI Actions
Migratory Bird Treaty Act permit |  |  | Required Target Completion Date - target date needed for Issuance of decision for permit/approval
NON-DOI Actions
ESA Consultation - NOAA-NMFS |  |  | Required Target Completion Date - 2 dates needed: Consultation Initiation Date and Final BO Issued
Magnuson-Stevens Act |  |  | Required Target Completion Date - 2 dates needed: Issuance of decision for permit/approval andNotice to proceed | Do we need this? Is this the same as Essential Fish Habitat consultation?
Essential Fish Habitat consultation (NOAA-NMFS) |  |  |  | Do we need this? Is this the same as Essential Fish Habitat consultation?
Marine Mammal Protection Act Incidental Take Authorization |  |  | Required Target Completion Date - 2 dates needed: Issuance of decision for permit/approval and Notice to proceed
Consultation to Protect National Marine Sanctuaries |  |  | Required Target Completion Date - 2 dates needed: Issuance of decision for permit/approval and Notice to proceed
Coastal Consistency (this is not currently in the list of Non-DOI Actions and the Department would need to develop a list of agreed upon milestones so we do not need to identify a completion date for Coastal Consistency at this point)
BRIEF PROJECT DESCRIPTION
The U.S. Fish and Wildife Service proposes the eradication of the invasive house mouse on the Farallon Islands. The preferred alternative is the aerial application of the rodenticide Brodifacoum. The Farallon Islands comprise four groups of small islands located about 30 miles west of San Francisco. Together, they constitute the Farallon Natonal Wildlife Refuge, administered by the USFWS. The islands host the largest seabird breeding colony in the United States outside of Alaska and Hawaii. Twenty-five percent of Califonia's breeding seabirds-an estimated 300,000 to 350,000 individuals of 13 species-can be found there. About 50% of the world's population of the rare ashy storm-petrel (listed as a Species of Management Concern by the USFWS and a Bird Species of Special Concern by the California Department of Fish and Wildlife) breed on the islands. The invasive house mice pose a pervasive threat to these important seabird habitats. We anticipate that the complete removal of mice would allow many of the island's natural ecosytem processes to be restored.
KEY WORDS
Habitat Restoration; Invasive Species; Wildlife; Conservation and Preservation; Other - we can add other key words, let me know.
PROJECT MANAGER POC - Responsible for the overall project and must be able to take direct calls from DOI.
NEPA TEAM | NAME
NEPA Lead POC
Solicitor POC | Veronica Rowan
1st line SES | Paul Souza
WAIVER
The FEIS will be greater than 150 pages. No waiver was obtained because there is a published Draft EIS - per Memorandum issued on April 27, 2018; Additional Direction for Implementing Secretary's Order 3355. The Service will meet the schedule requirements.
CO-LEAD Agency | None
COOPERATING AGENCY | None
CONTRACTOR USED | Yes - will need Gabrielle's Information
Formulas:
Date = [Date, row below]-3