# Operational Plan to eradicate Pacific Rats (Rattus exulans) on Lehua Island, Hawaii

Authors: Patty Baiao, Mele Khalsa, David Will, Tommy Hall, Pete McClelland

Reviewers: Erin Hagen, Gregg Howald

Version History:

| VERSION | DATE | AUTHOR | REASON FOR CHANGE |
| --- | --- | --- | --- |
| 1 | 30Jun17 | Patty Baiao | Original |
| 2 | 20Aug17 | Patty Baiao | Update |

Citation: This report should be cited as: Baiao, Patty, et al. (2017) Operational Plan to eradication Pacific Rats (Rattus exulans) on Lehua Island, Hawaii.  Unpublished report to Department of Natural and Land Resources.  Island Conservation: Honolulu, Hawaii.

# EXECUTIVE SUMMARY

This plan lays out the steps necessary to prepare for, implement and demobilise after the implementation of the eradication of rats (Rattus exulans) from Lehua Island (112 ha).   This project is being undertaken by a partnership consisting of Island Conservation, Hawiaii Department of Land and Natural Resources (DLNR)/ Division of Forestry and Wildlife (DOFAW), The Robinson Family / Niihau Ranch, Hawaii Department of Agriculture (HDOA) the US Department of Agriculture (USDA) and US Fish and Wildlife Service (USFWS). Island Conservation will be serving as the implementing organization while DOFAW will provide planning and logistics support.  The USFWS is the Federal sponsor for the project while the USDA will undertake independent non-target monitoring.

The project will use Ditrac 50 bait (Bell Laboratories) which contains 50ppm of the first-generation anticoagulant rodenticide diphacinone in 3/8in compressed cereal bait pellets.  Staging of equipment and baiting operations will be based at Nanina on Niihau Island.  Three separate bait applications will occur approximately seven and ten days apart, respectively.  Application dates are subject to change based on weather conditions and bait availability, with the goal of ensuring bait is consistently available for at least 25 days.  Each application will target 20kg/ha of bait on the ground across all parts of the island to ensure ready access to bait for all rats, and not exceed an average (total bait applied divided by island area) of 30 kg/ha per application.

A total of 10,084kg (22,225 lb) of bait will be packed in 22.7 kg (50 lb) paper bags with16 bags stacked into each of approximately 27 cardboard pod. The pods will be transported in a 20ft container to Kauai then shipped to Niihau on the Niihau Ranch landing craft along with all required fuel, two bait buckets and assorted other equipment and supplies. This will require one trip with the landing craft.

Project monitoring before, during, and after bait applications will be undertaken by a team of at least four staff based on Lehua.  Independent environmental (water and soil) and non-target species monitoring will be led by USDA-NWRC.   Operational (bait availability) and efficacy (rat fate tracking) monitoring will be led by Island Conservation.  Approximately 40 bait availability plots will be established to measure bait availability over time and used to inform changes to the application schedule if necessary.

# Table of Contents

EXECUTIVE SUMMARY	2

Table of Contents	3

GLOSSARY	9

1.	INTRODUCTION	11

2.	GOAL, OBJECTIVES and OUTCOMES	11

Goal	11

Objectives and Outcomes	11

3.	PROJECT SITE & TARGET SPECIES	12

The Site	12

The Target Species	14

4.	PERMITS AND APPROVALS	15

5.	OPERATIONAL TEAM	15

Incident Command Structure	16

Command Team	18

Roles and Responsibilities	19

Incident Command Team	19

Niihau Operational Team	21

Lehua Monitoring Team	24

Kauai Support Team	26

6.	LOGISTICS	26

Bait Logistics	26

Bait packaging and shipment	27

Bait transport and storage	28

Bait quality monitoring	28

Staging on Niihau	28

Personnel Staging	28

Lehua Monitoring Team	28

Niihau Operational Team	29

Demobilization	29

7.	BAIT APPLICATION STRATEGY	29

Timing	29

Baiting strategy	30

Timing between drops	31

Baiting rate	31

Bucket configurations	31

Baiting Plan	33

Hand baiting	34

Bait Estimates	36

Deviations from proposed baiting strategy	37

8.	HELICOPTER OPERATIONS	37

Contracts and operators	37

Niihau Helicopter	37

Baiting Helicopter and Pilot	37

Operational Locations	37

Lehua Island	37

Niihau Operational Site	38

Baiting Helicopter Storage	40

Flight Time Estimates	40

Helicopter fuel	41

Sourcing fuel	41

Fuel storage and spill response	41

Refueling the helicopter	41

Air Operations Communications	41

Flight Tracking and Flight Following	42

Staging Site Logistics	42

Baiting Helicopter	42

Bait Loading Site setup	42

Bucket Calibration	42

Calibration Site	43

Supplies	43

Site Preparation	43

Site Cleanup	44

9.	BAITING OPERATIONS	44

Weather Forecasting	44

Decision to activate operational team	44

Operational Site Preparation	44

Authorization to Commence Baiting Operations	45

Weather Requirements	46

Bait-bucket Loading Procedures	46

Clean up of loading site	48

Bait Application Monitoring	48

Monitoring Sow Rate	48

Deviations from Target Sow Rate	48

GPS	48

Wind monitoring	49

Off -Island Support	49

10.	EFFICACY MONITORING	49

Logistics	50

Bait density and availability	50

Study plots	50

Bait Density Analysis	51

Bait Availability Analysis	51

Reporting and Operational Response	51

Impacts on target species	52

Pre-operation	52

During operation	52

Post-operation	53

11.	NON-TARGET SPECIES	53

Seabird Mitigation	53

Carcass Search	53

Reporting	53

12.	ENVIRONMENTAL EFFECTS	54

Bait Spill Response	54

Fuel Spill Response	54

13.	OPERATIONAL DATA	54

14.	SAFETY	55

Hazards and Hazard Management	55

Safety roles and responsibilities	59

Safety briefings and trainings	60

Medical supplies and services	60

Reporting and Workers’ Compensation (For IC staff only).	61

Emergency Incidents	61

Operational responses to an Emergency Incident	61

Evaluating the appropriate Emergency Incident response	62

Communications	63

15.	OPERATIONAL BIOSECURITY	63

Purpose	63

Operational Biosecurity Measures	63

Pre-operation – all activities prior to first bait application	63

During operation – all activities between the first and final bait applications	66

Post-operation	67

Bait Shipment	68

People and Personal Gear	68

Transportation	69

Waste Management	69

16.	OPERATIONAL COMMUNICATIONS	70

Lines of communication	70

Modes of communication	70

Satellite phone	70

Radio	71

Cell phone	72

Public Notifications	72

17.	REFERENCES	72

Appendices	75

Appendix 1.  Ditrac D-50 MATERIAL SAFETY DATA SHEET	75

Appendix 2  DITRAC D-50 Label	81

Appendix 3. Helicopter Safety Plan	83

Lehua Helicopter Operations – Supporting Documents	83

Hazard Identification and Mitigation	83

General Hazards Identified and Controls:	84

Bird strikes	85

Flight Following	86

Flight Tracking	87

Emergency Response Actions	89

Radio Communications	89

Appendix 4. Aerial Operator’s Safety Plan	90

Appendix 5. Emergency Incident Action Plan	91

Appendix 6: Lehua Personnel Contact Information	95

Appendix 7: Bait Spill Protocol	99

Spill Response Procedures	99

General Response Procedures	99

Terrestrial spill on Kauai, Niihau, or Lehua	99

Spill in the marine environment	100

Adverse Incident Response Procedures	101

Appendix 8: Deviation from operational plan form, Lehua island rat eradication.	103

Appendix 9: Aerial Bait Tracking Worksheet	106

Appendix 10: Aerial Application Wind Speed Worksheet	107

# GLOSSARY

Average application rate – the average rate of bait applied across the island per application in kg/ha, expressed as the total bait applied divided by total island area.   This rate should not exceed the maximum amount described in the bait label of 30 kg/ha.

Bait application – a complete treatment of the island at the target application rate.

Bait bucket - a purpose built hopper with attached spinner which is designed to apply bait in a swath out each side at a prescribed rate. The bucket is slung under the helicopter when applying bait

Bait loading site – where the bait is loaded into the helicopter bucket- includes the bait loading platform.

Calibration- when bait is spread from the bucket in a controlled situation to measure the effective swath width and confirm bucket sow rate.

Decontamination area- an identified area where personnel change into and out off PPE when going into and leaving the hot zone. This is to reduce the risk of transferring the toxicant to clean areas.

Directional swath – when an internal deflector is put on the bucket to direct bait only out one side.

Effective swath width –horizontal distance from the bucket at which bait is estimated to be spread.

Fueling site- where all helicopter refuelling will take place.

Full swath – when the bucket is spreading out each side.

Hot zone- the bait loading area where all personnel are required to wear full PPE when the helicopter is present. A lower standard of PPE (as required for hand baiting) will be worn when the helicopter is not present.

Incident Command Center (ICC)- the site where the command team meet and includes the GIS specialist work station.

Narrow Swath – when the spinner which spreads the bait is removed and a cone put in its place so that bait drops almost straight down.

PPE Area – the area of the Operational Area in which personnel are required to the listed PPE. This includes the hot zone where full PPE is required and the refueling area where a lower standard is required.

Pod – a solid walled box approx. 3ft x 3ft x 1 ½ ft made of carboard to transport the bags of bait.

Flight line- the line produced on the GPS for the helicopter to fly along to give the required bait coverage. These must be straight parallel lines across the body of the island to minimize gaps between neighbouring swaths.

Flight path – the path that the helicopter flies as recorded by the GPS. This covers both when bait is being spread and when the helicopter is ferrying between the loading site and the target area along with all turns during the bait spreading ie at the ends of runs.

Fly by eye- where the required flight path is not straight so cannot be developed on the and directed by the GPS.

Niihau Operational Site - the site at Nanina at the north end of Niihau Island at which all bait loading, helicopter refuelling and associated activities will take place.

Runs – the area covered during one period when the bucket is spreading bait. These may be straight along flight lines or winding around the coast.

Secondary landing pad- an identified location away from the main loading / refuelling area that the helicopter can land at if required eg if some activity at the primary site precludes landing there.

Sow rate -  the rate of bait (in kg/ha) that bait is spread from the bucket.

Target application rate– the density of bait targeted on the ground in kg/ha for reach application.

Tracmap- the GPS equipment designed to guide and record the path of the helicopter when applying bait.

# INTRODUCTION

This document is to provide the required direction for the project team to implement a successful and safe eradication that is compliant with all state and federal regulations as well as the relevant permits and approvals. The plan is based on knowledge gained from the unsuccessful 2009 eradication attempt, the review of that attempt and targeted on site trials carried out in 2015, along with knowledge gained from numerous successful and unsuccessful eradication attempts undertaken around the world.

# GOAL, OBJECTIVES and OUTCOMES

## Goal

The project goal is to remove all rodents from Lehua with no staff injuries and minimal non-target impacts in order to allow the natural systems and processes on the island to recover.

## Objectives and Outcomes

The objectives that this project will achieve and the outcomes that will be a result of achieving these objectives are:

| Objectives | Outcomes |
| --- | --- |
| - Removal of all rodents from Lehua Island. | Increased flora recruitment and ability to revegetate the island including plantings |
|  | Increased survival of nesting seabirds through reduced predation of eggs and chicks and increased vegetation cover for shelter |
|  | Reestablishment of extant seabirds including Newels shearwater, Hawaiian petrel and Band-rumped storm petrel. |
|  | Restoration of natural ecological processes on Lehua including nutrient cycling. |
| - The safe and efficient implementation of the operational plan | No injuries or near misses to project personnel |
|  | Compliance with all permit and consent conditions |
|  | Increased support from all current and potential project partners |

# PROJECT SITE & TARGET SPECIES

## The Site

Lehua Island (112 ha) is located	1.2 km	off the	northern shore	of Niihau (a privately owned 18,650 ha island) and roughly 31 km west of Mana Point on the island of Kauai, falling within the county of Kauai (Figure 1) (Wood et al. 2004).

Figure 1. A map of the main Hawaiian Islands, showing the islands of Niihau and Lehua	inset.

Lehua is a crescent‐shaped, extinct volcanic crater open to the sea on its north side (Figure 1). The rocky substrate of the island is volcanic tuff which has been shaped over the years by volcanic activity, wave action, landslides, and weathering, resulting in a terrain of steep slopes, wave cut benches, radial	drainages, and troughs and gullies which run parallel to the shoreline (Palmer 1937, Wood et al. 2004). The island rises 699 feet (231 meters) above sea level, the sides of which have an average slope of 30° (Palmer 1937, State of HawaiI 2011). The planar area (i.e. the “footprint”) of the island is approximately112 hectares, however, the prevalence of steep slopes on the island means that the actual surface area of the island may in fact be as much as 135 ha (Palmer 1937). The climate on Lehua is generally very arid: subject to intense sun, receiving limited rainfall and buffeted by frequent winds (Wood et al. 2004, Eijzenga 2011). The steepest slopes of the island are sparsely vegetated while the remainder of the island supports a moderate to dense assembly of grasses, forbs, and shrubs. The island can be divided into three zones: the outer southern crescent, the inner crescent, and the south‐western slope. Dense vegetation can be found in the gulch bottoms along the outer crescent, but does not comprise a large portion of the island. The inner crescent sustains the densest vegetation in the upper crescent shelves where soil is less eroded. Vegetation most commonly consists of a variety of grasses, vines, and shrubs. The south‐western slope is sparsely covered in grasses, vines, flowering plants, and sedge (Wood et al. 2004).

Areas which appear barren during the dry season (April‐October) become lush with vegetation with the arrival of the first rains and continue to remain green through the wet season (November‐March).	 During	the dry	season, the island is subject to nearly constant trade winds and the highest average wind speed, while the wet season brings higher variability in wind patterns and lower wind speed, as well as storms originating from the south and southwest (USFWS and DLNR 2008). The seas around Lehua are generally calm in the summer months, but winter sea conditions rarely preclude access to the island by boat (USFWS and DLNR 2005).

Figure 2. A topographical map of Lehua Island (left) and a digital elevation model (right) of	Lehua

Lehua is federal property administered by the U.S. Coast Guard (USCG) while the natural resources on the island are managed by the Department of Fish and Wildlife (DOFAW) within the State of Hawaii’s Division of Forestry and Wildlife (DLNR). The USCG maintains a navigational marker (light) on the island but the island is uninhabited (Offshore Islet Restoration Committee 2006, Clark 2010). Prior to ownership by the US government and administration by the USCG, Lehua belonged to the territorial government of Hawaii; the island was annexed by the US government in 1928 by President Calvin Coolidge “for lighthouse purposes.” (Wikisource 2012). Lehua has been designated a State Seabird Sanctuary (§13‐126‐3) and has been zoned as a Conservation District; overnight camping, hunting, and disturbing wildlife are prohibited (DLNR 2010). The waters surrounding Lehua and the intertidal area (below the mean high water mark) are State property and are open to vessels for the purposes of fishing, diving, and tourism.

The island is closed to the public and is only occasionally accessed by resource managers (Hawaii Department of Land and Natural Resources), seabird researchers (Kauai Endangered Seabird Recovery Project—KESRP, Pacific Rim Conservation—PRC), members of the Coast Guard, and staff of the National Tropical Botanic Gardens (Offshore Islet Restoration Committee 2006). Lehua is most readily reached by boat, departing from Kauai; the round‐trip journey takes the better part of a day to complete and is subject to appropriate sea conditions (USFWS and DLNR 2005). When arriving by boat, the island can be accessed via a landing site at the center of the southern outer crescent (Wood et al. 2004). The island can also be accessed by helicopter, the preferred route for USCG personnel accessing the solar‐powered navigation aid (light) located at the summit of the island (Clark 2010).

As part of the initial 2005 Environmental Assessment, members of the public on Kauai and Niihau were interviewed about their use of Lehua and its natural resources. All respondents reported that people visit the island to fish and to collect opihi (marine limpets) and limu (seaweed or algae). As for tourism, a few Kauai based tourist operations bring visitors out to the island to enjoy the landscapes and marine life (scuba diving, and snorkel tours), but passengers are restricted to the surrounding water and not allowed on the island (USFWS and DLNR 2005).

## The Target Species

The target species is the Pacific/ Polynesian rat Rattus exulans which is currently negatively impacting the flora and fauna of Lehua through predation, competition and inhibiting natural processes including the recovery of the island.

Rattus exulans is thought to have originated in Southeast Asia and in the last 1,000‐2,000 years, has spread to much of Melanesia, Micronesia, and Polynesia (Aplin et al. 2003). R. exulans was the first Rattus species to reach the Hawaiian Islands, brought by Polynesians who first settled the island chain between 700 and 800 AD (Athens et al. 2002a, Athens 2009). It is a primarily nocturnal, small‐bodied rat (adult weight: 40‐80 grams) and the smallest of the pest Rattus species (Williams 1973, Lindsey et al. 1999, Aplin et al. 2003). R. exulans is both terrestrial and arboreal and has adapted to a wide‐range of habitat types throughout its distribution: human habitations, rainforest, grassland and rice, sugarcane, and coconut plantations, generally preferring areas with good ground‐cover and dry or well‐drained soil (Williams 1973, Aplin et al. 2003). The diet of R. exulans consists predominantly of vegetative matter (leaves, fruits, seeds, roots) and arthropods, but extends to reptiles and seabirds and their young (Bettesworth 1972, Sugihara 1997, Atkinson and Towns 2001, Shiels et al. 2013).

Female Pacific rats in New Zealand are estimated to reach sexual maturity within 8‐12 months of birth and research in Hawaii has shown that the average female can produce as many as 17 young every year (Tamarin and Malecha 1972, Moller and Craig 1987). In New Zealand, the breeding seasonality of R. exulans has been closely tied to food availability, with reproduction ceasing during winter months of low resource availability (Roberts and Craig 1990). Seasonal changes in population reflect breeding activity, with the highest population densities occurring immediately after breeding and prior to the months of food scarcity, at which point populations drop to the lowest densities (Craig and Bunn 1989).	Studies	in the lowlands and humid highlands of the island of Hawaii, however, suggest that R. exulans breeds year‐round in the lush habitats on that island (Lindsey et al. 1999, Scheffler et al. 2012). Rodent density estimates during the breeding season on Kure Atoll showed an average of 111 animals/ha, though this estimate is high when compared to other tropical locations where density estimates range from 7‐35 animals per hectare, including a study on Hawaii which saw a maximum density of 35 animals per hectare (Tomich 1970, Wirtz 1972, Aplin et al. 2003).

There is conflicting information about the annual or inter‐annual trend in the density of the R. exulans population on Lehua. Observations of rat density made with tracking boards from 2001 2004 indicate that rat numbers increase during the wet winter and decrease during the dry summer (USFWS and DLNR 2005). However, density estimates based on capture rates with standardized traplines conducted in July and September of 2007 and in March of 2008 found that rat numbers dropped from a boreal summer high to a winter low; in the summer months juvenile rats accounted for 50% of the sample population (USFWS and DLNR 2008). Rats on Lehua Island tend to be found in greater numbers in areas of high vegetation (USFWS and DLNR 2008) along the lower, southern slope. The population on Lehua Island is known feed primarily on invertebrates and vegetation, supplementing their diets with the eggs and chicks of nesting seabirds (USFWS and DLNR 2005).

# PERMITS AND APPROVALS

The Lehua rat eradication is a concerted effort lead by the state of Hawaii in partnership with USFWS, USDA, USCG, NTBG, Niihau Ranch, and IC. The island is owned by the USCG and it is managed by DLNR-DOFAW as a Seabirds Sanctuary. Because of this duel tenure, the project must comply with both state and federal regulatory processes, Hawaii Environmental Policy Act (HEPA) and National Environmental Policy Act (NEPA), respectively. USFWS is the federal sponsor for the project.

Additional to HEPA and NEPA, the following permits are required:

- Federal Finding of No Significant Impact

- Hawaii Finding of No Significant Impact

- DLNR Historic preservation

- US Coast Guard Lehua Island Use License

- Marine Mammal Protection Act Incidental Harassment Authorization (IHA)

- Coastal Zone Management Act Consistency (CZMA) Determination

- Conservation of Aquatic Life, Wildlife, and land plants HRS 195D and HAR 13-124

- National Pollutant Discharge Elimination System (NDPES)

- USFWS Migratory Bird Treaty Act Special Purpose Permit (MBTA)

- USFWS Section 7 Consultation

- NOAA Section 7 Consultation

- Federal Insecticide, Fungicide, and Rodenticide (FIFRA) Section 3 registration of bait product

- Hawaii Department of Agriculture (HDOA) Aerial Application Permit

Finally, a Certified Pesticide Applicator (CPA) category 2 is required to oversee the ground operations and a CPA category 4 is required for the helicopter pilot.

# OPERATIONAL TEAM

Incident Command System (ICS) – Roles and Responsibilities

The Lehua rat eradication operation will be managed under the Incident Command System (ICS) organizational structure.  For the purposes of this project, each aerial baiting operations will be considered an “Incident” and any emergency that might occur during the operation will be considered an “Emergency Incident”.

## Incident Command Structure

For Incident operations, every individual will be assigned one designated supervisor to whom he/she reports during the operation. The clear chain of command is illustrated below:

Figure 3. Lehua rat eradication Incident Command System (ICS) organizational structure.

The responsibilities listed for each position below are the major responsibilities; other responsibilities may be assigned to any of the positions by the Incident Commander as needed.

Table 1. Summary or roles and responsibilities for Incident operations.

| Group Name | Sub-group | Position | Role | Physical Location | Assigned Personnel |
| --- | --- | --- | --- | --- | --- |
| Incident Command Team |  | Incident Commander | Manages whole operation | Niihau | Patty Baiao |
|  |  | Operation Advisor | Ensures operation’s legal compliance, provides advice to Incident Commander | Niihau | Gregg Howald |
|  |  | Eradication Advisor | Ensures technical efficacy, provides advice to Baiting Operation Chief | Niihau | Pete McClelland |
|  |  | Assist. Incident Commander | Ensures operations are politically and socially acceptable | Niihau | Sheri Mann |
|  |  | Baiting Operation Chief | Manages bait application efficacy, including bait loading | Niihau | Tommy Hall |
|  |  | Independent Observer | Documents operations deviations, decision-making process, and procedures | Niihau | Shane Siers |
| Niihau Operational Team | Aerial Operation | GIS specialist | Records, summarizes, and reports the GPS-based data | Niihau | David Will |
|  |  | Baiting Pilot | Aerially broadcasts bait, establishes helicopter safety plan | Niihau | Rob Scherzinger |
|  |  | Helicopter Mechanic | Maintain helicopter, assists with refuelling | Niihau | Mike Borge |
|  | Bait Loading | Bait Loading Lead | Directs bait loading operations, supervises bait loading team | Niihau | Wes Jolley |
|  |  | Bait Loaders (5) | Assists bait leader | Niihau | Niihau community members Chelsea Derek Ohi Darian TBD |
|  | Logistics/ Biosecurity | Ground CPA | Enforces strict compliance with EPA section 3 bait label | Niihau | Mike Walker |
|  |  | Safety Officer | Identifies, assesses, and/or anticipates hazardous and unsafe situations. | Niihau | Jason Verecelli |
|  |  | Niihau Logistics Lead | Manages Niihau camp and operation logistics | Niihau | Wes Jolley |
|  |  | Biosecurity Officer | Implement biosecurity protocol | Niihau | Keith Robinson |
|  |  | External Communication Officer | Manages coordination for public information to partners, media, and public. | Niihau | Gregg Howald |
| Lehua Monitoring Team | Efficacy Monitoring | Bait Uptake Monitoring Officer | Manages efficacy monitoring operations, supervises monitoring crew, ensures field personnel safety, collects, analyses and reports data | Lehua | Araceli Samaniego |
|  |  | Bait Uptake Monitoring crew (1) | Assists Efficacy Monitoring Officer, implements monitoring | Lehua | Patrick Chee/Caleb Morrison |
|  | Environmental Monitoring | Env. Monitoring Officer | Manages Env. monitoring operations, supervises monitoring crew, ensures field personnel safety, collects, analyses and reports data | Lehua | Dean Foster |
|  |  | Env. Monitoring crew (1) | Assists Env. Monitoring Officer, implements monitoring | Lehua | Israel Leinbach |
|  | Logistics | Lehua Team Leader/Safety Officer | Manages Lehua camp and monitoring teams logistics, ensures field personnel safety, implement biosecurity protocol, and is POC with Assistant Incident Commander | Lehua | Mele Khalsa |
| Kauai Support Team |  | Logistics/ Biosecurity Support Kauai | Assists Logistic/Biosecurity Officer and Lehua Team Leader, provides equipment and supplies to Niihau and Lehua teams, implements biosecurity protocols | Kauai | Latham Keaweamahi Lindsay Ibara |
|  |  | Niihau Ranch Support Kauai | Assists Logistic/Biosecurity Officer regarding Niihau Ranch operations | Kauai | Mary Sue Matter |

## Command Team

The Incident Command Team is comprised of:

- Incident Commander

- Operational Advisor

- Baiting Operation Chief

- Eradication Advisor

- Assistant Incident Commander

Purpose

- To direct the baiting operations.

- To ensure that all legal requirements are observed during operations.

- To ensure that operations are done in socially and politically acceptable ways.

- To ensure operations are implemented per the Operational Plan.

- To approve any deviations from the Operational Plan

Activities

- Informs Incident Commander of issues that need to be addressed.

- Evaluates and approves deviations from the Operational Plan.

- Implements pre- and post-operations meetings.

## Roles and Responsibilities

### Incident Command Team

#### Incident Commander

The Incident Commander is ultimately responsible for the entire operation. For the Lehua eradication operation, Island Conservation personnel will fill the role of Incident Commander. The Incident Commander will designate a replacement to assume this role if the assigned Incident Commander is unable to do so.

Major Responsibilities:

- Has clear authority and must understand all legal requirements.

- Establishes priorities.

- Establishes an Incident Command Center.

- Monitors the baiting operation and effectiveness of the operation.

- Manages planning meetings.

- Implements the Emergency Incident Action Plan (Appendix 5).

- Coordinates activities of operational staff.

- Activates deviation protocols for Command Team approval.

- Approves requests for additional resources and for release of resources.

- Authorizes release of information to the media, partners, and the public.

- Ensures incident after-action reports are completed.

#### Assistant Incident Commander

The Assistant Incident Commander represents the Lehua Project’s lead agency DLNR/DOFAW in the Command Team and is responsible for ensuring implementation is conducted in politically and socially acceptable ways. The Assistant Incident Commander oversees the Niihau Logistics Lead, the Safety Officer and the Lehua Monitoring team. She/he reports to the Incident Commander.

Major Responsibilities:

- Responsible for go/no go decisions regarding social and political environments.

- Observes the operations.

- Responsible for documenting any approved deviations to the Operational Plan following deviation protocols and where relevant any decisions to not deviate from the plan.

- Participates in the Command Team and decision-making process.

- Serves as the Point of Contact for the Lehua Monitoring Team during applications.

- Keeps windspeed logs.

#### Operation Advisor

The Operation Advisor provides information and technical advice to the Incident Commander to ensure that the operations follow all pertinent legal requirements. The Operation Advisor is available as a backup to the Incident Commander, and the Eradication Advisor if needed.

Major Responsibilities:

- Provides advice to the Incident Commander on the legal consequences of any deviations to the operational plan.

- Monitors bait application and all GIS information and alerts the Incident Commander to any risk to legal compliance.

- Acts as a back up to the Incident Commander if he/she becomes unavailable.

- Acts as a back up to the Eradication Advisor if he/she becomes unavailable.

#### Eradication Advisor

The Eradication Advisor provides information and technical advice to the Baiting Operation Chief to ensure that the efficacy of the baiting operation is maximized.

Major Responsibilities:

- Provides advice to the Baiting Operation Chief on the technical consequence of any deviations to the operational plan.

- Monitors bait application and all GIS information and alerts the Baiting Operation Chief to any risk to operational efficacy as well as any opportunity to increase efficacy.

- Acts as back up to the Baiting Operation Chief if the he/she becomes unavailable.

- Acts as back up to the Bait Loading Leader if he/she becomes unavailable.

#### Baiting Operation Chief

The Baiting Operation Chief is responsible for managing all tactical operations. The Baiting Operations Chief oversees the Bait Loading Lead, the GIS specialist, and the baiting pilot. He/she is responsible for managing aerial baiting operation efficacy during the three bait applications on Lehua. This includes bait loading, bait application, review of baiting data, and making recommendations for ensuring effective bait coverage. The Baiting Operations Chief reports to the Incident Commander.

Major Responsibilities

- Ensures that the aerial baiting operations are conducted per the Operational Plan

- Coordinates pre-operation briefings to operational personnel

- Ensures all operational staff are properly trained and sites are safe to conduct operations.

- Manages Bait Loading Lead, GIS specialist, and baiting pilot.

- Directs information from the GIS specialist, Eradication Advisor and Bait Loading Officer to the Incident Commander.

- Requests additional resources to support tactical operations as required.

- Makes informed recommendations to Incedent Commad Team to ensure effective aerial baiting.

- Oversees loading site operations and safety.

- Is the Point of Contact (POC) for communication with the Baiting Pilot.

- Makes minor decisions on real-time baiting issues that do not require Command Team deliberation.

- Completes the baiting statistics from the pilot for each bucket load in the bait application tracking sheet.

- Receives GIS memory stick from Helicopter Pilot and transfers to GIS Specialist.

- Ensures that the Bait Buckets are in working order.

- Ensures that sufficient spares and relevant tools are available.

- Alerts Incident Commander to bait spills and deviations from aerial application plan.

#### Independent Observer

Responsible for documenting general procedures, decision making process, and deviation protocol implementation.

Major responsibilities

- Documents main procedures including authorization to commence baiting operations, conclusion of safety briefs, among others.

- Record time of operational procedures.

- Document decision making process and implementation of deviation protocols.

- Signs as a witness all deviation protocols.

- Documents permit required reporting.

### Niihau Operational Team

#### GIS specialist

Responsible for recording, mapping, summarizing, and reporting the GIS-based data generated during aerial baiting operations, and is specifically responsible for the data generated by the air operations.  The GIS specialist reports to the Baiting Operation Chief.

Major Responsibilities:

- Manages several weather forecasting tools and provides regular and on-demand weather forecast.

- Receives the USB memory stick with GIS bait application data generated by the helicopter, from the Baiting Operations Chief and downloads data.

- Produces bait application maps, identifies baiting gaps and/or areas with low density

- Provides the Helicopter Pilot with maps of baiting blocks.

- Interprets bait application maps to the Baiting Operations Chief to identify gaps and /or areas of low density.

- Calculates the sow rate achieved for each load and recommends changes to the Baiting Operations Chief to maintain the target sow rate.

- Ensures Tracmap unit is in good working condition.

#### Baiting Pilot

The Baiting Pilot is responsible for the aerial application of bait in accordance with the baiting strategy. The Baiting Pilot is a State of Hawaii Certified Pesticide Applicator (Category 4), and ensures that the pesticide application follows Federal (EPA, FIFRA) and HDOA regulations. Additionally, the baiting pilot establishes the helicopter safety plan. While piloting the helicopter, the Baiting Pilot reports to the Baiting Operations Chief.

Major Responsibilities

- Ensures helicopter is on site on Niihau before first light on application days.

- Aerially broadcasts bait onto the treatment area according to the baiting strategy.

- Reports baiting statistics to the Baiting Operations Chief for each bucket load.

- Works with the Helicopter Mechanic to ensure that the helicopter is properly maintained, and that problems are immediately and adequately resolved.

- Provides helicopter safety plan to Baiting Operation Chief and provides helicopter safety briefings to staff working in Loading Zone.

#### Helicopter Mechanic

The Helicopter Mechanic is responsible for the maintenance of the helicopter and undertaking refueling during air operations. The Helicopter Mechanic works with the pilot to identify and address helicopter maintenance needs. During air operations, the Helicopter Mechanic reports to the Baiting Operations Chief.

Major Responsibilities

- Maintains a working helicopter.

- Works with the Helicopter Pilot to ensure that the helicopter is properly maintained, and that any problems with the helicopter are immediately and appropriately resolved.

#### Bait Loading Lead

The Bait Loading Lead is responsible for managing and coordinating bait bucket loading for the aerial baiting operations including safety of bait loading operations. The Bait Loading Lead leads the Bait Loading Team. The Bait Loading Leader reports to the Baiting Operations Chief.

Major Responsibilities

- Reviews the bait operations equipment list and ensures all equipment needed is staged at both the staging and baiting site.

- Works with the Baiting Operations Chief and the Baiting Pilot to ensure the loading site is prepared for operations, including enough bait for the day is present at the baiting site and required safety equipment is in place, including PPE being worn where relevant.

- Defines the Loading Zone.

- Responsible for managing the loading of the spreader bucket during aerial operations and ensuring that all operations are undertaken in a safe manner.

- Responsible for coordinating the clean-up of any spilled bait at the loading site

- Implements appropriate training of Bait Loading Team.

- Instructs the Bait Loading Team to ensure correct staging of bait pods, hand loading procedure, loading the bait bucket with the prescribed amount of bait, and demobilizing and storing empty bait bags, bait pods and lids.

- Prior to reloading the bucket, confirms with the Baiting Operations Chief the amount of bait remaining in the spreader bucket before reloading.

- Monitors welfare of bait loading team- ensuring adequate rests, refreshments etc and replacement if necessary.

- Ensures that bait bucket motor is refuelled during shutdowns; this may include directing others to complete this task.

- Prior to each application, collects three bait samples from different pods and stores it for later analysis if necessary.

#### Bait Loaders

The Bait Loaders work with the Bait Loading Lead to prepare the bait loading site before each application and to complete spreader bucket loading for aerial baiting operations. The Bait Loaders report to the Bait Loading Lead.

Major Responsibilities

- Assists the Bait Loading Lead to ensure all baiting supplies and equipment are staged.

- Assists the Bait Loading Lead to set up the loading site including setting up loading platform and removing any debris that may pose a risk to operations.

- Transfer the bait from the storage site to the loading site on Niihau Ranch truck.

- Loads bait into the spreader bucket as directed by the Bait Loading Lead.

- Identifies any potential risks or health and safety issues during loading and notifies the Bait Loading Lead promptly.

- Ensures temporary safe storage of empty bags in the allocated holding container/ empty bait pods.

- Manages cleaning and storage of empty bait pods after operations are completed.

- Implements the cleanup of bait spilled at the baiting site.

- Works with the Baiting Operations Chief and Bait Loading Lead to ensure safe bait loading practices.

#### Ground CPA

The Ground CPA Is responsible to strict compliance with EPA section 3 label for bait product.

Major responsibilities

- Oversees transport of bait container to Niihau staging site.

- Reviews the appropriate use of PPE by all ground personnel on Niihau.

- Ensures proper documentation of relevant information.

- Reviews correct use of the bait product as per EPA section 3 label.

- Coordinates with Incident Commander any adjustments needed to bait loading team needed to maintain compliance.

- Communicates any violations of EPA section 3 label to Incident Commander.

- Is the point of contact for HDOA/EPA representative on Niihau.

#### Safety Officer

The Safety Officer’s role is to identify, assess, and/or anticipate hazardous and unsafe situations.  The Safety Officers reports to the Assistant Incident Commander.

There are separate Safety Officers for Lehua and Niihau operations.

Major Responsibilities

- Identifies hazardous situations associated with the operation, and resolve safety issues.

- Is fluent in the project’s safety plan procedures.

- Reviews the Safety Plan and the Emergency Incident Action Plan (Section 13, Appendix 5).

- Exercise emergency authority to stop and prevent unsafe acts via communications via Assistant Incident Commander to Incident Command Team.

- Confirm safety messages and briefings are made as needed.

- Ensure reporting of any incidents or near misses promptly to Incident Command Team so an appropriate response can be undertaken and corrective actions can be taken.

#### Niihau Logistics Lead

The Niihau Logistics Lead manages all logistics at the Niihau Operational Area. He/she is responsible for, managing the camp, coordinating with Niihau Ranch staff, and coordinating with the Logistics Support Kauai. The Niihau Logistics Lead reports to the Assistant Incident Commander.

Major Responsibilities

- Coordinates efforts to stage equipment and supplies on Niihau.

- Manages the operation site and camp site.

- Ensures all teams on Niihau have the supplies and equipment they need to perform their duties.

- Coordinates with Niihau Ranch staff on Niihau.

- Ensures staff are briefed on biosecurity protocols prior to initiating the operation.

- Ensures that camp is clean and food supplies are properly stored prior to commencing the aerial baiting operations.

#### Biosecurity Officer

The Biosecurity Officer implements biosecurity protocols on Niihau.  If he/she identifies a biosecurity risk that could compromise operational efficacy they must notify the Niihau Logistics Lead immediately.

#### External Communication Officer

The External Communication Officer will receive reports from the Incident Commander, and will be responsible for representing the ICS/Operation in public communications with the media, partners, and the public. He/she will determine with the Incident Commander, and key public information advisors, any limits or timing on information to be released.  The External Communication Officer reports to the Incident Commander.

Major Responsibilities

- Work with the off-site communications advisors (minimally DLNR/IC public information officers) to communicate and manage news releases to the media and general public, including briefings, tours, and interviews.

- Manages communications with cooperating agencies and donors.

- Monitor and forward media information that might be useful to the operation.

### Lehua Monitoring Team

#### Lehua Team Leader

The Lehua Team Leader manages all logistics for the Lehua based operations. He/she is responsible for coordinating staging activities, managing the camp, coordinating with the Logistics Support Kauai, and implement Emergency Incident protocols. He/she also implements biosecurity protocols on Lehua.  If he/she identifies a biosecurity risk that could compromise operational efficacy they must notify the Assistant Incident Commander immediately.  He/she is the POC for the Lehua based team. The Lehua Team Leader reports to the Assistant Incident Commander during operations.

Major Responsibilities

- Coordinates efforts to stage equipment and supplies on Lehua.

- Manages the camp site.

- Ensures all teams on Lehua have the supplies and equipment they need to perform their duties.

- Ensures a safe work environment for all personnel on Lehua.

- Briefs staff on biosecurity protocols prior to initiating the operation and ensures all Lehua Team members adhere to LIPP.

- Ensures that camp is clean and food supplies are properly stored prior to commencing the aerial baiting operations.

- Provides daily reports of bait density data.

- Provides hourly wind readings on aerial application days to Assistant Incident Commander.

- Is the CPA assigned to the Lehua hand-broadcast baiting operation. Ensures strict compliance with EPA section 3 bait label. Records all required hand-broadcast operation data and maintain records.

- Leads hand baiting on Lehua according to operational plan.

- Informs Assistant Incident Commander of any deviations from operational plan or bait spills.

- Leads on island seabird mitigation including identification of mapped accessible albatross and red-tailed tropicbird nests, removal of bait from active albatross and red-tailed tropicbird nests, briefing of Lehua team for avoidance of shearwater burrow collapse and excavating procedure in case of collapse.

- Ensures ground team members maintain 100 feet buffer from seals and avoid contact with federally listed plants.

- Leads the marking of archaeological sites and ensures that Lehua team members are informed of prohibitions to disturb sites.

- Oversees installations of signs alerting visitors of operation and rodenticide presence.

- Collects any federally endangered, listed species, or species of special concern with clear signs of toxicosis and delivers it to the humane society in Kauai.

- Provides therapeutic treatment on island or euthanizes any non-native MBTA-protected birds with clear signs of toxicosis.

#### Bait Uptake Monitoring Officer

The Efficacy Monitoring Officer is responsible for the implementation of the efficacy monitoring plan.

Major Responsibilities

- Ensures efficacy and non-target monitoring activities are implemented according to the Monitoring Plan.

- Instructs and supervises the Efficacy Monitoring Crew.

- Ensures a safe working environment for the Efficacy Monitoring Crew.

- Coordinates with the Lehua Team Leader to communicate data analyses and recommendations to Assistant Incident Commander.

- Reports bait density data to the Lehua Team Leader after bait application is complete.

- Reports in real-time any problems seen in the field relevant to the bait application.

#### Bait Uptake Monitoring Crew

The Efficacy Monitoring Crew assists the Efficacy Monitoring Officer for implementation of the Efficacy Monitoring Plan. Monitoring Crew personnel report to the Efficacy Monitoring Crew.

Major Responsibilities

- Undertake monitoring tasks as directed by the Efficacy Monitoring Officer.

#### Environmental Monitoring Officer

The Environmental Monitoring Officer is responsible for the implementation of the environmental monitoring plan.  USDA will be fulfilling this role to preserve the independence of data and ensure no conflict of interests.

Major Responsibilities

- Instructs and supervises the Environmental Monitoring Crew.

- Ensures a safe working environment for the Environmental Monitoring Crew.

- Coordinates with the Lehua Team Leader to communicate data analyses and recommendations to Assistant Incident Commander.

- Reports in real-time any problems seen in the field relevant to the bait application.

#### Environmental Monitoring Crew

The Environmental Monitoring Crew assists the Environmental Monitoring Officer for implementation of the Environmental Monitoring Plan. Monitoring Crew personnel report to the Environmental Monitoring Officer.

Major Responsibilities

- Undertake monitoring tasks as directed by the Environmental Monitoring Officer.

### Kauai Support Team

#### Logistics Support Kauai

The Logistics Support Kauai provides logistical support as requested to the baiting and monitoring operations. He/she will be based on Kauai and will be available by cell phone to provide necessary support. The Logistics Support Kauai reports to the Assistant Incident Commander.

Major Responsibilities

- Coordinates with Niihau Logistics Lead and Lehua Team Leader to provide equipment and supplies to the baiting and monitoring operations.

- Coordinates re-supply trips to Lehua Monitoring team.

- Coordinates reception and transport of samples from Lehua upon arrival in Kauai.

- Is on-call to activate E

- mergency Incident protocols in Kauai.

#### Niihau Support Kauai

The Niihau Support Kauai is the POC for all Niihau Ranch Operations. She provides on-call support as requested to the baiting operations, and the monitoring operation, and assists with the logistics of delivering that support.

Major Responsibilities

- Coordinates with the Niihau Logistics Lead.

- Is on-call to provide support to all field teams.

# LOGISTICS

## Bait Logistics

A cereal based pellet containing Diphacinone 50ppm will be used for the operation. The toxicant is a 1st generation anticoagulant rodenticide that has been used successfully for rat eradications. The bait, called DITRAC D50, was developed by Bell Labs, Inc. (Wisconsin, USA) for eradication of Pacific rats (Appendix 1 Material Safety Data Sheet, Appendix 2 Approved Label).

The DITRAC D50 bait is a 1-gram pellet, 3/8” in diameter and 1/2 to 3/8” long. The bait contains the biomarker pyranine, a non-toxic, odorless and tasteless dye that fluoresces green when exposed to UV light.

Table 2.  Bait amounts ordered for the Lehua Operation.

|  | Total Bait Needed |  | Packaging | Quantity |
| --- | --- | --- | --- | --- |
|  | (kg) | (lbs) |  |  |
| First application | 3335 | 7350 | 16 x 50 lb bags/ Oxbox pods | 147 bags = 9 pods + 3 bags |
| Second application | 3335 | 7350 | 16 x 50 lb bags/ Oxbox pods | 147 bags = 9 pods + 3 bags |
| Third application | 3335 | 7350 | 16 x 50 lb bags/ Oxbox pods | 147 bags = 9 pods + 3 bags |
| Hand broadcast | 79 | 175 | 25-lb/pail | 7 pails palletized |
| Total toxic (30 Kg/ha) | 10,084 | 22,225 |  | 441 bags in 27 pods + 7 pails |
| Non-toxic Formula 4 inert pellets, no dye, no biomarker – for bucket calibration |  |  |  |
| 3 mods x 2 buckets | 635 | 1400 | 22.7kg (50 lb) bags (318 kg) | 28 bags |

### Bait packaging and shipment

The bait will be packaged in 22.7 kg (50 lb) paper walled bags, which will protect it from moisture during transport and storage. There will be 16 x 50 lb bags placed inside a cardboard EcoShield boxed manufactured by OxBox container (“pod”). Twenty-eight pods containing 441 bags will be required for aerial broadcast. Additionally, 79 kg (175 lb) of bait will be packaged in 7 pails for supplemental hand application on Lehua. Each bag of bait will be labeled following EPA requirements (Appendix 2), and stamped with a batch reference code (as per Bell Labs standard). Bait pods will be packed with sufficient desiccant to reduce humidity inside and a sticky trap to prevent any mobile alien arthropods or mammals to be transported to Hawaii. Each bait pod will be labeled on one outer side with a unique identification (ID) number that relates to the batch reference code of the bait bags packed inside. One outer side of each bait pod will also be labeled with the appropriate pesticide storage warning label.

### Bait transport and storage

Bait pods will be shipped inside one 20 ft container from Bell Labs Inc., in Madison, Wisconsin, to Nawiliwili harbor on Lihue, Kauai.

Container will be placed on a chassis and transported to Niihau on the Niihau Ranch LCM landing craft, under supervision of DLNR’s assigned CPA.

### Bait quality monitoring

Quality analysis will be provided by Bell Labs as proof of optimum bait quality at their facility. Samples will be collected and analyzed for Diphacinone concentration and moisture content. Moisture content is used as a proxy for deterioration or mold growth. Results will be received prior to bait being accepted in Honolulu. Prior to each application, three bait samples from different pods will be collected and stored for later analysis if necessary.

The bait will be checked the day prior to each drop to confirm its suitability for application.

### Staging on Niihau

The Niihau Ranch LCM landing craft will transport all equipment and supplies including helicopter fuel to Niihau for the three applications. All equipment and supplies will be loaded onto the LCM landing craft at the Niihau Ranch Mahinaule harbor in Makaweli, Kauai, using their equipment. Niihau Ranch staff will coordinate offload via the LCM landing craft door directly onto the beach at Kauku’u.

## Personnel Staging

### Lehua Monitoring Team

The Lehua Monitoring Team will be transported to Lehua at least one week prior to the first application via the Niihau Ranch LCM landing craft. All equipment and supplies (including water, food, and bait for hand broadcast) will be transported together.

The LCM landing craft will first offload on Niihau and will then transfer the Lehua Monitoring Team. Personnel, equipment and supplies will be shuttled to shore at the USCG landing cave utilizing a small boat.

The Lehua Monitoring Team will be on site for 10 days after the third application.

#### Resupply and sample collection

The Lehua Monitoring Team will be resupplied roughly once a week. Resupply trips will aim to provide fresh foods, clean clothes and any additional items that may become necessary for the Lehua Monitoring Team. The resupply trips will also be used to collect environmental monitoring samples for transport to longer term storage sites and resupply dry ice and ice for sample storage on Lehua.

The first resupply/sample collection will be done during the second trip of the Niihau Ranch LCM landing craft for staging on Niihau. The following resupply trips will be coordinated with Niihau Ranch activities and will be done utilizing the same LCM landing craft on a schedule agreed in advance (contingent on weather conditions).

#### Environmental Samples

Environmental samples will be stored in coolers with dry ice on Lehua. They will be placed in smaller coolers for collection by the LCM landing craft weekly. The coolers will be picked up at the Niihau Ranch dock by project personnel and transported to DOFAW freezers or to USDA facilities in Lihue. The samples will finally be shipped to the USDA facility in Hilo for long term storage and analysis.

### Niihau Operational Team

All Niihau Operational Team personnel will be transported to Niihau the day prior to each application on two Niihau Ranch helicopter trips. The helicopter will depart from the Port Allen Airport in Hanapepe, Kauai. All personal gear and food for the Niihau Operational Team will be transported on the helicopter.

For each application, all personnel will stay on Niihau for two days/one night. The first day will be dedicated to setting up camp, incident command center, GIS station, baiting zone and fuelling area. Additionally, all team briefings and pre-operation meetings will be coordinated.

Baiting operations will commence as soon as possible on the second day, ideally at first light. Baiting operations are expected to be completed in 5-6 hours.  Site clean-up will occur after baiting operations and Niihau Operational Team personnel will return to Kauai at sunset on two Niihau helicopter trips.

## Demobilization

All equipment, including bait buckets; waste, including empty bait bags, pods, pellets and empty fuel drums; and unused supplies (bait and fuel) will be loaded into the empty container which will then be loaded on to the Niihau Ranch LCM landing craft at the earliest opportunity for transporting back to Kauai. In the case the container is not shipped back to Kauai, materials will be secured to the chassis for transport back to Kauai. Niihau Ranch staff will coordinate logistics and at least one project personnel will accompany the trip.

The Lehua Monitoring Team will be picked up from Lehua on the same LCM landing craft trip. Personnel and equipment will be shuttled to the LCM landing craft from the USCG landing cave using a small boat provided by Niihau Ranch.

The LCM landing craft demobilisation date will be coordinate with the Lehua Monitoring Team pick up date.

# BAIT APPLICATION STRATEGY

## Timing

It is generally considered that the best time of year to eradicate rats from island ecosystems is when the rat population is either in decline or approaching a low point in its annual cycle, which is primarily driven by food availability. On Lehua Island, food abundance (vegetation, invertebrates), availability of water, and rat activity is high during the winter/rainy season (October – April). Food availability and rat abundance generally decreases as the dry season progresses. Therefore, from a rat biology perspective, the best operational window for the eradication on Lehua is the boreal summer months between May and September.

The second important component determining the timing of the eradication is the potential risk to non-target species. The summer months between July and September would minimize impacts on breeding seabirds on Lehua. During these months, wedge-tailed shearwaters and red-footed boobies will still be nesting, but the breeding season for Black-footed (Phoebastria nigripes) and Laysan albatross (Phoebastria immutabilis) will be approaching the end. All albatross chicks are expected to have fledged by the end of July (Wood et al., 2004 and VanderWerf et al., 2007). Also, the number of migratory shorebirds is at its lowest April to August.

Finally, the summer months are the best option from an operational perspective because the weather and ocean conditions between June and September are generally calmer and more predictable (i.e. suitable sea conditions for transporting equipment and supplies to Niihau and suitable flying conditions for undertaking each of the three separate bait applications). Undertaking the bait applications in the dry season will minimize the chances of precipitation impacting bait condition and availability as well as reducing the potential for bait pellets being washed into the ocean.

Three discrete applications of bait containing Diphacinone are planned for Lehua during August -September, preferably within the month of August but possibility going into September. The first application is scheduled for the week of August 22nd, 2017. Once baiting initiates, the team will attempt to finish the three baiting applications within the best weather windows and logistical constraints available while meeting the overall eradication strategy.

| Anticipated operational window |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Figure 4. Timing matrix for Lehua Island rat eradication based on parameters that influence decisions for operational considerations and non-target species. Dark grey = high influence, light grey = moderate influence and white = minimal influence

## Baiting strategy

Due to its cumulative action, a rodent needs multiple feeds over several days to receive a lethal dose, specifically between 3 and 10 days with no more than 48 hours between feeds. Therefore, it is crucial that every rodent has ready access to the bait for at least 10 consecutive days. The goal of the baiting operation is to ensure bait is available in every potential rat territory in sufficient quantities and for at least 25 consecutive days. The following strategy is designed to make bait available for this duration.

### Timing between drops

Three discrete bait applications will be undertaken seven to ten days apart. Based on bait availability data from the bait trial of 2015, which had a bait consumption rate of 2kg/ha/day, it is planned that there will be 7 days between the first and second applications and 10 days between the second and third applications. This timing is subject to weather and logistical constraints, eg helicopter availability, as well as the rate of bait uptake after each drop which will be monitored daily by the team on Lehua.

If a period of bad weather is forecast, a drop can be brought forward to a minimum five-days subsequent the previous application. The exception would be if there was a major rain event following one of the bait applications which is of sufficient scale to have removed (degraded or washed out) bait from rat territories on any part of the island which would be informed via the Lehua Monitoring Team. In that case, the bait would need to be replaced as quickly as possible to ensure continuity of access for a full 10 days. Under this plan, every rat should have uninterrupted access to bait for at least 25 days.

### Baiting rate

Each bait application will target a minimum rate of 20kg/ha of bait on the ground. The baiting rate for a diphacinone operation should ensure high foraging encounter rates and high temporal availability of bait, meaning it should take longer for both target and non-target bait consumers to reduce the bait level below the minimum bait density desired. The agreed minimum bait density is 4 kg/ha, i.e. bait density on the ground should not be less than 4kg/ha at any point on the island at any time during the operation. If it decreases below 8 kg/ha, conversations within the ICS structure will be triggered to determine the appropriate course of action. These levels are all minimum rates across the whole of the island, not averages, as the latter could leave gaps in the baiting coverage which would lead to failure.

While the aim is to achieve a rate of 20kg/ha on the ground per drop, the maximum average application allowed is 30kg/ha per drop, meaning a maximum of 3,360kg/ha of bait can be used for each drop (30 kg/ha * 112 ha island size). The proposed combination of timing between drops and the quantity of bait applied is designed to maximize the probability that there is sufficient bait available both spatially and temporally to put every individual rat at risk. Bait availability monitoring with be on-going on the island to provide daily data regarding the bait density available on the ground.

### Bucket configurations

Three different bucket configurations provide three very different effective swath widths which will be adaptively applied in different scenarios on Lehua. According to the the width of target baiting area and probabilities of risk of bait entering the ocean, different bucket configurations can be employed to apply bait at the effective swath width, or the estimated horizontal distance of bait spread from the bucket. The bucket configurations are as follows (Figure 4):

- full swath - bait thrown out both sides of the bucket.

- directional swath – where an internal deflector is put in the spinner to only allow bait to be thrown out one side, which is used along the coast or where a full swath is too wide for the land area being treated.

- and narrow swath, spinner removed and a spreading cone put in so that bait essentially falls straight down, which is used to treat very narrow areas which are too narrow for the deflector bucket.

Effective swath widths will be confirmed during calibration trials prior to the operation.

Figure 4: Bait bucket configurations for use on Lehua.  Image credit: Island Conservation.

## Baiting Plan

Figure 5.  Proposed baiting plan showing different treatment areas on Lehua.

To accomplish a rate of 20 kg/ha on the ground while minimizing bait drift into the marine environment each bait applications will be divided into three treatment areas: interior, coastal zone, and coastal/interior overlap.

- Interior: Where the target area is >100m wide, so that bait can be applied with low risk of it going into the sea, bait will be applied using the full swath bucket. To minimize the risk of gaps between parallel flight lines interior swaths will be overlapped by 50%. To minimize the risk of bait entering the water interior flights will start and stop 20 meters from the coastal edge. The bucket will have a sow rate of 10 kg/ha.

- Coastal Zone: Bait will be applied along the mean high tide water line using the directional swath bucket so that bait is only dispersed inland and not into the sea. To minimize the chance of gaps along the coast and ensure consistency in bait application the coastal zone will be flown twice at a rate of 10 kg/ha.

- Coastal/interior overlap: To minimize the chance of gaps between the interior and coastal zone swaths, another coastal application flight will be flown with the full swath ~60 m inland of the coast and parallel to the coastal edge. This swath is intended to overlap both the coastal zone and interior swaths. This will be done at a sow rate of 10kg/ha.

- Narrow: If the area is wider than 40m but less than 90m bait will be applied with the directional swath bucket, while if the area is narrower than the deflector swath (40m) bait will be applied using the narrow swath bucket, sometimes requiring multiple parallel passes to cover it adequately.  This will have a sow rate of 20 kg/ha.

The direction of the flight lines will be set in consultation with the pilot to get the best consistency for flight speed and hence sowing rates while minimizing any bait going into the sea. This will be challenging given the shape of the island, the need for straight flight lines and the desire to get the maximum area covered with the full swath bucket.

At points where flight lines overlap, the amount of bait applied will exceed the target application rate of 20kg/ha. This is likely to occur along adjacent borders of parallel swaths, at the end of parallel swaths where they intercept the inner and outer coastal swaths, the boundary between the outer and inner coastal swaths, and adjacent to any areas missed during the initial baiting runs (for example, gaps as indicated by the GPS flight path data and subsequently rebaited).  Areas of overlap exceeding the target application rate will be minimized as much as possible while ensuring that all areas are baited with the at least the target rate.

Hand baiting may be used to fill any gaps where the risk of an unacceptable amount of bait going into the sea is deemed to be too great or areas that cannot be treated aerially. Hand baiting will be a combination of baiting from the ground where safe to do so, i.e. teams walk to the area and baiting, and helicopter baiting where bait is applied from the helicopter in small paper bags.

### Hand baiting

Limited supplemental hand bait application, including broadcast, bait trays (open trays on which bait is placed to allow easy access by rats and easy monitoring of bait uptake), and bait bags (paper lunch bags distributed out of a helicopter in inaccessible areas) may be used to reduce the risk of gaps in bait distribution in specific areas of concern (i.e. areas that cannot be treated aerially with a high level of confidence).

#### Sea caves

Sea caves are likely to contain rat territories as they may provide food sources in the form of nesting seabirds and invertebrates, and as such, it is crucial they are treated. There are two sea caves on the south side of the island which are only accessible by water. These will be baited by one of the following options in conjunction with each aerial application:

a) personnel from the Niihau Operational Team using the Niihau Ranch small boat to travel to Lehua and hand baiting by two people swimming into the caves with bait in sealed containers. Approximately 2 kg of bait above the splash zone (visible water marks) in areas accessible to rats will be used.

b) personnel from the Lehua Monitoring Team swim bait in sealed containers into the caves. Approximately 2 kg of bait above the splash zone in areas accessible to rats.

The area of the cave will be estimated and used to direct the amount of bait to be distributed. It is anticipated that a higher than average quantity of bait (approximately 300 bait pellets for each 10m2) will be put into each cave every time it is entered to ensure bait availability over time, even if caves cannot be accessed during the following baiting operations.

#### Dry caves

These are caves above the high-water mark. Where possible to safely do so, these caves will be baited by hand broadcast into the cave. Where they are inaccessible by foot, the helicopter will hover at the mouth of the cave with the deflector bucket and target bait into the cave. As an added measure, if legally allowed, small paper bags of bait will the thrown into the cave from the helicopter. Based on previous operations it is believed that any rats present will readily chew through the bags to access the bait.

#### Manmade structures and shelters

While most of the manmade structures on the island are not large enough to provide a full-time refuge for rats (ie they will almost certainly come out to feed on the bait which will be spread aerially over the structures), as an additional precaution bait will be placed in/under each structure. Namely:

- Water catchment and tanks in Gully West of Camp

- Water catchment/ storage area and tanks associated with camp

- Toilet

- Temporary tarp shelter

- Tent platforms x 5

Where possible, these will be baited by placing an open bait station under the structure containing 30 individual pellets. Bait stations that have been deployed in these areas since 2009 will be used to avoid neophobic behaviour. Observations made using coconut as bait showed the rats freely entered such bait stations.

For any structure where it is not practical to use a bait station a handful of baits will be thrown under the structure (e.g. tent platforms).

#### Weather port storm shelter

Due to the larger area of this structure and the equipment stored under it providing a larger refuge for rats, three open stations are to be placed under the weatherport. They will each have 30 bait pellets put in them.

Each of the three stations will be checked at least every other day for the first two weeks, then, as required after that. During each check, the number of individual bait pellets will be counted and recorded. Any partially consumed or missing pellet will be replaced to ensure a total of 30 pellets.

All bait stations will be individually numbered and labelled and the record sheet (refer appendix 11) will be used to record all relevant hand baiting activities included initial baiting and ongoing servicing of devices including the amount of bait uptake.

Hand broadcast

While it is preferable to treat as much of the island as possible aerially to reduce the risk of gaps in bait coverage, in the event that a gap in the aerial baiting application is identified which is not able to be filled using the helicopter (e.g. the gap is identified after aerial baiting has ceased), it may be possible to ensure bait distribution using hand broadcast. In that event, the amount of bait available to be used (i.e. ensuring the total bait used for any application does not exceed an average of 30kg/ha) will be reviewed and a detailed description, preferably detailed GPS coordinates, will be provided to the Lehua Monitoring Team. The Team will then treat the area by following the NZ Department of Conservation hand broadcast SOP. Specifically, they will identify the width of the area to be treated and space personnel out at 10m intervals at the start of the gap. They then move forward 10m and spread a cup containing approximately 200 bait pellets (the cup will be marked with a line to identify the required amount of bait). The bait will be divided evenly into five portions. They will spread bait to the four quarters of the compass out to 5m, so that the bait from adjacent baiters meet and around the baiter's feet. All baiters move forward 10m and repeat. If the area is narrower than the number of baiters, the area covered by each baiter can be reduced accordingly as long as the amount of bait is reduced proportionally. If the gap requires more bait than is available on Lehua the option of using more bait from Niihau will be considered (as long as the total used for all techniques for any application does not exceed the permitted 30kg/ha).

Ideally all hand baiting will be done on the same day as the aerial application; however, if this is not possible (e.g. due to logistical constraints) they will be treated as soon as practicable afterwards.

#### Toilet Structure

As an additional precaution for the composting toilet, which provides an alternative food supply to rats, two Sherman live-catch traps will be baited with coconut, and set up inside the toilet structure and checked regularly. Live catch traps will be used due to the risk posed by kill traps to shearwaters which use the composting toilet for nesting. These will be maintained for as long as personnel are on the island. The cover will be kept down on the toilet bowl to prevent entry by rats.

The Lehua Team leader is responsible for ensuring that these actions are undertaken as directed.

### Bait Estimates

Table 3. Bait required per treatment area during each of the three bait applications.

| Treatment Area Description | Per Application |  |  |  |
| --- | --- | --- | --- | --- |
|  | Area (ha) sowed |  | Sow Rate (kg/ha) | Bait Applied (kg) |
| Coastal zone | 22.5 |  | 20 | 450 |
| Coastal/interior overlap zone (‘safety buffering’) | 16.7 |  | 10 | 167 |
| Interior zone | 198 |  | 10 | 1980 |
| SUBTOTAL |  |  |  | 2,597 |
| Supplemental bait (additional application of up to ~30% of the maximum bait applied to the above treatment areas, as needed) | 76.3 | 10 |  | 763 |
| TOTAL BAIT ALLOWED IN EACH APPLICATION |  |  |  | 3,360 |
| TOTAL BAIT ALLOWED IN THREE APPLICATIONS |  |  |  | 10,080 |

Maximum average application rate per application is 3,360 kg / 112 ha = 30 kg/ha)

## Deviations from proposed baiting strategy

Three main factors will be considered to determine the specific time interval between applications: weather conditions, bait uptake monitoring data, and logistical considerations.

These factors will be collectively considered and decisions will be made following agreed deviation protocols (see Appendix 8).  Other unforeseen factors may become important and will be incorporated as needed through the same deviation protocols.

# HELICOPTER OPERATIONS

## Contracts and operators

### Niihau Helicopter

The Niiahu helicopter pilot and Niihau ranch staff will provide safety briefings and ensure all required flight protocols are followed. The contact for Niihau ranch and helicopter activities is Mary Sue Matter at the Niihau Ranch business office, (808) 338-0710.

The Incident Commander or their delegate will be responsible for coordinating all flights on the Niihau helicopter.

### Baiting Helicopter and Pilot

An Aerial Operator will be contracted to provide a suitable helicopter for three bait applications on the dates specified by the project management team. This will require ferrying the aircraft from Maui at least one day prior to each anticipated bait application day. A pilot who has the required skillset and experience with underslung spreader buckets and Tracmap GPS systems will operate the helicopter. The Aerial Operator will also provide an A&P certified mechanic for each of the bait applications. All helicopter maintenance will be coordinated to ensure the machine is available for each bait application.

The Baiting Operations Chief will be responsible for coordinating all logistics for the baiting helicopter.

## Operational Locations

The following locations will be used for the Lehua Operation. A helicopter operational site will be considered any site where it is anticipated that there is a reasonable likelihood that the aircraft will set down or any site which is planned to be treated with bait during the operation.

- Nanina Beach, Niihau Operational Site – bait loading/refueling

- Lehua Island – External loads and personnel transport, bait application

### Lehua Island

A landing pad will be identified near the field camp in case personnel transport is required directly to/from Lehua, either for a medical evacuation or otherwise. Additionally, a location will be identified close to the field camp for receiving/sending external loads. If sling loads are required to send gear or supplies to Lehua Island, a Kauai based helicopter company will be hired to undertake the job, unless it is more convenient to use the baiting helicopter in which case arrangements will be made with the Aerial Operator.  There are no specific plans for personnel transport or external loads on Lehua Island.

### Niihau Operational Site

The aerial baiting operation will be based at Nanina beach on the Northern point of Niihau Island, referred to as the Operational Site (figure #). The bait loading and refuelling sites will be managed by the Baiting Operation Chief during all aerial bating. Non-crucial personnel will not enter the PPE area when active flight operations are taking place. The Operational Site will have the following key components:

- Primary landing pad – The location that the helicopter will sit down at when not required, eg either while still running eg when doing a GPS download, or when switching off. Will be marked on the ground so that only approved personnel (by the BOC or Pilot) including the mechanic enter it. This is within the PPE zone

- Bait loading site- the area immediately around the bait loading platform where the bucket will be placed during loading. PPE as per bait label ie overalls. Closed toed shoes, gloves, googles and dust mask along with helmet and ear protection for working under the helicopter will be worn within this site whenever the helicopter is operating. Overalls, closed toed shoes and gloves will be worn at all other times.

- Bait loading platform- a raised platform to facilitate the easy loading of the bait bucket while the helicopter is hovering to the side or has set down behind the platform. This will either be the back of a flatbed truck.

- Fueling Site – Adjacent to the loading site. This is likely to be the same as the primary landing pad. A fuel spill kit will be staged at this location to manage any spillage on the ground. Secondary containment is not required for the fuel drums being used (55 gallons or less).

- Decontamination/Changing area – For personnel to clean off after being exposed to bait/toxin. Comprises of fresh water washing station, eye wash station, bags to contain contaminated clothing and equipment. This area will also include drinks for the loading team.

- Secondary landing pad – In case of emergency or the sudden presence of a hazard at the primary landing pad. To be confirmed by the pilot prior to initiating operations

- Fuel Storage- 12 drums (55 gallons) of Jet A1 to be stored on the back of Niihau Ranch Truck away from the refuelling site until required for refuelling the helicopter. In addition, there will be 15 gallons of petrol for running the bucket motor and the generator at the ICC.  Secondary containment not necessary.

- Bait Storage – 20 ft shipping container on a Niihau Ranch truck chassis, will be covered with a tarp to reduce heat and camouflage netting to make it less conspicuous Bait in the container is in 50lb bags with 16 bags to a cardboard pod.

- Incident Command Center – (ICC) will be established adjacent to the load site, where it can oversee all operations but is outside the hot zone, to monitor bait loading and refuelling  activity and analyse GIS data during operations. The equipment at the ICC will include, but is not limited to: computers and printer, relevant maps, a satellite phone, and VHF radios and will be the site of operations for the IC, Assistant IC, GIS Manager and observers.

Figure 6. Schematic of the set up within the Niihau operational area – not to scale

Figure 6. Schematic of the set up within the Niihau operational area – not to scale

Secondary Helicopter Pad

Secondary Helicopter Pad

Bait Storage Area

Bait Storage Area

PPE Area

PPE Area

Hot Zone

Hot Zone

Bait loading site including bait loading platform

Bait loading site including bait loading platform

Hot Zone

Hot Zone

Refuelling Site

Refuelling Site

Wind indicator

Wind indicator

Decontamination Area

Decontamination Area

ICC

ICC

The area will be marked on the ground for to demarcate the different operational sites and PPE required for each site

Fig 7 Proposed Operation Area set up  To be confirmed on site.  North is down in the image below.

### Baiting Helicopter Storage

The Aerial Operator will coordinate all overnight storage of the helicopter on Kauai. When not in use at one of the operational sites the helicopter will remain at the Lihue airport. On all operation days the helicopter will be fuelled and ready to begin flights as early as legally possible.

## Flight Time Estimates

The following flight times are estimations for planning purposes.

Table 4. Anticipated time estimates for aerial operations. Flight time is the number of helicopter hours required. Operational time is the amount of flight time plus refuel time and time for filling bucket and hook up and unhook time required. Contingency operational time refers to the number of additional hours allowed for operations.

| Flight | Flight Time (unit) | Operational Time (hrs) including flight time | Contingency Operational Time (hrs) | Total Allocated time (hrs) |
| --- | --- | --- | --- | --- |
| Ferry Maui to Kauai | 2 (hrs) | Na | Na | 4 |
| Ferry Kauai to Niihau operational site (one way) | 20 (min) | Na | Na | 1 |
| Ferry Nanina to Lehua | 3 (min) | Na | Na | Na |
| Bait application including ferry from Nanina | 3.5 (hrs) | 4.5 | 3 | 7.5 |

## Helicopter fuel

### Sourcing fuel

12 x 55 gallon drums of helicopter fuel (Jet A / Jet A-1) have been purchased for the baiting operation. Fuel will be transported in DOT approved 55 gallon drums. The fuel will be loaded on to a Niihau Ranch truck for transport to Niihau by the Niihau Ranch Barge it will then be stored at the Niihau operational site until required. Niihau Ranch staff will oversee the loading and offloading of the fuel drums on the barge on Kauai and Niihau.

### Fuel storage and spill response

Fuel will be stored in DOT HAZMAT rated 55 gallon drums on a Niihau Ranch once at the Operations site. It will then be moved to the refueling site as required. Secondary containment is not required when using 55 gallon drums. A fuel spill response kit will be available at the load site and fuel spill response plan will be developed (see Section 12, Fuel Spill Response). Empty fuel drums will be collected and removed from the site as soon as possible/ at the completion of the operation. All remaining drums containing fuel will be used by Niihau Helicopters or will be transported back to Kauai on the barge at the end of the project.

### Refueling the helicopter

The Aerial Operator is responsible for all testing and handling of fuel and all fuelling of the aircraft. However, some of the ground crew may assist in moving fuels drums as necessary. The Aerial Operator will follow NFPA and FAR protocols for all fuelling actions.

During baiting operations helicopter refuelling will occur in the designated fuelling area at the operational site. Fuelling will be carried out from 55 gal drums. An electric pump will be the primary refuelling system, a second electrical pump will be available as a backup. Only qualified and authorized personnel will be present at the refuelling site during helicopter refuels. The drum being used for refuelling will be held in secondary containment in case of spill.

Only the pilot or mechanic are to undertake refuelling operations, ground crew may assist under direct supervision if requested. The helicopter does not need to be shut down during refuelling for the operation. To control spills, self-closing nozzles will be used and not blocked open or dragged along the ground. Additionally, a fuel spill kit will be available at the operational site to manage any spillage onto the ground.

When the helicopter is refuelled during baiting operations, the bait bucket motor will be refuelled with unleaded fuel dispensed from a small jerry can, 15 gallons of petrol will be available for this purpose. This will be managed by the Bait Loading Lead.

## Air Operations Communications

Communication between pilot and ground crew will be via Air Band radio and structured to reduce the amount of traffic from non-essential personnel. All team members will be briefed on radio use and the schedule of radio frequencies prior to the start of operations. The majority of communication while the helicopter is in the air will be between the Baiting Operations Chief and Pilot.

The following frequencies will be used: Aviation Band 123.45

# Flight Tracking and Flight Following

Flight tracking will be done through Spidertracks http://www.spidertracks.com  which is the GPS based system used by the Aerial Operator. The login information will be provided to the Bait Operation Chief for the duration of the operation. Additionally, flight following during the operations will be recorded via the bait tracking worksheet, which will be the responsibility of the Bait Operation Chief. More info on flight following and helicopter safety can be found in the Lehua Helicopter Safety Plan.

Prior to departing LIH each flight the Baiting Pilot will call the Baiting Operations Chief communicate time of departure and estimated time of arrival at the Ni’ihau Operational Site. The pilot will contact the Baiting Operations Chief when approaching the site to confirm the loading zone is clear of obstacles and debris. The Baiting Operations Chief will record this info and time of arrival on a flight following worksheet. All other non-bait application flight will be recorded on a flight following worksheet.

## Staging Site Logistics

### Baiting Helicopter

The baiting helicopter will travel, with baiting pilot and mechanic, from the Aerial Operator’s base to Kauai at least one day prior to each bait application. The helicopter will refuel and then proceed to the Niihau Operational Area for site familiarisation, operational checks and team briefings. The Bait Operation Chief, will be the point of contact with the Aerial Operator regarding logistics. Upon completion of baiting operations for the day the baiting helicopter will depart Niihau and return to Kauai.

### Bait Loading Site setup

The day prior to the application day, the bait required for that application (the maximum amount that can legally be spread during that application) will be manually transferred from the storage container onto a flatbed truck for transport to the loading site. It is planned to use the truck bed as the loading platform for the operation as this minimises the handing of the bags of bait. If for any reason the truck bed is not suitable a loading platform will be constructed out of bait pods next to the truck and the bait transferred to the platform as required. The final strategy for bait loading will be identified on the setup day once the team is on site.

## Bucket Calibration

The main objectives for the bait bucket calibration are:

For each of the required bucket setups- full swath, directional and narrow swaths:

- Determine the size/s of the bucket aperture/s required to deliver the desired application rate/s at the prescribed air speed.

- Determine the RPM of the spinner and the belt size and pulleys required to deliver the effective swath width desired.

- Confirm the effective swath width and bait spread pattern produced by the bucket.

- Confirm the actual swath width- for planning flight lines to minimise bait going into the marine environment.

- Confirm the function and compatibility of bucket and helicopter operating systems.

Additionally, the bait bucket calibration for the Lehua project will be used as a training opportunity for project staff unfamiliar with aerial baiting operations, including the pilot and bait loading crew.

Bait calibration will be undertaken for each set up for each bucket that may be used during the operation and will comply with Island Conservation’s standard operating procedures (SOP) on bait calibration.

### Calibration Site

The Kauai Raceway Park has been secured for the Lehua calibration operation. The park is a large fenced area used monthly for drag races. An area of approximately 225 m x 85 m on the west end of the park has been identified. This area is mostly covered with asphalt with sparse low grass in between paved tracks. The park is surrounded by trees and shrubs (mostly invasive species) that provide shelter from wind.

This area is privately owned and access is easily controlled. This is an area with high levels of disturbance and environmental impacts are not expected. No livestock or domestic animals are kept in the park.

### Supplies

- String, flagging tape, pin flags, chalk for marking the grid.

- 4 x orange pails for marking the flight line.

- 1 x box zip lock bags and marker pens for collecting bait.

- Electronic scales for weighing bait (accurate to 0.1g and able to weigh up to 200g).

- Radio comms for air to ground communications.

- 100m measuring tape for marking out the grid.

- Tachometer.

- Calculator.

- Data sheets and clipboard.

### Site Preparation

Calibration will only happen under the following weather criteria:

- No active rain.

- Winds less than 15 mph at 100 ft above ground level.

Prior to the helicopter arrival, up to four person-hours will be necessary to prepare the calibration site. Personnel will set up a 100 x 10 m grid a using string, chalk, and pin flags.  The grid will be set up across the track.

The straight path through the centre of the grid, and baiting start and stop points 100 m before and 50 m after the grid, will be marked using orange 20lt pails so that it is clearly visible to the pilot.  All bait from previous bucket calibration runs will be cleared.

Calibration procedures will follow Island Conservation Bucket Calibration SOP.

### Site Cleanup

Clean up of pellets will be required only on the raceway and a street cleaner will be made available by the Kauai Raceway Park. Special consideration will be made for bait bouncing on the asphalt surface when measuring swath widths

# BAITING OPERATIONS

## Weather Forecasting

Weather conditions are expected to be favourable during the proposed operational window. The main weather considerations for the eradication on Lehua are rain events, tropical storms, and hurricanes.

The first application will use the following weather criteria:

- No rain forecast for a minimum of 4 days/3 nights.

- No major rain events forecast for at least 6 days.

- No winds above 20 mph forecast for the days of the bait applications.

The second and third application will use the following weather criteria:

- No major rain events forecast for at least 3 days.

- No winds above 25 mph forecast for the days of the operations.

If weather conditions do not meet the above criteria, operations may be delayed as deemed necessary to maximise the efficacy of the operation.

The weather forecast will be monitored daily starting 10 days prior to the first application. The following websites will be used to assist with weather prediction. Additional weather outlets may be used if suitable.

- University of Hawaii meteorology website.

- Tropical Tidbits

- Windy tv

The GIS Manager is responsible for receiving daily weather forecasts and communicating these to the Baiting Operations Chief.

## Decision to activate operational team

If at five days out from the drop date the forecast is looking suitable, i.e. no significant rain and wind, then the team and relevant partners including the Aerial Operator, will be put on standby. This will be revisited the following day and, if conditions are still suitable, the Niihau Operational Team will be informed so that, they are ready to go to Niihau.

Three days prior to the proposed bait drop the Incident Commander will convene the Incident Command Team to review operational readiness and decide to mobilize the operational team to Niihau.

## Operational Site Preparation

The day before the drop the operational team will:

- Transfer the maximum number of bags of bait allowed for application the next day from the container on to a flatbed truck. The truck will then be driven to the loading site where, if suitable it will be used as the loading platform. If for any reason this is not possible the bags of bait will be manually carried to the loading site/ a loading platform will be constructed out of bait pods and plywood.

- Transfer approximately three drums, as directed by the pilot, of Jet A1 from the storage site to the refuelling site where one drum will be set up in a bunding/ spill containment system.

- Set up the Incident Command Centre, consisting of a shelter, table for the GIS manager, chairs and refreshments at safe distance from the loading site.

- Set up the decontamination area where all personnel who have been handling bait wash prior to drinking and change prior to eating and at the end of the operation.

- Mark out the loading site on the ground to identify the PPE area including demarcating the “Hot”/Toxic area and the decontamination area.

## Authorization to Commence Baiting Operations

Social Environment and Compliance Check

Prior to initiating the aerial baiting operation a compliance check will be performed. Aerial baiting operations will not commence unless all necessary permits are in place.

The Assistant Incident Commander will advise Incident Command Team on whether the social environment is acceptable to commence aerial baiting operation.

Operational Readiness

Prior to initiating the aerial baiting operation, an operation checklist will be completed by the Baiting Operation Chief, and reviewed by the Incident Command Team. The checklist shall include, but not be limited to:

- Helicopter, buckets, and associated equipment tested and ready

- Bait condition confirmed

- Pilot briefed and ready to commence

- Safety equipment and procedures in place, safety briefings completed

- Fuelling location prepared

- Bait loading site prepared

- Site is clear of all potential hazards to helicopter operations

- Debris management protocol is prepared

- Weather conditions on Lehua confirmed

- HDOA/EPA representative satisfied

The checklist will also be reviewed and approved by the Incident Command Team in advance of baiting operations. The Baiting Operation Chief will be responsible for providing details of flight activities for the day, while the decision to fly on any given day will be made by the Incident Commander.

Following approval by the Incident Commander, the authorization to commence aerial baiting operations will be given to the baiting pilot and will depend on suitable weather conditions for safe, effective baiting.

## Weather Requirements

Poor weather conditions may cause baiting operations to be halted, changed, or delayed. Daily baiting will be delayed (or discontinued if flying has already commenced) if the weather is unsuitable, and/or the pilot feel it is no longer possible to continue flying in a safe manner, for example, risk of bird strike.

Weather conditions in which baiting may be halted or delayed are:

- Wind speeds more than 25 mph (22 knots), with an evaluation of the terrain and impact of the wind conditions.

- Visibility conditions in the area being treated are obscured, inhibiting the pilot’s ability to safely operate.

- Conditions of heavy rain (loading bait buckets in rainfall may cause “gumming” of bait and potentially cause bait bucket to jam or clog).

## Bait-bucket Loading Procedures

The Bait Loading Team will consist of:

Bait Loading Lead

Bait loaders (5)

Bait loading will be done manually with a team of five personnel along with the Bait Loading Lead present to oversee operations. Only four team members will be working at any time in order to allow one to rest. Two bait loaders will be on the bait loading platform when the bucket is being filled with the helicopter overhead with two others standing nearby on the ground to collect the empty bags. The Baiting Team Lead will stand clear of the loading platform during active bait loading operations in order to oversee operations, including safety, however they will be close enough assist as necessary (i.e. in the event of a loose bag.)

The bait spreader bucket will be filled with bait directly from pre-opened 50 lb. (22.7kg) bags. A secure loading platform will be created to facilitate emptying bags of bait into the bucket, this is referred to as the bait loading platform. This is likely to be the flat deck of a truck with the back up being a platform made from empty bait pods and plywood.  If any plywood sheets are used, they will be secured down to ensure they don’t get caught in the rotor downdraft (downwash). Up to 16 pre-opened bait bags (360 kg load) but usually 6- 10 will be arranged on the top of the loading platform in readiness for the next bucket.

While approaching the bait loading site, the Pilot will communicate to the Baiting Operations Chief the desired amount of bait that will go into the next bucket. Additionally, the pilot will also relay the total area covered in the previous run, the Baiting Operations Chief will record this information onto the bait tracking worksheet.

Bucket loading sequence:

- The bucket will be attached to the helicopter with nine-meter strops.

- The 50 lbs. bags of bait will be arranged in two rows of bags on each side of a small clear area in the middle of the platform, and pre-opened in readiness.

- The pilot will communicate to the Baiting Operations Chief when inbound to the bait loading site.

- The Baiting Operations Chief will maintain a position in line of sight with the pilot during bait bucket loading.

- Bait Loading Lead will direct bucket in to loading position as required.

- When the helicopter is at the bait loading site in a hover only four people will be under the helicopter. The Bait Loading Lead will be overseeing operations.

- Two bait loaders will be positioned on top of the loading platform ready to pour bags of bait in to the bucket while 2 others will be on the ground in front of the platform ready to position the bucket and receive empty bait bags.

- When the bucket arrives the two loaders on the ground or the baiting team lead will grab the bucket by the frame and guide it next to the loading platform.

- The Bait Loading Lead will check the bucket every time it comes in to ensure there is approximately 10 kg of bait remaining in the bottom. The Bait Loading Lead will relay this information to the Baiting Operations Chief.

- Once the bucket is next to the loading platform the two loaders standing by on top of the loading platform will lift and empty each bag into the bucket.

- The two staff on the ground will grab and secure the empty bags from the loaders. The two staff on top of the loading platform will maintain positive contact with the bag and not let go until the bait loader on the ground has securely grabbed the bag.

- The bait loaders will hold empty bags securely, ensuring no bags become lose while helicopter is present is critical to the safety of the operation.

- Once all bags have been emptied into the bucket the two staff on the platform will ensure the bucket lifts off the platform smoothly by holding the frame and guiding it away from the loading platform.

Between bucket loads the loading team will dispose of empty bait bags and any other debris securely, check the site for any loose bait (to be collected and disposed of appropriately) and then set up for the next load, ie open the required number of bags on the loading platform. It will be up to the Bait Loading Lead to ensure staff stay on task and prepared to receive and load the bucket as required. The Bait Loading Lead must confirm to the Baiting Operations Chief that they are ready before the pilot is given the approval to come in to refill.

Time in between bucket loads will be spent either tidying the loading site, resting or carrying out duties such as bucket maintenance and GIS management. Team members will be rotated as needed to reduce the risk of heat exhaustion, injury, etc.

A key aspect of safety on the loading sites is the securing of empty bait bags. These can cause extensive damage if drawn up into the rotors after being caught in the rotor wash. Empty bags will be secured by two designated loading team members then placed in a bait pod designated for this purpose and far enough from the loading site to not be affected by rotor wash. Pods that are filled with empty bait bags will be moved as needed during shut downs. One of the key roles of the Baiting Operations Chief will be to ensure the pace of loading is conducted at a rate that empty bags and maintaining the load site clear of debris can be managed.

The helicopter pilot will communicate with the Baiting Operation Chief to indicate how much bait they want in each individual load, taking into consideration the site to be baited. The bucket should return to the load site with some bait – approximately 10kg, left in the bottom to demonstrate that the bucket did not run out of bait. This will be checked by the Bait Loading Lead and relayed to the Baiting Operation Chief. If the bait bucket returns empty, the Baiting Operation Chief will relay information to the Incident Commander and GIS Specialistt and notify the Baiting Pilot that the previous line needs to be rebaited.

The helicopter will be set down at regular intervals to allow analysis of baiting swaths, the bucket will be refuelled at that time or more frequently if required i.e. at least every 45 min.  Refuelling of the bucket will be undertaken by the Baiting Operation Chief.

## Clean up of loading site

Following each days operation a full check of the loading site and flightpaths over Niihau will be undertaken and all bait collected for appropriate disposal. This is in addition to the loading team collecting any bait spilled during loading as quickly as possible i.e. either during the loading or prior to the next load.

All empty bags and other waste including empty fuel drums will be collected and stored appropriately for later disposal.

## Bait Application Monitoring

### Monitoring Sow Rate

On arrival at the bait loading site at each bucket reload, the helicopter pilot will communicate via radio to the Bait Operations Chief the area (measured in ha) that has been treated with bait. This is cumulative. The Bait Operations Chief will record this information into the bait-application monitoring spreadsheet (see Appendix 9) and calculate the sow rate achieved by each bucket load to direct any necessary changes to either the helicopters speed or the bucket’s aperture size to obtain the desired sow rate.

### Deviations from Target Sow Rate

The Baiting Operation Chief will ask the pilot to adjust flight speed if the reported sow rate is varying between 2 and 5 kg/ha from the target sow rate.

The Baiting Operations Chief will notify the Incident Commander immediately if the reported sow rate is more than 5 kg/ha from the target sow rate. In that case, the Baiting Operations Chief will direct the pilot to set down the helicopter. The Incident Commander will call for a halt in operations and review the bait application data (bait used, area covered etc), then consult with the Incident Command Team about how best to achieve the target application rate before resuming operations.

### GPS

On aerial baiting days, the helicopter will halt operations and set down and the GPS information will be downloaded after the first load, then as frequently as needed to monitor the standard of the baiting operation including the bait sow rate.

To download the GPS information, the helicopter will shut down and the Baiting Operations Chief will collect the GPS TracMap information from the pilot and give to the GIS Specialist. The GIS Specialist will produce bait application maps and interpret the data looking for any possible errors in flight lines, GPS logging, or bait application rates and provide this to the Baiting Operations Chief to provide to the Incident Commander.

Operations will not resume until the GPS information has been reviewed by the Incident Command Team and approval to resume given by the Incident Commander. During this review, the helicopter pilot will provide a quick assessment of the aerial baiting operation including: weather conditions, wind, bucket operation, bucket loading and general observations.

### Wind monitoring

The Lehua Team Leader shall determine and report wind direction and speed at Lehua Island, beginning no later than one hour before, hourly during, and one hour after each application is made.  Wind reports will be communicated to the Assistant Incident Commander and the Incident Command Team.

If the wind speed at time of measurement exceeds 25 MPH (21.7 knots) all application shall cease, pause or be delayed until such time that the wind speed no longer exceeds 25 MPH (21.7 knots).   The Baiting Operations Chief is responsible for recording wind reports and determining the appropriate course of action.

## Off -Island Support

A designated off-island support person will be positioned at Lihue during aerial baiting, to serve as off-island support for the aerial operation (Logistics/Biosecurity Support Kauai). The main responsibility of this position is to respond to and coordinate response to emergency situations and urgent mechanical or operational incidents.

# EFFICACY MONITORING

As part of the larger Lehua Island Rat Eradication Project, parallel activities will be carried out leading up to, during, and after the bait applications to provide information relevant to the success of the operation, and to inform if what is observed is in line with the expected outcomes as outlined in the Environmental Assessment (EA).

The monitoring programme for Lehua Island needs to consider two important factors:

Challenging terrain, which can impact the quality of the baiting operation (i.e. complete and consistent coverage) as well as limit staff operational capacity. Despite its relatively small size (112 ha, 212 m high), Lehua is very steep, has vertical cliffs, and the sharp volcanic rocks make it difficult, unsafe or time-consuming to access certain areas even when wearing boots with micro-spikes.

Limited infrastructure on the island, which restricts the size of the field team. The campsite (a “Weatherport” enclosed shelter) is located close to the shore and is small (max capacity 4 people) in terms of both sleeping and storage capacity. Others could be present for limited periods, for example around the baiting days. The monitoring proposed is then to be mainly conducted by an experienced 5-person team stationed on the island for up to 6 weeks (starting up to 1 week prior to the commencement of baiting).

The value of continuity with monitoring team members is recognized, therefore personnel changes will be managed to maximise continuity throughout the operation. This will help minimise any individual biases, and will also minimize down time with training or getting familiar with the island. Some activities, pre-operational sampling and radio collaring rats will commence days before the implementation of the eradication, as described below. An adaptive management approach will be applied throughout; activities will be combined as much as possible to maximize efficiency.

## Logistics

A camp site will be assembled by the Weatherport on Lehua island. The camp site will consist of tent platforms and a 20x 20 tent. All gear will be transported to Lehua on the Niihau Ranch LCM landing craft. The Weatherport will be used for food preparation and storage.

All archeological sites previously identified on Lehua will be flagged using flagging tape, except for those with difficult access that could pose undue risk to the Lehua team members and/or undue disturbance to wildlife. Exceptions will be documented.

## Bait density and availability

On the ground monitoring will be undertaken to try and ensure that all individual rats are put at risk by the eradication strategy. Specifically, that bait is present in every rat territory in enough quantity and for long enough that all rats have access to a lethal dose. Bait availability plots will be used to evaluate the application rate (pellet density), and bait consumption/degradation over time. The data collected will be used to inform the bait application strategy and may trigger responses to ensure adequate bait quantities are continually available (i.e .trigger a subsequent bait application to occur sooner than currently planned) or possibly to adjust the bait application rate for the subsequent application. Data will continue to be collected for until 10 days after the final (third) application of bait.

### Study plots

The detailed bait availability monitoring, measured in plots, will provide data on bait availability throughout the project and an estimate of bait density achieved on the application day.

Three meter radius (28.3 m2) circular bait availability plots will be established within rat habitat areas which are representative of rat territories.  Approximately 40 permanent circular plots will be marked in advance with chalk or stakes and string across the island: 20 in each slope, including varying altitudes and suitable rat habitat types (bush and grass). This design will allow the analysis of slope (north or south), altitude and habitat as potential factors influencing bait availability.

The location of the plots will be selected rather than random, as large expanses of bare ground, although proportionally abundant on Lehua, will be avoided. Bare ground provides neither cover nor food for rats, and it is likely that bait availability there will be lower due to steepness of the terrain. In other words, bait will be measured where rat activity is most likely. The plots will be distributed along transects when possible (Figure 7) to facilitate logistics.

Each plot will have an individual code and will be monitored every 24 hours in a consistent order. Each observer will monitor 10 plots daily (five at each slope). At each plot, pellets will be collected, counted, weighed collectively using a Pesola scale and collectively assessed for bait degradation on the Craddock (2004) scale before being placed back within the same plot.

Plots will not be cleared in between each application and will measure cumulative pellets observed throughout the duration of the three bait applications.

Additionally, observers will visually evaluate if the general bait density matches the density measured inside the plots. This is necessarily a subjective process, but it would allow the team to validate the extrapolation to larger areas.

Figure 7. Example of monitoring plots (40 circles) along the inner and outer slopes in the two main rat habitats: shrub and grass. The line indicates the transect for the live traps to be set both before and after the operation.  Actual distribution will depend on current vegetation coverage.

### Bait Density Analysis

By evaluating bait availability on the day of the drop the on-the-ground bait application rate can be confirmed, and the values can be used as the basis upon which to start estimating daily bait consumption. A similar regime will be used after each bait application unless this process is found to be ineffective. All observers will be trained on the practical definition of ‘pellet’ to ensure systematic monitoring.

### Bait Availability Analysis

Bait densities will be monitored within bait availability plots by collecting data on the total weight of pellets in each plot over time. The 99% confidence interval lower limit (99 CI LL) of bait availability will be calculated for each day based on daily bait density data.  The rate decrease will be estimated by calculating the linear trend of the 99% confidence interval lower limit over the first four days following each application.

### Reporting and Operational Response

The Lehua Team Leader will provide daily reports of efficacy and environmental monitoring data to the Assistance Incident Commander and the Incident Command Team.  This will include, but not limited to:

- Raw daily bait density data from each plot

- Status and fate of radio collared rats

- Anecdotal observations of bait density around the island

- Weather and environmental conditions observations

- Non-target species carcass collection

Reported data and observations will be used to inform operational decision making.  Bait densities are expected to decrease over time because of consumption and/or degradation at a rate of 2 Kg/ha/day on the higher productivity areas (as per 2015 bait trial). If the rate decrease is equal or greater than 3 Kg/ha/day, or daily 99 CI LL bait densities are below 8 Kg/ha, the Incident Commander will initiate a discussion about adjusting the interval between bait applications to ensure bait is continually available.

## Impacts on target species

Efficacy of the bait applications will be evaluated with a pre/post bait application monitoring protocols using multiple indicators.  In the short term, efficacy of the baiting will be evaluated with radio collared rats monitored pre/post baiting until mortality (or not) is confirmed. In the longer term, rats will be monitored using direct and indirect detection tools. All tools used have been tested on the target population on Lehua before the operation, and monitoring will be conducted every 3-6 months for 1-2 years.

### Pre-operation

Prior to the first bait application, up to 15 rats will be fitted with radio-collars. To capture rats, approximately 30 live traps will be set and baited using coconut bait in high quality rat habitat near the camp site. Ideally, a balanced sex ratio and a range of age classes and breeding status will be targeted. However, animals in reproductive condition and juveniles will be preferentially collared because there is limited data on bait acceptance by these groups. Individuals will be fitted with the radio-collars and released at the capture site.

Capture success rates will be calculated from the live traps and will be used to assess population status prior to the eradication. Additionally, body condition, morphometrics, and phenology data will be collected from captured rats.

Radio-collared rats will be monitored for 1-2 days prior to the first application to ensure they are alive and to identify burrow locations. Motion trigger cameras will be placed at the entrance of identified burrows to document bait acceptance and social interactions as well as survival (i.e. lack of activity) during the operation.

### During operation

Radio telemetry monitoring will commence five days after the first bait application and will continue until all collared rats are confirmed dead. All rats will be monitored every other day around sunset to check for movement. Once an individual is suspected to be dead, the site will be marked with GPS, and a recovery operation will be carried out as soon as possible.

Recovery may involve digging/moving rocks. Staff will be informed of all archaeological or other sensitive sites which are not to be disturbed. If dead rats are found to be within these areas, the monitoring team will only attempt to recover the radio collared individual if it does not compromise the site.

Body condition, morphometric, and phenology data will be recorded for all recovered radio collared rats. Additionally, fresh carcasses will be collected to assign cause of death and for toxicology analysis.

### Post-operation

If logistics allow, suitable passive detection devices which may include chew cards, wax tags, and tracking tunnels will be deployed on Lehua after the third application to get an initial indication of the efficacy of the operation. More complete efficacy monitoring/ success monitoring will be undertaken the following summer once any possible surviving rats have had the chance to breed, increasing the population to the point where there is a high likelihood of detecting them.

# NON-TARGET SPECIES

Environmental residue (water and soil) and non-target species monitoring will be led by USDA-NWRC (see protocols in Monitoring diphacinone resides after an eradication of Polynesia rats from Lehua Island, Hawaii).

## Seabird Mitigation

Prior to the first application accessible active albatross and red-tailed tropicbird nests will be mapped and recorded with a GPS.  As soon as possible after each application bait will be removed from the area directly surrounding mapped albatross and red-tailed tropicbird nests.

All monitoring crew will be briefed on procedures for avoiding shearwater burrow collapse and excavating in case of collapse.

The Lehua Team Leader is responsible for ensuring seabird mitigation is completed.

## Carcass Search

The monitoring team will perform a full-island search for carcasses prior to the start of baiting and opportunistically throughout the bait and environmental monitoring periods. This will be done by dividing the island into quadrants and staff will walk as much of the accessible area as possible while looking for bird carcasses. Staff will use a GPS to track coverage within their zone. The goal will be to get good coverage of the whole island rather than detailed coverage of a small portion of the island during this survey. Fresh carcasses will be collected to assign cause of death and for toxicology analysis.

## Reporting

The death of the following, post applications, will be reported to HDOA in compliance with the Additional Conditions to SPECIAL PERMIT TO APPLY RESTRICTED USE PESTICIDES BY AIRCRAFT:

- Ten (10) or more birds of any species,

- Twenty-five (25) or more fish of any species,

- Any endangered or threatened birds or marine mammals.

The total number and species of carcasses collected will be reported by the Lehua Team Leader to the Assistant Incident Commander and Incident Command Team.

# ENVIRONMENTAL EFFECTS

## Bait Spill Response

A bait spill response plan has been developed for this operation (see Appendix 7).  A bait spill is defined as any discharge of bait above 5Kg in a non-treated localized area.

## Fuel Spill Response

A fuel spill response plan will be provided by the Aerial Operator for responding to any spills at the refueling site.

A containment device will be used to manage minor spills of Jet A1 during refueling of the helicopter with any spilt fuel to be collected for appropriate disposal. Due to the porous nature of the substrate at the operational site and the high temperature of the operating area it is anticipated that spilled fuel will rapidly evaporate making it difficult to clean. In the event of a major spill:

- Baiting Operations Chief notifies Incident Commander

- Incident Commander notifies the land owner

- Incident Command Team considers any response or remedial actions that may be able to be undertaken.

# OPERATIONAL DATA

The following operational data is planned to be collected throughout the operation.  The following table denotes operational data and responsible party.

| Category | Data | Responsible |
| --- | --- | --- |
| Bait Application | Aerial bait tracking worksheet Operations Checklist | Baiting Operations Chief |
|  | Aerial application windspeed worksheet | Assistant Incident Commander |
|  | Tracmap GPS flight path data | GIS Specialist |
|  | Toxic Bait Samples | Bait Loading Leader |
|  | Ground baiting application worksheet GPS locations of bait stations and baited structures GPS locations of hand broadcast points | Lehua Team Leader |
| Efficacy Monitoring | GPS data of bait uptake plot locations Daily bait density data for bait uptake plots Rat radio collar tracking data Rainfall data | Bait Uptake Monitoring Officer |
| Environmental Monitoring | GPS data of flagged archaeological sites GPS data of active albatross and red-tailed tropic bird nests GPS tracklogs of carcass search effort GPS locations of collected carcasses Carcass collection data | Lehua Team Leader |

# SAFETY

Human safety is paramount for the Lehua rat eradication operation. The purpose of this Safety Plan is to identify potential safety hazards, as well as the mechanisms by which these hazards will be managed and assign responsibilities and accountabilities for safety management, as well as to clearly define the Emergency Incident Action Plans for Lehua and Niihau.

## Hazards and Hazard Management

To ensure safety, all field personnel will comply with the following operational practices to reduce risks of illness, injury, death and property damage.

| Description of hazard | How hazard will be managed |
| --- | --- |
| Physical Hazards |  |
| General. General tasks to implement project activities pose physical hazards including slips, trips. | - All personnel will use precaution at all times. - Hiking boots with adequate ankle support is the preferred footwear for the Niihau Operational Team and is required for the Lehua Monitoring Team. - Micro spikes are required for all personnel climbing steep slopes on Lehua island. - Every team members will carry a radio and additional battery pack when working independently. - Personnel are not to place themselves at undue risk by working outside their comfort zone or on steep areas which are unsafe (to be determined by the Lehua team leader and the personnel involved) or near to cliff edges. |
| Pesticide/Rodenticides. Diphacinone, a first generation anticoagulant, will be present in the rodent bait (50ppm) applied on Lehua. Personnel could be exposed to diphacinone if handling bait or bait bags, loading spreader buckets, or moving around the island after bait is applied. Diphacinone is primarily absorbed through the gastrointestinal tract, but can also be absorbed although to a lesser extent through inhalation and skin contact. | - All personnel must read and understood the Material Safety Data Sheet for DITRAC D50 (see Appendix 1 below) before commencing work on the project. - All staff involved in handling open bait bags must wear the appropriate PPE; overalls, gloves, covered footwear, and eye protection. Half faced respirators will be worn by staff working under the helicopter. In other situations, dust masks will be worn if exposure to dust is a possibility. - Bait bags will be secured at the load site and will not be re-used for any other purpose. - Protective clothing and equipment will be removed and hands/arms/face thoroughly washed at the end of a task or before eating, drinking, or using the toilet. - Food and water supplies will be covered during bait application. - Only designated staff will be in the vicinity of the bait loading site. |
| Helicopters. The use of a helicopter poses inherent risks. | - Access to the helicopter landing area will be restricted to personnel directly involved with tasks that require their presence in this area. - All personnel working under helicopter will wear protection helmets. - All personnel involved in helicopter operations will receive a helicopter safety briefing prior to commencing work on the project. - Refer Appendix 3 Helicopter safety plan. |
| Fire. Project activities or natural phenomena can cause fires in dry environments such as Lehua and Niihau. | - Areas for evacuation will be identified and included in personnel briefings. - Should a fire occur on Lehua, personnel will retreat to the coastline into areas with few burnable fuels or, if necessary/possible, evacuate the island completely. - Should a fire occur on Niihau, personnel will move away from fuel storage area, retreat to the coastline into areas with few burnable fuels (e.g. beach) or, if necessary/possible, evacuate the island completely. - Personnel should attempt to put out a fire if they can do so without putting themselves at risk. - Incident Command Team should be notified immediately of all fires. |
| Sun Exposure. The operation will be conducted during the summer and extreme heat conditions are expected. Sunburn is a likely if no protective measure are taken. | - All personnel are encouraged to use a commercial sun-block with a minimum solar protection factor (SPF) of 30 and reapply frequently. - Further protection measures include sunglasses, a wide-brimmed hat, and protective clothing/accessories (long sleeved shirt) to avoid sunburn. |
| Heat Stress. The operation will be conducted during the summer and extreme heat conditions are expected. Heat stress is a potential hazard, particularly to non-acclimated personnel. | - All personnel will drink sufficient water, wear a wide-brimmed hat, take shade breaks, and be conscious of how they feel and the condition of others. - If heat exhaustion is suspected, first aid procedures for this condition will be implemented immediately. |
| Dehydration. The operation will be conducted during the summer and extreme heat conditions are expected. Dehydration is a potential hazard. | - All personnel will drink plenty of non-alcoholic, non-caffeinated fluids to maintain hydration (water is best). - When working in the field, personnel will carry enough water to last all day plus extra. - The recommended amount of water consumption is 3 to 4 litters per day. - During sustained hard exercise, especially in hot environments, 8 oz. of water every 20 minutes is the recommended amount. |
| Hand tool use. A variety of hand tools, including machetes, hammers etc. may be used during the Lehua operation and pose inherent injury risks. | - All personnel will wear relevant PPE to protect themselves from injury. - All personnel will work at least three meters apart when using hand tools. - Duties will be shared to avoid fatigue related or repetitive motion injuries. - Personnel will only use tools for which they are suitably experienced with or under guidance of an experienced operator. |
| Biological Hazards |  |
| Centipedes are present on both Lehua and Niihau. They are venomous and cause painful bites. Honey Bees could be present on both Lehua and Niihau and cause painful bites and stings. Anaphylaxis is a potential hazard for personnel with a history of allergic reactions. | - Personnel will check ground ahead when moving across the island or before placing hands and sitting down. - Personnel will check personal tents and gear daily for the presence of centipedes. - Epi Pen and antihistamines will be based on both islands and stored within the med kit. - If individuals have a history of allergic reactions to insect bites/stings they will alert others in advance and keep an Epi Pen and antihistamines within their field pack. |
| Disease |  |
| Rats. Rats are known to carry a variety of diseases. Leptospirosis and murine typhus are the most likely that could occur on Lehua and Niihau. | - All personnel will use gloves to handle any live rats or rat carcasses. - Hands and contaminated surfaces will be washed well after handling. - Eating or drinking will be avoided while wearing PPE. - All personnel will wash hands thoroughly and frequently, for 15-20 seconds with soap and hot water after handling rats and rat carcasses. |
| Tetanus. It is caused by a prevalent bacteria species, likely present on Lehua and Niihau. | - All personnel must have a current tetanus vaccine. - If injurie such as cuts and lacerations occur from rusted tools and equipment, personnel will monitor for symptoms and consult a doctor through their respective remote medical service if necessary for potential treatment. |
| Boats and Island landings |  |
| Boat use. Boating during project activities poses inherent risks including injuries, Carbon Monoxide poisoning, and drowning. | - Weather and sea conditions will be checked prior to departure. - Personnel travelling in small boats will wear life jackets and these will only be removed once onshore. - All personnel will follow the instructions of the boat captain and staff. - Hands and limbs will be kept inside the boat when approaching shore. - Back packs will not be worn when disembarking and embarking. - Load and people limits will be respected. |
| Island Landings. Access to Lehua can be challenging, especially in rough sea conditions. Crushing injuries, concussion, cuts and drowning are possible. | - All personnel will use caution at all times. - Flotation devices (e.g. paddle boards) will be used to ensure safety when necessary. - Access to sea caves for baiting will only be done in suitable sea conditions and will include an observer with a radio outside the cave at all times. |
| Campsite |  |
| Food preparation. Cooking with campsite equipment poses inherent risks, including burning and scalding with hot foods and water. | - Common sense and care while cooking will prevent injuries during cooking. - The gas cooker will be operated in a well ventilated area and clearly marked as hot if recently used. |
| Food safety. Lack of proper ways to store cooked, unconsumed foods poses a risk of food poisoning. | - Cooked or unpreserved foods will be consumed immediately and will not be allowed to spoil. - Spoiled food will be disposed of appropriately. |
| Food contamination. Handling of food without proper hygiene can lead to food contamination. | - Personnel will wash hands and use antibacterial gel and wipes before handling food. - Kitchen tools and utensils will be appropriately cleaned and stored. |
| Flammables. Propane camp stove will be used on Lehua and are flammable and present a fire hazard. Helicopter fuel will be stored at the Niihau camp area and present a fire and poisoning hazard. | - Fuel will be stored away from cooking areas. - No smoking is allowed on Lehua or Niihau. - All hazardous material will be stored in appropriate containers. - Tops/lids will be placed back on containers after use. |
| Alcohol and drugs. Due to the dangerous nature of working on islands with environmental and operational hazards, alcohol and drugs can be related to significant risks and will therefore not be consumed on islands. | - Project personnel will not consume alcohol or non-prescribed drugs while on Lehua and Niihau. Violation of this policy could lead to the removal of personnel from the project. - If staff are on prescribed drugs, they should notify the respective Safety Observer if there are side-effects or symptoms related to the medication or condition that may jeopardize their or other’s safety. |

## Safety roles and responsibilities

All field personnel involved in the Lehua rat eradication operation will be briefed on the contents of this safety plan and will be given ample opportunity to question and clarify procedures prior to the commencement of field activities.

Safety is the responsibility of all project personnel. Project personnel should not participate or support activities that they deem unsafe, and should work to modify or change unsafe operations so that risk can be sufficiently reduced to themselves and others. It should be understood and respected that an individual’s comfort with a situation may be different than your own. In the event that an activity or proposed tasks is not mutually agreed upon, it will be up to the respective island’s Safety Officer to resolve the situation. Any activities which any team member deems to be unsafe must be raised with the team member’s direct supervisor as soon as practicable; if the supervisor does not allay the concern the team member should raise the issue with the First Aid Responder.

In addition to the safety responsibilities described in the roles of each ICS team member, First Aid Responders and back ups are identified for each island as follows:

| Position | Name | Safety Responsibility |  |
| --- | --- | --- | --- |
| First Aid Responder Niihau | Wes Jolley – Primary First Responder Tommy Hall – Back up First Responder | Responsible for coordinating medical emergencies |  |
| First Aid Responder Lehua | Mele Khalsa – Primary First Responder Dean Foster – Back up First Aid |  | Responsible for coordinating medical emergencies. |  |

### Safety briefings and trainings

All personnel involved in the implementation of the Lehua rat eradication will be provided with an orientation and safety briefing prior to deployment. Additional safety briefings will be held on site as deemed appropriate for specific activities e.g. bait loading, by the First Aid Responder on each island.

Staff involved in specialist activities such as working around helicopters will be appropriately experienced or receive training prior to deployment; in addition staff will be provided safety briefings.

Personnel safety briefings will include:

- Emergency Incident Action Plan - Personnel will understand the lines of authority regarding health and safety, as well as personnel roles and responsibilities.

- Personal Protective Equipment (PPE) - Personnel will be informed of the level of personal protective equipment required on site and/or for specific activities, and the appropriate use of PPE.

- Special Hazards - Personnel involved in higher risk operations such as working around helicopters or pesticide handling will be briefed on appropriate techniques to be used, and precautions to follow. All personnel handling rodent bait will be informed about the potential routes of exposure, the necessary protective clothing, precautionary measures, and signs or symptoms of exposure.

- Communication Methods - Personnel will be informed of normal and emergency communications plans including the location and operation of cellular phones, satellite phones, hand-held and base station radios.  All personnel will be briefed in radio protocol, etiquette, and check in schedules.

### Medical supplies and services

First Aid Responders will manage an advanced first aid kit capable of providing temporary treatment and basic emergency first aid on both Lehua and Niihau islands. Individuals that require personal items based on pre-existing conditions, such as Epi-pens for allergic reactions and prescription medication, are responsible for bringing needed items. In addition, each Lehua team member is responsible to carry a compact first aid kit issued to them for use away from camp. Each kit contains supplies intended to stabilize minor wounds and treat medical issues until the person can get back to camp.

Island Conservation employees and contractors have continuous telephone access to emergency physicians experienced in the delivery of remote medical care in environmental extremes via Remote Medical International. All employees and contractors can coordinate with the First Aid Responder on island to call for medical advice, but use of prescription medication requires authorization by a physician. Contact the Island Conservation HR manager for assistance in obtaining the most recent description of benefits.

All Island Conservation employees and contractors, as well as Lehua field staff, will be asked to complete a voluntary medical history form with emergency contact information.  This will be kept confidential by the First Aid Responder and only used to inform higher medical personnel if evacuation is necessary.

### Reporting and Workers’ Compensation (For IC staff only).

In the event of any injury, the employee is responsible for:

- Seeking care as applicable.  If the care is first-aid only, seeking no outside care (RMI, medical clinic, etc) then no reporting is necessary.

- If the injury requires outside care, including consultation with RMI that results in treatment, the employee notifies their direct supervisor, and / or the Island Conservation off-island contact. This needs to occur as soon as possible without jeopardizing the well-being of the injured person.

- The direct supervisor is responsible to notify Island Conservation’s Point of Contact, but best practice is for the injured person (or someone working with them if the person is unable) to notify the Island Conservation’s Point of Contact as well.

- The Island Conservation Point of Contact will guide the workers compensation claim process (or equivalent process depending on employee’s country of residence), if applicable.

- The IC Point of Contact must be alerted to any injury covered in item b as soon as logistically possible.

## Emergency Incidents

Because of the complexity of eradication work and the multi-agency participation, operational staff will work under an Incident Command System (ICS) organizational structure. For the purposes of this project, normal aerial baiting operations will be considered an “Incident” and any emergency that might occur during the operation will be considered an “Emergency Incident”.

In the event of a significant emergency Incident, roles within the existing ICS structure will be reassigned to activate new roles as needed. The Incident Commander is responsible for activating Emergency Incident roles; roles will be activated depending on the incident complexity, experience, training and the judgment of the incident – not all roles may be activated in an incident and not all roles may be activated at the same time.

In the event of an Emergency Incident, all activities should be temporarily suspended (stopped) until the incident is fully understood.

### Operational responses to an Emergency Incident

Several options are available for suspending operations:

- Continue as Normal: If the incident does not drastically impact or impede the continuation of the operation, Incident Commander will assign specific tasks to personnel as needed.

- Slow Down: Some or all aspects of implementation may need to be slowed down but can occur while other actions are being carried out, e.g. due to temporary loss of machinery which slows bait loading or application, re-assignment of personnel to non-serious emergency, etc.

- Time Delay: A time delay can be implemented for a specified amount of time needed, e.g. to complete minor repairs, weather changes, etc.

- Indefinite Time Delay: A delay may be needed for an unspecified amount of time, for repairs, weather, etc. Personnel should remain ready and standing by.

- Postpone: If operation is unable to continue and cannot resume the same day, e.g. a forecasted storm system, serious mechanical failure, legal issues, etc.

- Full stop:  Should be implemented for any incident with a high or potentially high level of seriousness, for example when:

- Life threatening situations arise.

- The situation becomes completely uncontrollable and dangerous.

- The nature of the situation requires it.

- The situation requires a safe and thorough assessment.

- An emergency response requires activities to temporarily cease.

### Evaluating the appropriate Emergency Incident response

A general approach to an emergency situation should proceed as follows:

- Report the incident to the appropriate Safety First Responder.

- Safety First Responder moves the notification through ICS to Incident Commander.

- Incident Commander decides on course of action (Full stop or Delay).

- Response to situation should be developed based on response protocols available.

- Appropriate actions should be taken in a safe and timely manner. This may include assignments of personnel by the Incident Commander.

- When incident is resolved, Incident Commander consults with the Operations Advisory Group to enable operations to proceed.

Slow-down Emergency Incidents: Examples that may not require immediate Full

Personnel Injury

- Non-life threatening injury at staging site or bait loading site caused by heavy machinery, lifting heavy equipment, etc.

- Non-life threatening injury or illness such as heat exhaustion, dehydration, fainting, or allergic insect sting, etc.

- Non-life threatening injury such joint or muscle injury, fractured or broken limb, falling, burns etc.

- Non-life threatening injury or illness from HazMat use (rodent bait, ant bait, fuel)

- Minor illness (asthma, headaches, cold, flu, digestive problems)

Equipment Failure

- Mechanical failure or breakdown

- Helicopter mechanical failure or breakdown

- Spreader bucket malfunction

- Equipment malfunction or breakage (e.g. GIS)

Bait or Fuel Spill

- Incidental bait spill at staging site or bait loading site

- Incidental fuel spill at staging site or bait loading site

Operational Issues

- Over-baiting

- Insufficient bait available

Full-Stop Emergency Incidents: Examples of Emergency Incidents that require an immediate Full-Stop

- Helicopter set-down

- Helicopter crash

- Overdue aircraft

- Boat crash

- Overdue boat

- Personnel evacuation

- Bait bucket (empty or with bait) dropped into sea / onto land

- External cargo load dropped into sea / onto land

- Earthquake/Tsunami alert

- Life threatening injury

## Communications

Off island contact will be maintained during all stages of project implementation and monitoring.

| Organization/Agency | Off-Island Point of Contact | Phone Numbers |
| --- | --- | --- |
| DOFAW Kauai | Lindsey Ibara | 808-645-1649 |
| DLNR (for Mike Walker) |  |  |
| PCSU (For Patrick Chee) | David Duffy | 808-956-8218 (office) 808-754-6299 (cell) |
| USDA | Shane Siers or Lei Costales | 808- 961-4482 x34 (SS office) 808-209-1459 (SS cell) 808-319-7808 (SS cell) 808-961-4482 x22 (LC office) 808-747-2001 (LC cell) |
| USFWS | Domingo Cravalho | 808-792-9445 (office) 808-221-9667 (cell) |
| Island Conservation | Jonathan Steinberg | 831-359-4787 (office) 831-247-2323 (cell) |
| HDOA (For Scott Enright) |  |  |
| Pacific Helicopters | office | 808 871 9771 |

# OPERATIONAL BIOSECURITY

Biosecurity refers to the policies and protocols designed to prevent the introduction and spread of invasive alien species (IAS). This plan includes all activities associated with preventing new invasive species introductions to Lehua and Niihau as a result of the rat eradication operation.

## Purpose

The purpose of this biosecurity plan is to provide guidelines to implement an effective eradication operation while safeguarding Lehua island and the staging site on Niihau from the introduction of novel IAS.

## Operational Biosecurity Measures

Protocols and guidelines for biosecurity will be implemented in all three operational phases of the bait application: pre-operational, during operations, and post operational. The categories that encompass all the activities included under this biosecurity plan are: storage and transportation, people and personal gear, and field camps. Specific responses take the form of physical removal of organisms or plants or the use of readily available insecticides and traps.

### Pre-operation – all activities prior to first bait application

| Category | Activity of Risk | Mechanisms of exposure | Mitigation | Response |
| --- | --- | --- | --- | --- |
| Storage + Transportation | Bait shipment and storage on Oahu and Kauai | Infestation of shipping container | - Limit duration of container doors being open. - Place sticky traps inside the container. | Remove any organisms found inside container (pesticide, trapping, etc) |
|  | Buckets shipment and storage | Infestation of bucket crates | Limit access time | Remove any organisms found inside the crate (pesticide, trapping, etc) |
|  | Equipment and supplies shipment and storage | -Infestation of packaging or items at origin or in transit. -Infestation at storage site. | -Inspect upon arrival -Inspect storage areas/units. -Place sticky traps at storage site. | -Remove any organisms found on equipment and supplies packaging and in storage areas (pesticide, trapping, etc). -Eliminate infested equipment and supplies that cannot be cleared. |
|  | LCM operations | -Infestation of the vessel | -Implement biosecurity protocols from Niihau Ranch -Visual check by implementation staff. -Closely watch loading and unloading operations. | -Remove any rodents and plant propagules encountered. |
|  | Small boat operations | -Infestation of the vessel | -Inspect the vessel | -Delay operation until all organisms of concern are removed. |
| People + personal gear | People and personal gear presence on Niihau and Lehua | -Gut resistant seeds -Infestation of personal gear | -Implement guidelines for fruit consumption prior to operation. -Use the sanitary facilities on Lehua and Niihau. -Self declared inspection by every team member of all personal gear following specific protocols. | -Remove any organisms encountered. -Eliminate infested gear that cannot be cleared. |
|  | Boat charter operations | -Infestation of gear in transit | -Visual external inspection of gear prior to transfer to Lehua | -Delay transfer until all organisms of concern encountered are removed. |
|  | Niihau helicopter operations | -Infestation of gear in transit. | -Visual external inspection of gear prior to transfer to Lehua. -Inspect external parts of helicopter. | -Delay transfer until all organisms of concern encountered are removed. |
| Camp + logistics | Food and water | -Infestation of food and water containers. | -All fresh food is thoroughly washed. -No fruits with viable seeds are to be brought to the island. -All food is kept in rodent resistant containers. -Water containers are sealed to avoid drip. | -If able, remove organisms of concern. -If too widespread (e.g. ants, cockroaches, etc) seal container and dispose of it as soon as possible. |
|  | Waste management | Infestation of waste from camp activities and the organisms spread by field staff | All waste food and food containers must be collected in garbage bags, sealed, and removed from the island. | -If able to, remove organisms of concern. -If too widespread (e.g. ants, cockroaches, etc) seal container and dispose of it as soon as possible |

### During operation – all activities between the first and final bait applications

| Category | Activity of Risk | Mechanisms of exposure | Mitigation | Response |
| --- | --- | --- | --- | --- |
| Storage + Transportation | Niihau storage area | Infestation of shipping container | - Limit duration of container doors being open. - Place sticky traps inside the container. | Remove any organisms found inside container (pesticide, trapping, etc) |
|  | Helicopter from Maui | Infestation of interior space or equipment (fuel pumps etc) and exterior structures | Visual inspection of interior, exterior and all equipment prior to departure from Maui by the pilot | Delay departure and remove any organisms. |
|  | Bait bucket operations between Niihau and Lehua | No biosecurity inspection of buckets prior to air operations | Consistency in biosecurity inspections at the landing zone | Delay helicopter departure and remove any organisms observed |
| People + personal gear | People and personal gear presence on Niihau and Lehua |  |  |  |
|  | Niihau Ranch helicopter operations | -Infestation of gear in transit. | -Visual external inspection of gear prior to transfer to Lehua. -Inspect external parts of helicopter. | -Delay transfer until all organisms of concern encountered are removed. |
| Camp + logistics | Food and water | Infestation of food and water containers. |  |  |
|  | Waste Management |  |  |  |

### Post-operation

| Category | Activity of Risk | Mechanisms of exposure | Mitigation | Response |
| --- | --- | --- | --- | --- |
| Storage + Transportation | LCM operations | -Infestation of the vessel | -Implement biosecurity protocols from Niihau Ranch -Visual check by implementation staff. -Closely watch loading and unloading operations. | -Remove any rodents and plant propagules encountered. |
|  | Small boat operations | -Infestation of the vessel | -Inspect the vessel | -Delay operation until all organisms of concern encountered are removed. |
|  | Niihau Ranch helicopter operations | -Infestation of external areas of the helicopter | -Inspect external parts of helicopter. | -Delay transfer until all organisms of concern encountered are removed. |

## Bait Shipment

- Bait pods will have the lids secured with straps and shrink wrapped to help prevent rodents or insects from accessing the bait

- The shipping container should be in new or like new condition with no holes. Door seals should be intact. Shipping containers will be locked whenever the doors are closed.

- Glue traps (large enough for rodents) will be placed inside the container, at least one at each corner. A smaller glue trap can be placed on top of the liner bag inside each pod to catch any insects.

- Efforts will be made to minimize the frequency the shipping containers are opened.

- Shipping containers will never be left open and unattended.

- Shipping containers will, if possible, be stored in open areas, away from sources of pests like garbage piles, areas of thick vegetation, etc.

- Additional items will not be added to the shipping container (e.g. as a way to get some gear from Kauai to Niihau, or in between bait drops), unless it has been thoroughly inspected and cleared of biosecurity threats.

- If a partial container load of bait is left-over between applications, the container will receive a thorough inspection (including making sure sticky traps are in place) before the container is closed, and again upon opening. All bait bags will be packed in a pod with space and it will be tightly closed. The container will be swept clean so that stray pellets don’t serve as a potential food source to attract pests. (before closing this is another possible time to spray some insecticide).

- Sticky traps will be checked whenever practical (e.g. traps near the door checked when inspections occur, traps in back checked during unloading.). Any detection of a pest will prompt further action as deemed appropriate. A single small insect may not prompt any response, while a rodent or serious number of ants may prompt a thorough inspection to scope out any infestation or damaged bait.

- The outside of the container will be inspected in Kauai before loading for transport to Niihau, and again at arrival to Niihau. Biosecurity officers will pay particular attention to the bottoms and crevices.

## People and Personal Gear

- Avoid utilizing used shoes, clothing, soft sided bags; mud, dirt, seeds, insects etc. could be attached in treads, soles, laces, seams, cuffs, pockets, and folds.

- Avoid clothes or other equipment with Velcro or fabrics with similar textures that could trap and hold seeds.

- Fumigate the equipment to kill insect pests prior to departure.

- Do not use corrugated cardboard to store food or equipment (older cardboard represents a higher risk).

- Clean and inspect all clothing, shoes, and fabrics.

- Physically remove all traces of mud and seeds.

- For soft items, if difficult to clean entirely, place in a freezer for 48 hours before leaving for the island.

- Pack all items at one time; do not leave bags/boxes open overnight or for an extended time period as this is when invertebrates, geckos, and seeds can enter. Securely close each bag/container after each item is added.

- Pack bags/boxes/containers in a clean, preferably enclosed, area away from the risk of wind-blown seeds, and insects. Packed bags should be placed in a designated area away from the threat of collecting seeds, invertebrate, and reptile pests.

- All boxes, containers, bags, etc. will be closed tightly /sealed to minimize opportunities for animals to hide inside.

- All cargo, clothing, boots etc. must be clean and free of invertebrates, mud, debris and seeds.

- Items including clothes, backpacks, sleeping bags, etc. should be freshly washed and not worn or used elsewhere prior to travelling to the island.

## Transportation

- The members of any party accessing Lehua will ensure that any vehicles (boats, helicopters) going to Lehua are inspected for animals and seeds prior to loading and before departure. Larger boats have a greater chance of harboring rodents. It may be necessary to implement rodent control measures (such as bait stations) well in advance of departing for the island.

- When contracting or chartering boats, agreements should include the right to inspect the vehicle and/or require necessary preventative measure be in place.

- Members of any party accessing Lehua will ensure that all cargo is inspected immediately before loading onto the boat/helicopter. Particular attention will be placed on high-risk cargo such as food, timber, fabric, and other items that may attract or hide non-native species.

- The helipad provides a good opportunity to see and capture any unintentional escapes during unpacking. Gear should be unpacked in the open on the helipad. If anything is found while unpacking, capture and dispose of it. If possible, a can of insect spray should be available to deal with any invertebrates that may be found while unpacking.

- Rodent bait stations and/or traps should be maintained around the point of entry or the duration of the visit.

## Waste Management

Human food sources such as garbage, food scraps, and perishable food items increase the chances of inadvertent seed dispersal and also provide food resources for non-native species, if present. For this reason, all waste food and food containers must be collected in garbage bags, sealed, and removed from the island. In addition, the campsite, especially the kitchen area, must be kept clean and all food scraps removed from the ground and the stove.

  - All garbage and waste perishable food must be collected on-island in sealed garbage bags, inside rodent proof containers (i.e. sealed garbage bins).

  - Ensure that all totes/Action Packers containing food are sealed tightly with lids in place; tinned food is the only packaging that rats cannot chew into.

  - Routine inspections will occur daily to assess if all rodent proofing barriers remain intact and in functional condition; signs of rodent activity will result in additional baiting actions (hand-spread or bait stations, depending on type and location of sign) in the vicinity.

  - Ensure that no food items or food wrappers remain in your backpack at night, remove to a sealed tote.

  - Do not discard any foodstuffs, empty food containers/tins/packaging into vegetation or into the sea.

  - For used dishes and kitchen utensils, scrape all remaining food into garbage bags and/or wipe with kitchen paper then wash.

  - Ensure that all kitchen utensils, pots, pans etc. are cleaned after each meal and packed in totes.

  - Clean-up and dispose of food scraps on the ground and keep the stove clean.

  - Maintain a clean and hygienic camp.

  - All staff are to remain vigilant and take action to identify waste disposal risks and remove food sources where identified.

# OPERATIONAL COMMUNICATIONS

## Lines of communication

The project is being run using a standard Incident Command System (ICS) structure which clearly lays out the lines of communication and responsibility. Unless expressly approved otherwise by the Incident Commander, all relevant communications are to follow the stated lines.

## Modes of communication

Communications between the Niihau loading site and Kauai, Honolulu and other off-island sites will be via cell phone and utilizing a satellite phone as a back-up. During baiting operations only the Incident Commander and the External Communications manager should be in contact with personnel off island. Communications within the ICS structure will be direct or via radio. Communications among the Bait Loading lead and Bait Loaders will be direct via previously-agreed-upon hand signals as all personnel will be wearing hearing protection.

Communications between Lehua and Niihau will be via radio or cell phone, using a satellite phone as a back-up. During field operations only the Lehua Team Leader should be in contact with the Assistant Incident Commander (off island). Communications among the Lehua field team will be direct or via radio.

### Satellite phone

Lehua - satellite phone number (8816-326-33587) and the satellite network phone number (1-480-768-2500)

Niihau - satellite phone number (8816-325-36557) and the satellite network phone number (1-480-768-2500) (**).

**To connect to a satellite phone:

Using a cell phone to call the 12-digit number directly is often not possible (the cell phone provider won’t allow it). Instead you can provide the emergency services with the satellite network number which can be called from a cell phone.

Dial the satellite network at 1-480-768-2500. A recording will answer “Welcome to the Iridium Satellite Global Network”. Enter the Iridium 12 digit satellite phone number. If the Iridium Phone is not switched on, it will connect to voicemail. The originator will pay a long distance charge to Arizona and the Iridium Phone will be billed at $1.99 per minute regardless of rate plan.

### Radio

On Niihau for each baiting day aviation band radios will be issued to Incident Commander, Baiting Operations Chief, Helicopter Mechanic, Bait Loading Lead, and GIS Manager. Standard helicopter operating requirements, for example refuelling, will be directly between the pilot and the mechanic; all other communications with the pilot are to go through the Bait Operations Chief on aviation band: 123.45. The loading team lead and the GIS manager will also listen in on this channel to receive bait and loading information.

All field teams on Lehua, ie anyone working out of direct contact with other team members, are to carry at least one (1) radio and a spare battery when working away from the base.

All communications between teams on Lehua will be on marine channel 82a

There are two types of VHF marine radios on Lehua: ICOM and HYT. The ICOM radios will be used only by the team on Lehua island for monitoring related activities. The HYT radios will be used for communications between Lehua and Ni’ihau and for all non-aerial operation related activities.

| HYT CHANNEL | FREQUENCY |
| --- | --- |
| 1 | IC 1 |
| 2 | IC 2 |
| 3 | IC 3 |
| 4 | IC 4 |
| 5 | Marine 82a |
| 10 | Marine 10 |
| 16 | Marine16 |

All communications between the Lehua and Ni’ihau will either by radio or cell phone. All radio communications between Lehua and Ni’ihau will be on HYT Channnel 1 (IC registered freq). Communications between Lehua and Ni’ihau during aerial baiting operations will be via Lehua Team Lead and the incident commander.

### Cell phone

Lehua Camp cell phone number (808-652-6515), Lehua Team Lead cell phone); Niihau Camp cell phone number (808-358-4614), Incident Commander’s cell phone).

Additional cell phone numbers for ICS team and additional support for project are in Appendix 6.

## Public Notifications

Once the decision to proceed on the application day has been made, ie the baiting helicopter is heading to Niihau, the DOFAW public information sites ie message phone and website will be updated to reflect that the operation is very likely to proceed that day. This will be undertaken by DOFAW (Patrick Chee) at approx. 06:00.

A notice to mariners advising them to remain clear of the area to avoid hazardous interactions with operations will be issued by the USCG once the decision to proceed on the application day has been made. Patrick Chee (DLNR) is responsible for updating the USCG.

# REFERENCES

Aplin, K. P., P. R. Brown, J. Jacob, C. J. Krebs, and G. R. Singleton. 2003. Field methods for rodent studies in Asia  and the Indo-Pacific. Australian Centre for International Agricultural Research, Canberra, Australia.

Athens, J. S. 2009. Rattus exulans and the catastrophic disappearance of Hawai’i’s native lowland forest.  Biological Invasions 11:1489‐1501.

Athens, J. S., H. D. Tuggle, J. V. Ward, and D. J. Welch. 2002a. Avifaunal Extinctions, Vegetation Change, and  Polynesian Impacts in Prehistoric Hawai'i. Archaeology in Oceania 37:57‐78.

Athens, J. S., H. D. Tuggle, J. V. Ward, and D. J. Welch. 2002b. Avifaunal extinctions, vegetation change, and  Polynesian impacts in prehistoric Hawai'i. Archaeology in Oceania 37:57‐78.

Atkinson, I. and D. Towns. 2001. Advances in New Zealand mammology 1990‐2000: Pacific rat. Journal of the  Royal Society of New Zealand 31:99‐109.

Bettesworth, D. J. 1972. Rattus exulans on Red Mercury Island. Tane 18:117‐118.

Case, T., D. Bolger, and A. Richman. 1998. Reptilian Extinctions over the last ten thousand years.in P. Fiedler  and P. Kareiva, editors. Conservation Biology for the coming decade. Chapman & Hall, New York, New  York.

Clark, D. 2010. Lehua Ownership. US Fish & Wildlife Service, Honolulu, Hawai'i.  Conry, P. 2008. Re: Final Supplemental Environmental Assessment (FSEA) and Finding of No SIgnificant Impact  (FONSI) for the Lehua Island Ecosystem Restoration Project, Kauai County. Department of Land and  Natural Resources, Division of Forestry and Wildlife, Honolulu, Hawai'i.

Craig, J. L. and T. Bunn. 1989. The effects of experimental manipulation of food supplies on a population of  Rattus exulans. New Zealand Journal of Zoology 16:419‐425.

Eijzenga, H. 2011. Vegetation change following rabbit eradication on Lehua Island, Hawaiian Islands. Pages 290‐ 294 in C. Veitch, M. Clout, and D. Towns, editors. Island invasives: eradication and management.  IUCN, Gland, Switzerland.

Kier, G., H. Kreft, T. M. Lee, W. Jetz, P. L. Ibisch, C. Nowicki, J. Mutke, and W. Barthlott. 2009. A global  assessment of endemism and species richness across island and mainland regions. PNAS 106:93229327.

Lindsey, G. D., S. Mosher, S. G. Fancy, and T. Smucker. 1999. Population structure and movements of  introduces rats in an Hawaiian rainforest. Pacific Conservation Biology 5:94‐102.

Moller, H. and J. L. Craig. 1987. The population ecology of Rattus exulans on Tiritiri Matangi Island, and a  model of comparative population dynamics in New Zealand. New Zealand Journal of Zoology 14:305328.

Palmer, H. 1937. Geology of Lehua and Ka`ula Islands. Bernice P. Bishop Museum Occasional Papers XII:3‐36.

Roberts, M. and J. L. Craig. 1990. The demography of kiore, Rattus exulans in three habitats. New Zealand  Journal of Zoology 17:43‐53.  oss, F. 2009. Development of Genetic Plans For Current and Future Island Conservation Projects. Island  Conservation, Santa Cruz, California.

Scheffler, P., D. Foote, C. Forbes Perry, K. Schlappa, and C. P. Stone. 2012. Population dynamics of introduced  rodents in Hawai'i Volcanoes National Park 1986‐1990. University of Hawai'i, Honolulu, Hawai'i.

Shiels, A., C. Flroes, A. Khamsing, P. Krushelnycky, S. Mosher, and D. Drake. 2013. Dietary niche differentiation  among three species of invasive rodents (Rattus rattus, R. exulans, Mus musculus). Biological  Invasions 15:1037‐1048.

Sugihara, R. T. 1997. Abundance and diets of rats in two native Hawaiian forests. Pacific Science 51:189‐198.

Tamarin, R. H. and S. R. Malecha. 1972. Reproductive Parameters in Rattus rattus and Rattus exulans of Hawaii,  1968 to 1970. Journal of Mammalogy 53:513‐528.

Tomich, P. Q. 1970. Movement Patterns of Field Rodents in Hawaii. Pacific Science 24:195‐234.  Towns, D. 2009. Eradications as reverse invasions: lessons from Pacific rat (Rattus exulans) removals on New  Zealand islands. Biological Invasions 11:1719‐1733.

Towns, D., I. Atkinson, and C. H. Daugherty. 2006. Have the harmful effects of introduced rats on islands been  exaggerated? Biological Invasions 8:863‐891.

USFWS and DLNR. 2005. Final Environmental Assessment: Lehua Island Ecosystem Restoration Project. US Fish  and Wildlife Service and Hawai'i Department of Land and Natural Resources, Honolulu, Hawai'i.

USFWS and DLNR. 2007. Ecosystem restoration plan for Lehua Island Kauai County, Hawaii. US Fish and  Wildlife Service, Pacific Islands Office and Hawaii Department of Land and Natural Resources, Division  of Forestry and Wildlife.

USFWS and DLNR. 2008. Draft Supplemental Environmental Assessment: Lehua Island Ecosystem Restoration  Project. US Fish and Wildlife Service and Hawai'i Department of Land and Natural Resources   Honolulu, Hawai'i.

Wikisource. 2012. United States Statutes at Large Volume 45 Part 2.djvu/1314. Wikisource,  http://en.wikisource.org/w/index.php?title=Page:United_States_Statutes_at_Large_Volume_45_Part _2.djvu/1314&oldid=3569198.

Williams, J. 1973. The Ecology of Rattus exulans (Peale) reviewed. Pacific Science 27:120‐127.

Wirtz, W. 1972. Population Ecology of the Polynesian Rat, Rattus exulans, on Kure Atoll, Hawaii. Pacific Science  26:433‐464.

Wood, K. and M. LeGrande. 2006. An Annotated Checklist and New Island Records of Flowering Plants From  Lehua Islet, Niihau, Hawai‘i. BISHOP MUSEUM OCCASIONAL PAPERS 87:19‐29.

Wood, K., E. VanderWerf, C. Swenson, M. LeGrande, H. Eijzenga, and R. Walker. 2004. Biological Inventory and  Assessment of Lehua Islet, Kaua'i County, Hawai'i. Final Report Prepared for the U. S. Fish and Wildlife  Service Pacific Islands Fish and Wildlife Office USFWS Research Grant No: 12200‐1‐J014.

# Appendices

## Appendix 1.  Ditrac D-50 MATERIAL SAFETY DATA SHEET

|  | DITRAC D-50 PELLETS |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| SAFETY DATA SHEET | ACCORDING TO REGULATION: OSHA Hazard Communication Standard 29 CFR 1910.1200 |  | DATE OF ISSUE: June 2017 |  | PREPARED BY: CAR |
| SECTION 1. PRODUCT AND COMPANY IDENTIFICATION |  |  |  |  |  |
| Product Identifier: DITRAC D-50 PELLETS EPA Registration Number: 12455-147 Relevant identified uses of the substance or mixture and uses advised against Relevant identified uses: Anticoagulant Rodenticide - Ready to use Uses advised against: Use only for the purpose described above MANUFACTURER/SUPPLIER: Bell Laboratories, Inc. 3699 Kinsman Blvd. Madison, WI 53704, USA Email: sds@belllabs.com Phone: 608-241-0202 Medical or Vet Emergency: 877-854-2494 or 952-852-4636 Spill or Transportation Emergency: 800-424-9300 (CHEMTREC) |  |  |  |  |  |
| SECTION 2. HAZARDS IDENTIFICATION |  |  |  |  |  |
| Classification according to Regulation OSHA 1910.1200(d): Not classified Signal Word: None See Section 15 for information on FIFRA applicable safety, health, and environmental classifications. |  |  |  |  |  |
| SECTION 3. COMPOSITION/INFORMATION ON INGREDIENTS |  |  |  |  |  |
| Component |  | CAS No. |  | % By weight |  |
| Diphacinone [2-(Diphenylacetyl-1H-indene-1,3(2H)-dione] |  | 82-66-6 |  | 0.005% |  |
| Inert and Non-Hazardous Ingredients (Unlisted components are non-hazardous) |  | Proprietary |  | 99.995% |  |
| SECTION 4. FIRST AID MEASURES |  |  |  |  |  |
| Description of first aid measures Ingestion: Call physician or emergency number immediately. Have person sip a glass of water if able to swallow. Do not induce vomiting unless instructed by physician. Inhalation: Not applicable. Eye contact: Hold eye open and rinse slowly with water for 15 – 20 minutes. Remove contact lenses, if present, after the first 5 minutes, then continue rinsing eye. If irritation develops, obtain medical assistance. Skin contact: Take off contaminated clothing. Rinse skin immediately with plenty of water for 15 - 20 minutes. If irritation develops, obtain medical assistance. Most important symptoms and effects, both acute and delayed Ingestion of excessive quantities may cause nausea, vomiting, loss of appetite, extreme thirst, lethargy, diarrhea, bleeding. Advice to physician: If ingested, administer Vitamin K1 intramuscularly or orally as indicated for bishydroxycoumarin overdoses. Repeat as necessary as based upon monitoring of prothrombin times. Advice to Veterinarian: For animals ingesting bait and/or showing poisoning signs (bleeding or elevated prothrombin times), give Vitamin K1. If needed, check prothrombin times every 3 days until values return to normal (up to 30 days). In severe cases, blood transfusions may be needed. Component; OSHA; ACGIH; Other Limits. Diphacinone; Not Established; Not Established; Not Established. |

SECTION 5. FIRE-FIGHTING MEASURES

Extinguishing media Suitable Extinguishing Media: water, foam or inert gas. Unsuitable Extinguishing Media: None known. Special hazards arising from the mixture: High temperature decomposition or burning in air can result in the formation of toxic gases, which may include carbon monoxide. Advice for firefighters: Wear protective clothing and self-contained breathing apparatus.

SECTION 6. ACCIDENTAL RELEASE MEASURES

Personal precautions, protective equipment and emergency procedures: Gloves should be worn when handling the bait. Collect spillage without creating dust. Environmental precautions: Do not allow bait to enter drains or water courses. Where there is contamination of streams, rivers or lakes contact the appropriate environment agency. Methods and materials for containment and cleaning up For Containment: Sweep up spilled material immediately. Place in properly labeled container for disposal or re-use. For Cleaning Up: Wash contaminated surfaces with detergent. Dispose of all wastes in accordance with all local, regional and national regulations. Reference to other sections: Refer to Sections 7, 8 & 13 for further details of personal precautions, personal protective equipment and disposal considerations.

SECTION 7. HANDLING AND STORAGE

Precautions for safe handling: Do not handle the product near food, animal foodstuffs or drinking water. Keep out of reach of children. Do not use near heat sources, open flame, or hot surfaces As soon as possible, wash hands thoroughly after applying bait and before eating, drinking, chewing gum, using tobacco, or using the toilet. Conditions for safe storage, including any incompatibilities: Store only in original container in a cool, dry place, inaccessible to pets and wildlife. Do not contaminate water, food or feed by storage or disposal. Keep containers closed and away from other chemicals.

SECTION 8. EXPOSURE CONTROLS/PERSONAL PROTECTION

Established Limits Appropriate Engineering Controls: Not required Occupational exposure limits: Not established Personal Protective Equipment: Respiratory protection: Not required Eye protection: Not required Skin protection: Shoes plus socks, and waterproof gloves. Hygiene recommendations: Wash thoroughly with soap and water after handling.

SECTION 9. PHYSICAL AND CHEMICAL PROPERTIES

Information on basic physical and chemical properties Appearance/Color: Blue-green granular pellet Odor: Sweet grain-like Odor Threshold: Not applicable, odor not associated with a hazardous material. pH: Not applicable, is not dispersible with water. Melting point: Not applicable to rodenticide bait Boiling point: Not applicable to rodenticide bait Flash point: Not applicable, does not contain components classified as flammable. Evaporation rate: Not applicable, is a solid. Flammability: Not applicable, is a solid. Upper/lower flammability or explosive limits: Not applicable, does not contain components classified as flammable or explosive. Vapor Pressure: Not applicable to rodenticide bait Vapor Density: Not applicable, is a solid Relative Density: 1.27 g/mL @ 20°C Solubility (water): Not water soluble Solubility (solvents): Not applicable to rodenticide bait Partition coefficient: n-octanol/water: Not applicable to rodenticide bait Auto-ignition temperature: Not applicable, does not contain components classified as flammable. Decomposition temperature: Not applicable to rodenticide bait Viscosity: Not applicable, is not a liquid.

SECTION 10. STABILITY AND REACTIVITY

Reactivity: Stable when stored in original container in a cool, dry location. Chemical stability: Stable when stored in original container in a cool, dry location. Possibility of hazardous reactions: Refer to Hazardous decomposition products Conditions to avoid: Avoid extreme temperatures (below 0°C or above 40°C). Incompatible materials: Avoid strongly alkaline materials. Hazardous decomposition products: High temperature decomposition or burning in air can result in the formation of toxic gases, which may include carbon monoxide. NFPA; Health: 1 (caution); Flammability: 1 (slight); Reactivity: 0 (stable); Specific Hazard: None. HMIS; Health: 2 (moderate); Flammability: 1 (slight); Reactivity: 0 (minimal); Protective Equipment: B.

SECTION 11. TOXICOLOGICAL INFORMATION

Information on toxicological effects Acute Toxicity LD50, oral (ingestion): >5000 mg/kg (rats) (Diphacinone Rat LD50 oral: 2.3 mg/kg bw). LD50, dermal (skin contact): > 5001 mg/kg (rats) (Diphacinone rabbit LD50 dermal: 3.6 mg/kg bw). LC50, inhalation: Product is a granular pellet and therefore exposure by inhalation is not relevant. Skin corrosion/irritation: Not irritating to skin. Serious eye damage/Irritation: Not irritating to eyes. Respiratory or skin sensitization: Dermal sensitization: Not a Sensitizer (Guinea pig maximization test). Germ cell mutagenicity: Contains no components known to have a mutagenetic effect. Carcinogenicity: Contains no components known to have a carcinogenetic effect. Reproductive Toxicity: No data Aspiration Hazard: Not applicable. Product is a granular pellet. Target Organ Effects: Reduced blood clotting ability.

SECTION 12. ECOLOGICAL INFORMATION

Ecotoxicity Effects: This product is extremely toxic to fish, birds and other wildlife. Dogs and predatory and scavenging mammals and birds might be poisoned if they feed upon animals that have eaten this bait. Do not apply this product directly to water or to areas where surface water is present or to intertidal areas below the mean high water mark. Runoff also may be hazardous to aquatic organisms in water adjacent to treated areas. Do not contaminate water when disposing of equipment wash water or rinsate. Persistence and degradability: Product is inherently biodegradable. Bioaccumulative potential: Not determined. Diphacinone water solubility is extremely low (< 0.1mg/l). Mobility in Soil: Not determined. Mobility of Diphacinone in soil is considered to be limited. Other adverse effects: None.

SECTION 13. DISPOSAL CONSIDERATIONS

Do not contaminate water, food or feed by storage or disposal. Pesticide Storage: Store only in original container in a cool, dry place inaccessible to children and pets. Keep containers closed and away from other chemicals. Pesticide Disposal: Wastes resulting from the use of this product may be placed in trash or delivered to an approved waste disposal facility. Container Handling: Non-refillable container. Do not reuse or refill this container. [Plastic:] Offer for recycling or reconditioning; or puncture and dispose of in a sanitary landfill; or by incineration. In most states, burning is not allowed. [Paper:] Dispose of empty container by placing in trash, at an approved waste disposal facility or by incineration. In most states, burning is not allowed.

SECTION 14. TRANSPORT INFORMATION

UN number: Not regulated UN proper shipping name: Not regulated Transport hazard class(es): Not regulated Packing group : Not regulated Environmental Hazards DOT Road/Rail: Not considered hazardous for transportation via road/rail. DOT Maritime: Not considered hazardous for transportation by vessel. DOT Air: Not considered hazardous for transportation by air. Freight Classification: LTL Class 60 Transport in bulk according to Annex II of MARPOL 73/78 and the IBC code: Not applicable Special precautions for user: None

SECTION 15. REGULATORY INFORMATION

Safety, health and environmental regulations/legislation specific for the substance or mixture: FIFRA: This pesticide product is regulated by the United States Environmental Protection Agency and is subject to certain labeling requirements under federal pesticide law. These requirements differ from the classification criteria and hazard information required for safety data sheets (SDS), and for workplace labels of non-pesticide chemicals. The safety, health, environmental, and hazard information required on the pesticide label is listed below and reflected throughout this SDS. The pesticide label also includes other important information, including directions for use. Signal Word: CAUTION Precautionary Statements: Contains the anticoagulant Diphacinone which may cause bleeding if ingested. Harmful if swallowed or absorbed through the skin. Keep away from children, domestic animals and pets. Do not get in eyes, on skin or on clothing. Potential Health Effects: Eye Contact: May cause irritation Skin Contact: Non-irritating to the skin Ingestion: Harmful if swallowed TSCA: All components are listed on the TSCA Inventory or are not subject to TSCA requirements CERCLA/SARA 313: Not listed CERCLA/SARA 302: Not listed

SECTION 16. OTHER INFORMATION

For additional information, please contact the manufacturer noted in Section 1. Disclaimer: The information provided in this Safety Data Sheet has been obtained from sources believed to be reliable. Bell Laboratories, Inc. provides no warranties; either expressed or implied, and assumes no responsibility for the accuracy or completeness of the data contained herein. This information is offered for your consideration and investigation. The user is responsible to ensure that they have all current data, including the approved product label, relevant to their particular use.

## Appendix 2  DITRAC D-50 Label

## Appendix 3. Helicopter Safety Plan

Helicopter operations for this project are considered high risk.

Helicopter safety is the responsibility of every individual on the project. However mechanical safety of the helicopter is the responsibility of the helicopter vendor and flight safety is the responsibility of the pilot. The Baiting Operations Chief (BOC) will manage personnel safety, and other potential risks to the helicopter and pilot, in and around the helicopter landing zone(LZ) , i.e. the Niihau Operational Area including  the bait loading site and refueling site. The BOC will delegate specific safety management tasks to other individuals where needed and will be supported by the pilot.

Unless specified otherwise this plan relates solely to the aerial baiting operations to be undertaken by the Aerial Operator. Passenger transport operations undertaken by Niihau helicopters will be covered under the safety procedures established by that operator.

### Lehua Helicopter Operations – Supporting Documents

- Aerial Operator’s Safety Plan

The helicopter vendor will provide their Standard Operating Safety Procedures for helicopter safety management and emergency response during the operations. All safety protocols and procedures will follow the Operator’s FAA operating specifications for this project.

Five Steps to a Safe Flight

1. Pilot/Aircraft Data Card – Approved and Current

2. Flight Plan/Flight Following Initiated

3. PPE in Use When Required.

4. Pilot Briefed on Mission & Flight Hazards

5. Crew & Passenger Briefing to Include:

- Aircraft Hazards 		- Fire Extinguisher

- Seat-belt & Harness 	- Fuel & Electrical Shut-off

- ELT & Survival Kit 	- Oxygen Equipment

- First Aid Kit 		- Emergency Egress

- Gear & Cargo Security 	- No Smoking

(not under seats)

Five Steps to a Safe Flight

1. Pilot/Aircraft Data Card – Approved and Current

2. Flight Plan/Flight Following Initiated

3. PPE in Use When Required.

4. Pilot Briefed on Mission & Flight Hazards

5. Crew & Passenger Briefing to Include:

- Aircraft Hazards 		- Fire Extinguisher

- Seat-belt & Harness 	- Fuel & Electrical Shut-off

- ELT & Survival Kit 	- Oxygen Equipment

- First Aid Kit 		- Emergency Egress

- Gear & Cargo Security 	- No Smoking

(not under seats)

[OAS-103, NFES 1399, April 1997]

### Hazard Identification and Mitigation

The pilot will work jointly with the BOC to manage hazards associated with aerial baiting operations. Common hazards as well as those known hazards specific to this site/ operation for helicopter missions will be identified prior to each bait drop and controls provided to reduce risk. The BOC will assist the pilot in identifying aerial hazards and will ensure high-level reconnaissance is made prior to low-level flight if deemed necessary by the pilot.

### General Hazards Identified and Controls:

Lack of Knowledge/Experience

  - Personnel will be provided orientation and training in helicopter safety, and individual duties and responsibilities during operations.

  - All personnel at the Loading Zone are expected to have read and be familiar with the Helicopter Safety Plan.

  - The pilot and all Air Operations and Baiting Operations personnel will be briefed on the project and associated safety issues prior to operations.

  - The BOC/ Loading Team Lead will provide daily helicopter safety briefings prior to helicopter operations. The Loading team will debrief throughout operations and at the end of Each application to identify any risk areas/ areas of improvement which can then be discussed with the BOC and if agreed implemented..

Unsafe Activities at Landing Zones

  - The BOC will manage all personnel working within the Landing Zone; only personnel critical to the loading operations will be within helicopter activity zones. This zone will be marked on the ground at the operating site.

  - The Safety Officer located at the operational site will monitor general operational safety and inform the BOC if personnel are observed to engage in unsafe activities at helicopter activity zones.

  - All personnel in t the Operational Area are tasked with identifying any potential dangerous activities and notifying their direct manager or the Safety Officer promptly.

Inclement/Changing Weather Conditions

  - Daily weather forecasting and monitoring of weather conditions prior to commencing operations each day.

  - Defined maximum wind speeds for application of bait (25 mph)

  - A wind indicator will be established at the LZ. ??

Overweight for takeoff and landing

  - Maximum allowable weight limits will be calculated by the pilot at the beginning of the Operation, prior to any flights, and will updated as necessary.

  - Maximum allowable weight limits will not be exceeded.

Over-water flight

  - Crew provided with certified personal life preservers.

  - Helicopter fitted with an emergency GPS locator (e.g. ELT/EPIRB)

  - Radio communication established and confirmed with the BOC or appointed delegate.

  - Flight-following procedures implemented as described.

Fuel capacity vs. ferry distance

  - In addition to fuel required for baiting operations extra fuel, sufficient to return to Kauai, will be held at the staging site in case of an emergency.

Landing areas

  - A circle of safety will be establi at each LZ, circle of safety will have a diameter equivalent to 1.5 times the rotor length. This will be in place for the bait loading, refueling and standing sites.

  - Approach and departure paths for personnel – eg to collect the GIS data will be identified and agreed with the pilot prior to operations.

  - When possible, ground personnel will clear all Foreign Object Debris(FOD) that presents an unacceptable risk to operations prior to use. Any debris not removed will be highlighted to the pilot.

  - Non-essential personnel will not be allowed into landing areas during the operation.

Other aircraft

  - A flight plan for each bait application will be submitted to the USCG and other government agencies.

  - Pilot will alert ATC at barking sands of operations in the areas.

Wire and other aerial obstructions

  - There is no manmade aerial obstructions present around the loading site, baiting area or flight paths.

### Bird strikes

While bird strikes in helicopters are avoided where practicable, they are not uncommon because of the slow airspeed and high inertia rotor system of the helicopter. While pilot and helicopter safety is paramount, during baiting operations it is important that the pilot flys to the agreed flight lines to reduce the risk of gaps, reduce overlap/ excess use of bait and to minimize bait going into the water, this increases the likelihood of bird strikes. Most birds will actively avoid the helicopter but this is not always the case. Because of the potential safety concern to the integrity of the helicopter caused by a bird strike and the high number of larger birds present over Lehua, procedures outlined below will be followed.

Three possible situations are identified to occur in the event of a bird strike:

- The event of the strike is unknown by the pilot, and only identified after landing during an inspection.  Termed “Unknown”

- The event is felt or observed by the pilot during a flight but has not affected helicopter operations to the pilot’s knowledge.  Termed “Known”

- The event triggers an operational failure of the helicopter.  Termed “Strike Emergency”

In the event of a Known strike:

- The pilot or helicopter mechanic will notify the BOC of a strike occurrence.

- The BOC will notify the Incident Commander (directly or by radio).

- At the earliest opportunity, the helicopter will be inspected for structural integrity and flight integrity according to established protocols, by the BOC and mechanic, and verified by the pilot.

- Any mechanical irregularities will be documented and if possible corrected by the mechanic. If it’s not possible to fix the problem on site the mechanic will decide whether it is safe to continue baiting operations or whether they need to be halted until the problem can be fixed.

- Documentation of the incident and mechanical repairs implemented will be available to the Incident Commander by the Mechanic , pilot and BOC.

In the event of an Unknown strike:

This will only be identified when the pilot/ mechanic are undertaking their regular inspections of the machine during operations.

- The pilot or helicopter mechanic will notify the BOC of a strike occurrence.

- The BOC will notify the Incident Commander (directly or by radio).

- Prior to taking of again the helicopter will be inspected for structural integrity and flight integrity according to established protocols, by the BOC and mechanic, and verified by the pilot.

- Any mechanical irregularities will be documented and if possible corrected by the mechanic. If it’s not possible to fix the problem on site the mechanic will decide whether it is safe to continue baiting operations or whether they need to be halted until the problem can be fixed.

- Documentation of the incident and mechanical repairs implemented will be available to the Incident Commander by the Mechanic , pilot and BOC.

In the event of a Strike Emergency:

- Pilot will radio in MAYDAY to BOC.

- Emergency Response is initiated –refer below.

- Incident is reported to the Incident Commander.

- All actions will be documented

- Documentation of the incident will be available to the Incident Command Group.

To reduce the risk of a bird strike:

- operations will commence as early as possible in order to be completed before the warming air allows birds to glide over the island on thermals which increases as the day progresses,

- baiting will be done over the higher areas of the island first so as to complete these as early as possible.

### Flight Following

Flight following requirements will be clearly identified with the pilot prior to operations, including check-in procedures, time and location, individuals responsible for flight following, radio frequencies to be used, and any special circumstances requiring check-ins.

Flight following during baiting operations will be coordinated by the BOC. The BOC will have radio contact with the pilot to ensure status tracking between the bait loading site and Lehua Island.

Flight following during transit flights between Kauai and Niihau will be undertaken by the Aerial Operator via Spidertracks satellite flight tracking.

During baiting operations Radio Check-ins with the BOC shall be made as follows:

- At intervals, not to exceed fifteen (15) minutes.

* If it is anticipated that terrain will interfere with check-in at the landing site, the pilot may call in while still at altitude, giving a reasonable estimate of the expected time out of contact.  The pilot should confirm radio coverage as early as possible (i.e. are there any dead spots).

The radio check-in shall consist of:

- Current flight objective (baiting, returning to LZ for bait, returning to refuel, setting down on Lehua, etc…)

During in-flight operations, if check-ins cannot be made due to equipment failure, the aircraft shall return immediately to the Niihau Operational Site. Operations must not proceed until the problem is corrected and communications are established. The BOC shall immediately implement emergency response procedures for overdue or missing aircraft (see below) if check-in requirements are not met.

### Flight Tracking

The Aerial Operator will be responsible for flight tracking during the Aerial baiting operations. The flight tracking information will be used in the event of an overdue or missing aircraft incident.

Helicopter Crash

Operations will come to a FULL-STOP until further notice

- Helicopter crash over water

- Helicopter crash over land

- Helicopter pilot suffers injury or illness causing crash

Response

- BOC notifies Incident Commander immediately

- Incident Commander notified USCG, request Search and Rescue

- Incident Commander notifies all personnel to STOP and standby

- Incident Commander meets with Section Chiefs to determine response action

- Section Chiefs delegate response tasks to staff – saving life is the PRIORITY

- BOC notifies Pacific Helicopters Environmental Solutions Management:

| Vice President: | Alex Fisher Cell: 808-283-3799 |
| --- | --- |
| Chief Pilot: | Yoshi Sawanura Cell: 808-280-6353 |
| Safety Program Manager: | John Ross Cell: 406-579-8203 |

Pacific Helicopters notifies NTSB Communications Center

- If personnel are injured, Injured Persons Action Plan is implemented

Overdue Aircraft

Operations will come to a FULL-STOP until further notice

A. Helicopter exceeds ETA by fifteen minutes.

Response

1. Air Ops Supervisor attempts radio contact with pilot on all channels.

2. IF DURING BAITING – Bait Operations Chief contacts Lehua Team Leader for helicopter visual/radio contact

3. If no helicopter contact, Air Ops Supervisor notifies Incident Commander

5. Air Ops Supervisor notifies Pacific Aviation:

| Vice President: | Alex Fisher Cell: 808-283-3799 |
| --- | --- |
| Chief Pilot: | Yoshi Sawanura Cell: 808-280-6353 |
| Safety Program Manager: | John Ross Cell: 406-579-8203 |

a. Pacific Aviation notifies NTSB Communications Center at 202‐314‐6290

6. Incident Commander meets with Section Chiefs to determine response action

7. Section Chiefs delegate response tasks to staff

### Emergency Response Actions

- Assess scene safety prior to approaching the crash site. Time is a critical factor in responding to an emergency situation. Immediate positive action is necessary, delay may affect someone’s survival.

- Preserve life.

- Do whatever is necessary to extricate injured occupants, and to extinguish fires.

- Secure the area (once life is protected ie the pilot extracted, deny access except to credentialed officials).

- Deactivate the ELT/EPIRB if no longer needed.

- Determine if HazMat is onboard and request appropriate assistance.

- Utilize PPE and protective devices for potential exposure to hazards such as flammable and toxic fluids, and sharp or heavy objects.

- Do not exceed your personal physical limitations.

- Treat the area like a crime scene. Wreckage and cargo should not be removed or disturbed. Document and/or photograph the location of any debris which must be disturbed in order to carry out rescues or fire suppression. Document perishable evidence and witness information.

### Radio Communications

- All communications with the Pilot are to be through the BOC.

- All radio communications should be clear, concise and professional in manner. Please remember that transmissions may be overheard.

- Conversations should be kept to a minimum to reduce congestion.

- Radio frequencies for direct contact with the Pilot and contact via the repeater should be established and tested prior to the mission.  Also, test radio coverage.

Radio call signs are to be confirmed prior to take-off, (“Niihau Base” and the helicopter call sign) and a procedure determined for contact and sign-off confirmed between the pilot and BOC.

## Appendix 4. Aerial Operator’s Safety Plan

Printed in Air Ops Binder.

Available as separate PDF doc.

## Appendix 5. Emergency Incident Action Plan

This plan covers the procedures to be followed in the event of a person being injured on Lehua or Niihau Islands during any part of the planned rat eradication operation where they will require immediate attention and may require evacuation.

Human safety and welfare has priority over all other tasks.

Step 1 - Assess Incident:

- Assess situation, ensure it is safe before responding.

- Alert the First Aid Responder who will then contact the Incident Commander. Convey to First Aid Responder:

  - Number of patients

  - Location of incident

  - Description of incident

  - Additional resources required

  - If the First Aid Responder cannot be reached, contact the backup First Aid Responder or ask a team member to dispatch First Aid Responder.

- If it appears to be a serious incident possibly requiring evacuation, the First Aid Responder will instruct someone to call 911 right away.

- Put on PPE if appropriate.

- Initiate life-saving measures to the injured person if required: Airway, Breathing, Circulation, Disability (spinal injury) – ABCD. Do not move injured person unless there is danger of further harm or exposure at the site.

- If injuries are life threatening (problems with ABCD), proceed to Step 2.

- If injuries are non-life threatening, but require stabilization,

  - Complete a head to toe exam

  - Take vital signs

  - Take SAMPLE history (Signs and symptoms, Allergies, Medications, Past medical history, Last oral intake, Events leading up to the injury or illness).

  - Compile a SOAP note (see below) and be prepared to relay this information to remote physician.

- Protect patient from exposure.

- Proceed to Step 2.

Step 2 - Stabilize Patient/s:

- Contact a Remote Physician: Remote Medical International +1 (206) 734-3430

If necessary, arrange for a satellite phone to communicate with Physician.

- Tell them you are in an emergency situation.

- Provide them with the following phone numbers in case the call gets disconnected:

Lehua - Camp cell phone number (808-652-6515), satellite phone number (8816-326-33587) and the satellite network phone number (1-480-768-2500) (**).

Niihau – Camp cell phone number (808-358-4614), satellite phone number (8816-325-36557) and the satellite network phone number (1-480-768-2500) (**).

**To connect to a satellite phone:

Using a cell phone to call the 12-digit number directly is often not possible (the cell phone provider won’t allow it). Instead you can provide the emergency services with the satellite network number which can be called from a cell phone.

Dial the satellite network at 1-480-768-2500. A recording will answer “Welcome to the Iridium Satellite Global Network”. Enter the Iridium 12 digit satellite phone number. If the Iridium Phone is not switched on, it will connect to voicemail. The originator will pay a long distance charge to Arizona and the Iridium Phone will be billed at $1.99 per minute regardless of rate plan.

- Give the physician the following information:

  - Emergency location:

Lehua Island, Hawaii (Lat 22°00'54.972''N Long 160°05'50.676''W)

Niihau Island, Hawaii (Lat 22°00'06.192''N Long 160°05'14.748''W)

  - What the emergency is & how it happened.

  - SAMPLE history & vital signs.

  - Relevant medical history.

- Follow the physician’s instructions as they walk you through patient stabilization.

- If the physician recommends patient evacuation, continue to Step 3.

- If not, continue to Step 4.

Step 3 - Initiate Evacuation

- Call 911, if recommended by physician and 911 hasn’t yet been called.

- Tell them you are in an emergency situation.

- Provide them with the following phone numbers in case the call gets disconnected:

Lehua - Camp cell phone number (808-652-6515), satellite phone number (8816-326-33587) and the satellite network phone number (1-480-768-2500).

Niihau – Camp cell phone number (808-358-4614), satellite phone number (8816-325-36557) and the satellite network phone number (1-480-768-2500).

- Provide them with the following information:

    - Emergency location:

Lehua Island, Hawaii (Lat 22°00'54.972''N Long 160°05'50.676''W)

Niihau Island, Hawaii (Lat 22°00'06.192''N Long 160°05'14.748''W)

    - What the emergency is & how it happened.

    - That you have been in contact with a Remote Physician Service and they advised an evacuation.

    - Provide any further details given by physician relevant to the patient’s condition and any relevant medical history.

- Once evacuation has been initiated, proceed to Step 4.

Step 4 - Notify Point of Contact

- Use chart below to identify organizational point of contact.

- Describe the type of emergency, patient’s name, current status and describe how the person was injured.

- Inform them what measures have been taken to assure patient’s well-being (contact with RMI/Air One, etc) and what the next steps are.

- Once all arrangements have been made for further care, proceed to Step 5.

Table 1: Off-island Points of Contact

| Organization/Agency | Off-Island Point of Contact | Phone Numbers |
| --- | --- | --- |
| DLNR (For Mike Walker) | Rob Hauff | 808 726 3020 |
| DOFAW Kauai | Lindsey Ibara | 808-645-1649 |
| PCSU (For Patrick Chee) | David Duffy | 808-956-8218 (office) 808-754-6299 (cell) |
| USDA | Shane Siers or Lei Costales | 808- 961-4482 x34 (SS office) 808-209-1459 (SS cell) 808-319-7808 (SS cell) 808-961-4482 x22 (LC office) 808-747-2001 (LC cell) |
| USFWS | Domingo Cravalho | 808-792-9445 (office) 808-221-9667 (cell) |
| Island Conservation | Jonathan Steinberg | 831-359-4787 (office) 831-247-2323 (cell) |
| HDOA (For Scott Enright) |  |  |
| Pacific Helicopters | office | 808 871 9771 |

Step 5 - Continued care and reassessment

- Continue to care for the patient as per the physician’s advice.

- Although the patient may be stabilized, periodically reassess the patient until the evacuation has taken place.

- Keep records of all actions with the patient as well as any observations- losing consciousness, mumbling, complaining about an injury as well as vital signs – provide these to the evacuation medical staff.

## Appendix 6: Lehua Personnel Contact Information

The project is being run using a standard Incident Command System (ICS) structure which clearly lays out the lines of communication and responsibility. Unless expressly approved otherwise by the Incident Commander, all relevant communications are to follow the stated lines.

Table 1. Contact information for project personnel in ICS structure.

| Group Name | Sub-group | Position | Role | Physical Location | Assigned Personnel | Phone Number |
| --- | --- | --- | --- | --- | --- | --- |
| Incident Command Team |  | Incident Commander | Manages whole operation | Niihau | Patty Baiao | 808-3584614 |
|  |  | Operation Advisor | Ensures operation’s legal compliance, provides advice to Incident Commander | Niihau | Gregg Howald | 250-8594534 831-4207116 |
|  |  | Eradication Advisor | Ensures technical efficacy, provides advice to Baiting Operation Chief | Niihau | Pete McClelland | 808-2126451 |
|  |  | Assist. Incident Commander | Ensures operations are politically and socially acceptable | Niihau | Sheri Mann | 808-7290714 (cell) 808-2743436 (office) |
|  |  | Baiting Operation Chief | Manages bait application efficacy, including bait loading | Niihau | Tommy Hall | 831-9173123 |
|  |  | Independent Observer | Documents operations deviations, decision-making process and procedures | Niihau | Shane Siers | 808-2091459 |
| Niihau Operational Team | Aerial Operation | GIS specialist | Records, summarizes, and reports the GPS-based data | Niihau | David Will | 925-9637483 |
|  |  | Baiting Pilot | Aerially broadcasts bait, establishes helicopter safety plan | Niihau | Rob Scherzinger | 805-4441234 |
|  |  | Helicopter Mechanic | Maintain helicopter, assists with refuelling | Niihau | Mike Borge | 808-357-3128 |
|  | Bait Loading | Bait Loading Lead | Directs bait loading operations, supervises bait loading team | Niihau | Wes Jolley | 801-5562184 |
|  |  | Bait Loaders (5) | Assists bait leader | Niihau | Niihau community members Chelsea Derek Ohi Darian TBD | 808-3380701 (Mary Sue office); 808-2128902 (Mary Sue cell) |
|  |  | Ground CPA | Enforces strict compliance with EPA section 3 bait label | Niihau | Mike Walker | 808-357 3128 |
|  | Logistics/ Biosecurity | Safety Officer | Identifies, assesses, and/or anticipates hazardous and unsafe situations. | Niihau | Jason Vercelli | 808 212 4505 |
|  |  | Niihau Logistics Lead | Manages Niihau camp and operation logistics | Niihau | Wes Jolley | 801-5562184 |
|  |  | Biosecurity Officer | Implement biosecurity protocol | Niihau | Keith Robinson | 808-3381856 |
|  |  | External Communication Officer | Manages information to partners, media, and public. | Niihau | Gregg Howald | 250-8594534 831-4207116 |
| Lehua Monitoring Team | Efficacy Monitoring | Efficacy Monitoring Officer | Manages efficacy monitoring operations, supervises monitoring crew, ensures field personnel safety, collects, analyses and reports data | Lehua | Araceli Samaniego | 808 278 2099 |
|  |  | Efficacy Monitoring crew (1) | Assists Efficacy Monitoring Officer, implements monitoring | Lehua | Caleb Morrison Patrick Chee | 808 278 8181 808-3547044 (cell) |
|  | Environmental Monitoring | Env. Monitoring Officer | Manages Env. monitoring operations, supervises monitoring crew, ensures field personnel safety, collects, analyses and reports data | Lehua | Dean Foster | 808-9895309 |
|  |  | Env. Monitoring crew (1) | Assists Env. Monitoring Officer, implements monitoring | Lehua | Israel Leinbach TBD | 928-5811394 |
|  | Logistics | Lehua Team Leader/Safety Officer | Manages Lehua camp and monitoring teams logistics, ensures field personnel safety, implement biosecurity protocol, and is POC with Assistant Incident Commander | Lehua | Mele Khalsa | 808-2230494 |
| Kauai Support Team |  | Logistics/ Biosecurity Support Kauai | Assists Logistic/Biosecurity Officer and Lehua Team Leader, provides equipment and supplies to Niihau and Lehua teams, implements biosecurity protocols | Kauai | Lindsay Ibara Latham Keaweamahi (DOFAW) | 808-6451649 808-6393644 |
|  |  | Niihau Ranch Support Kauai | Assists Logistic/Biosecurity Officer regarding Niihau Ranch operations | Kauai | Mary Sue | 808-3380701 (office) 808-2128902 (cell) |

Table 2. Key contacts outside of ICS structure

| Organization | Name | Number |
| --- | --- | --- |
| UHC Global Evacuation Service | ID# 374596 | 410 453 6330 |
| Remote Medical International | ID# 19916, Island Conservation | 206 734 3430 |
| Satellite phones | Niihau Lehua | 8816 325 36557 8816 325 33587 |
| DOFAW | Josh Attwoood | 808-3884317 |
| DLNR | Suzanne Case | 808 587-0400 |
| Niihau Ranch | Bruce Robinson | 8086390685 |
| DOCARE | Kalani Addington | 808 346 7358 |
| DOCARE | Lawrence Fernandes | 808 346 0623 |
| Pacific Helicopters Environmental Solutions | Alex Fisher | 808 283 3799 cell 808 871 9771 office |
| Niihau Helicopters |  | 877-441-3500 |
| Airbourne Aaviation |  | 808-246-1088 |
| HDOA | Scott Enright Tom Matsuda | 808 854 1200 808 973 9404 |
| US Coast Guard | John Bannon | 808 522 8264 |
| DOBOR | Bruce Kelekoma Manny Andrade | 808 645 1644 808 6451642 |
| Kauai Humane Society |  | 808 632 0610 |
| Kauai Veteran’s Hospital in Waimea |  | 808 338 9431 |
| NOAA | Richard Hall Don Golden | 808 725 5018 |
| DAR | Katie Nalesere Bruce Anderson | 808 482 4297 cell 808 274 3345 office 808 341 4381 cell 808 587 0110 office |

Table 3. Off island emergency incident points of contact

| Organization/Agency | Off-Island Point of Contact | Phone Numbers |
| --- | --- | --- |
| DLNR (For Mike Walker) | Rob Hauff | 808 726 3020 |
| DOFAW Kauai | Lindsey Ibara | 808-645-1649 |
| PCSU (For Patrick Chee) | David Duffy | 808-956-8218 (office) 808-754-6299 (cell) |
| USDA | Shane Siers or Lei Costales | 808- 961-4482 x34 (SS office) 808-209-1459 (SS cell) 808-319-7808 (SS cell) 808-961-4482 x22 (LC office) 808-747-2001 (LC cell) |
| USFWS | Domingo Cravalho | 808-792-9445 (office) 808-221-9667 (cell) |
| Island Conservation | Jonathan Steinberg | 831-359-4787 (office) 831-247-2323 (cell) |
| HDOA (For Scott Enright) |  |  |
| Pacific Helicopters | office | 808 871 9771 |

## Appendix 7: Bait Spill Protocol

### Spill Response Procedures

The purpose of this section is to describe the actions that will be taken if a spill of bait containing Diphacinone 5Oppm occurs during the Lehua rat eradication operation. The Material Safety Data Sheet for DITRAC D50 is attached to this document (Appendix 1) for handling and management in case of an accidental release.

Human safety takes precedence over all response activities.

The objectives of the Bait Spill Response Plan are:

  - Define bait spills.

  - Ensure the safety of personnel and the public.

  - Control the source of the spill.

  - Contain and recover spilled material.

  - Inform partners and agencies with jurisdiction.

For this plan, a bait spill is defined as any discharge of bait above 5Kg in a localized area.

### General Response Procedures

Human Safety is the primary concern in any emergency. Before any action, evaluate the scene to ensure it is safe for personnel to enter. Take all necessary precautions for human safety.

### Terrestrial spill on Kauai, Niihau, or Lehua

The Incident Commander will coordinate an appropriate response. The following procedures are based on the Material Safety Data Sheet (SDS) for DITRAC D50 (Appendix 2) and should be followed in case of a spill on land.

- Inform the Incident Commander

- Evaluate the scene and make sure the area is safe for people to enter. Take all necessary precautions for human safety. If relevant and appropriate, stop helicopter operations until the spill is cleaned up.

- Determine if any personnel are injured and take appropriate steps to assist individual(s) if it can be done safely.

- Consult with appropriate personnel to identify the location of spill (GPS coordinates if available) and amount of bait, if possible.

- Identify and control source of spill.

- Retrieve Terrestrial Bait Spill Kit and initiate clean up. All personnel handling bait must wear appropriate PPE.

- Place spilled bait in labelled bags.

- Transport bags to a suitable area for additional containment.

- Dispose of all wastes in accordance with all local, regional and national regulations

- Inform appropriate authorities.

- Review incident/cause of spill and make any changes to minimise any risk of it being repeated.

Terrestrial Bait Spill Kit:

  - 3 brooms

  - 3dustpans

  - 4 shovels

  - 1 box industrial strength garbage bags & ties

  - 1 box labels

  - 2 Sharpies

  - 1 Storage bin (for supplies)

  - 4 plastic buckets (5 gallons)

  - 1 laminated copy of the bait label for PPE and disposal references

  - 4 pair Tyvek overalls

  - 1 box of particle size dust masks

  - 1 box nitrile gloves (Size XL to accommodate all hand sizes)

  - 4 safety goggles

There will be one Terrestrial Bait Spill Kit on Lehua island, at camp, and one on the Niihau staging area, by the loading site.

### Spill in the marine environment

The Incident Commander will coordinate an appropriate response. If the spill involves a helicopter incident — safety of the pilot and all other personnel is paramount.

The following procedures are based on the Safety Data Sheet (SDS) for DITRAC 050 and should be followed in case of a spill on the marine environment.

- Inform the Incident Commander

- Evaluate the scene and make sure the area is safe for people to enter. Take all necessary precautions for human safety. If relevant and appropriate, stop helicopter operations until the spill is cleaned up.

- Determine if any personnel are injured and take appropriate steps to assist individual(s) if it can be done safely.

- Consult with appropriate personnel to identify the location of spill (GPS coordinates if available) and amount of bait, if possible.

- Identify and control source of spill.

- Retrieve Marine Bait Spill Kit and initiate clean up. All personnel handling bait must wear appropriate PPE.

- Place spilled bait in labelled containers.

- Transport containers to a to a suitable area for additional containment.

- Dispose of all wastes in accordance with all local, regional and national regulations.

- Inform appropriate authorities.

Marine Bait Spill Kit:

  - 1 box industrial strength garbage bags and ties

  - 2 Sharpie

  - 1 storage bin (for supplies)

  - 3 medium hand nets

  - 4 plastic buckets (5 gallons)

  - 1 laminated copy of the bait label for PPE and disposal references

  - 4 pair Tyvek overalls

  - 1 box of particle size dust masks

  - 1 box nitrile gloves (Size XL to accommodate all hand sizes)

  - 4 safety goggles

The Marine Bait Spill Kit will be stored on the Niihau staging site and will deployed with any vessel transporting bait or sent to respond to a bait spill in the marine environment.

### Adverse Incident Response Procedures

For adverse effects in the marine environment notify:

- Incident Commander

- Department of Land and Natural Resources

- Division of Aquatic Resources

For marine mammals notify:

- Incident Commander

- NOAA

For human adverse effects notify:

- Incident Commander

- Kauai Veterans Memorial Hospital in Waimea;

For adverse effects to birds:

- Incident Commander

- Kauai Humane Society;

For Endangered Species notify:

- Incident Commander.

- USFWS (PIFWO)

BAIT SPILL

Marine Environment and Shoreline

On Kauai

On Niihau or Lehua

1.Notify:Incident Commander and Baiting Operations Chief

2. USCG National Response Center (24 hours): 1- 800 323-7233

3. National Marine Fisheries Service NOAA Fisheries, Honolulu

4. DLNR-DOFAW

5. State of Hawaii Dept of Agriculture, Pesticide Branch

6. For adverse effects in the marine environment Notify Department of Land and Natural Resources and Division of Aquatic Resources

7. For marine mammals notify NOAA;

8. For human adverse effects Notify the Kauai Veterans Memorial Hospital in Waimea

9. For adverse effects to birds Notify the Kauai Humane Society

10. For Endangered Species, notify USFWS (PIFWO)

Follow general response procedures. Begin bait clean-up with marine bait spill response kit stored in the staging site on Niihau

1. Notify: Incident Commander and Baiting Operations Chief

A spill kit for minor bait spills and clean up during transport will be held with the bait on Niihau Any bait collected will, if suitable, be placed into the spreader bucket for application on the target area as per all relevant approvals. If for any reason it is not suitable for application it will be bagged and returned to Kauai at the end of the project for appropriate disposal.

1. For human adverse effects Notify the Kauai Veterans Memorial Hospital in Waimea

2. For adverse effects to birds Notify the Kauai Humane Society

3. For Endangered Species, notify USFWS (PIFWO)

1. Notify: Incident Commander and Baiting Operations Chief

2. Island Conservation staff will manage clean up with resources available following general responses procedures. Begin bait clean-up with bait spill response kit stored at Niihau at the operational site or at the main camp on Lehua.

Any bait collected will, if suitable, be placed into the spreader bucket for application on the target area as per all relevant approvals. If for any reason it is not suitable for application it will be bagged and returned to Kauai at the end of the project for appropriate disposal. 1. For human adverse effects Notify the Kauai Veterans Memorial Hospital in Waimea

2. For adverse effects to birds Notify the Kauai Humane Society

3. For Endangered Species, notify USFWS (PIFWO)

BAIT SPILL

Marine Environment and Shoreline

On Kauai

On Niihau or Lehua

1.Notify:Incident Commander and Baiting Operations Chief

2. USCG National Response Center (24 hours): 1- 800 323-7233

3. National Marine Fisheries Service NOAA Fisheries, Honolulu

4. DLNR-DOFAW

5. State of Hawaii Dept of Agriculture, Pesticide Branch

6. For adverse effects in the marine environment Notify Department of Land and Natural Resources and Division of Aquatic Resources

7. For marine mammals notify NOAA;

8. For human adverse effects Notify the Kauai Veterans Memorial Hospital in Waimea

9. For adverse effects to birds Notify the Kauai Humane Society

10. For Endangered Species, notify USFWS (PIFWO)

Follow general response procedures. Begin bait clean-up with marine bait spill response kit stored in the staging site on Niihau

1. Notify: Incident Commander and Baiting Operations Chief

A spill kit for minor bait spills and clean up during transport will be held with the bait on Niihau Any bait collected will, if suitable, be placed into the spreader bucket for application on the target area as per all relevant approvals. If for any reason it is not suitable for application it will be bagged and returned to Kauai at the end of the project for appropriate disposal.

1. For human adverse effects Notify the Kauai Veterans Memorial Hospital in Waimea

2. For adverse effects to birds Notify the Kauai Humane Society

3. For Endangered Species, notify USFWS (PIFWO)

1. Notify: Incident Commander and Baiting Operations Chief

2. Island Conservation staff will manage clean up with resources available following general responses procedures. Begin bait clean-up with bait spill response kit stored at Niihau at the operational site or at the main camp on Lehua.

Any bait collected will, if suitable, be placed into the spreader bucket for application on the target area as per all relevant approvals. If for any reason it is not suitable for application it will be bagged and returned to Kauai at the end of the project for appropriate disposal. 1. For human adverse effects Notify the Kauai Veterans Memorial Hospital in Waimea

2. For adverse effects to birds Notify the Kauai Humane Society

3. For Endangered Species, notify USFWS (PIFWO)

## Appendix 8: Deviation from operational plan form, Lehua island rat eradication.

DEVIATION FROM OPERATIONAL PLAN FORM, LEHUA ISLAND RAT ERADICATION

| Requested by |  | Change # |  |
| --- | --- | --- | --- |
| Topic |  | Date Submitted Time submitted |  |

Description of Deviation (Please include Operational Plan page number)

Potential EPA Label 	violation	Yes	         No

If “No”, why not – point to the label instruction that made you conclude “No”.

If “Yes”, why?

Need to call EPA/HDOA for consultation on label interpretation?

Yes	         No

If “No” why not?

If “Yes”, who called, and when? Attach notes from discussion.

Potential legal compliance violation?	        Yes	          No

If “Yes”, which Permits

| Effect on Non-Target Risk, Efficacy, and Project Cost |  |  |
| --- | --- | --- |
| Non-target Risk | Efficacy | Project Cost |

Signatures

| Role | Name | Organization | Date | Signature |
| --- | --- | --- | --- | --- |
| Incident Commander |  |  |  |  |
| Assist. Incident Commander |  |  |  |  |
| Baiting Operation Chief |  |  |  |  |
| Operation Advisor |  |  |  |  |
| Eradication Advisor |  |  |  |  |
| Witness |  |  |  |  |

## Appendix 9: Aerial Bait Tracking Worksheet

| Aerial Bait Tracking Worksheet |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Load Number | Date | Depart Time | Arrival Time | Block ID | Heli ID | Bucket Type | Disc Size | Bait Out (kg) | Bait In (kg) | TracMap Area (ha) | Notes |

## Appendix 10: Aerial Application Wind Speed Worksheet

| Application Date: | Application Location: | Target Application Rate: |
| --- | --- | --- |

| Time | Windspeed | Wind Direction |
| --- | --- | --- |
| 0400 |  |  |
| 0500 |  |  |
| 0600 |  |  |
| 0700 |  |  |
| 0800 |  |  |
| 0900 |  |  |
| 1000 |  |  |
| 1100 |  |  |
| 1200 |  |  |
| 1300 |  |  |
| 1400 |  |  |
| 1500 |  |  |
| 1600 |  |  |
| 1700 |  |  |
| 1800 |  |  |
| 1900 |  |  |
| 2000 |  |  |

## Appendix 11: Hand baiting record sheet

| Lehua Ground Baiting Record |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Application # |  |  |  |  |  |  | Date |  |  |  |  |  |  |  |
| Sea Caves |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sea Cave 1 | Time treated |  |  |  | Weight bait used |  |  |  |  | Baiter |  |  |  |
| Sea Cave 2 | Time treated |  |  |  | Weight Bait used |  |  |  |  | Baiter |  |  |  |
| Sea cave 3 | Time treated |  |  |  | Weight bait used |  |  |  |  | Baiter |  |  |  |
| Structure | Device | Date | Person initials | # baits left | Date | Person initials | # baits left | Date | Person initials | # baits left | Date | Person initials | # baits left |  |
| Water catchment in West Gully | Bait Station |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Camp Water catchment | Bait Station |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Toilet | Bait Station |  |  |  |  |  |  |  |  |  |  |  |  |  |
| tarp shelter | Bait Station |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Weatherport 1 | Bait Station |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Weatherport 2 | Bait Station |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Weatherport 3 | Bait Station |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tent platform 1 | Hand |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tent platform 2 | Hand |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tent platform 3 | Hand |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tent platform 4 | Hand |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tent platform 5 | Hand |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Toilet 1 | Live trap |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Toilet 2 | Live trap |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Bait used |  |  |  |  |  |  |  |  |  |  |
| Broadcast | Area 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Area 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Area 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |